## Sheet1
LESSONS IDENTIFIED AND ACTIONS REGISTER
Lesson ID | Date Identified | Building / Site (if relevant) | Scenario / Event Type | Source (E.g. Exercise, Incident, Audit, Review, Hazard Planning, Debrief) | Capability Area(eg. Roles, communication, coordination) | Observation (Record a factual summary of what happened) | What Worked Well (Strengths to retain or repeat) | What Didn't Work (Capture specific gaps, issues or breakdowns observed) | Why did this occur? (Note the likely reason or contributing factor such as unclear roles, lack of information, poor communication, untested procedures, etc.) | Lesson Identified | Action Required (Record the practical step needed to address the lesson) | Linked Action ID | Action Owner (person or team responsible) | Priority (Low/Med/High based on urgency and risk) | Status (Open / In Progress / Implemented / Closed) | Due Date (Target date for completion) | Notes
LL-001 | 2026-01-30 | Building A - Main Office | Evacuation Exercise | Exercise Debrief | Communication | During the exercise, several staff were unsure where to report after evacuating the building | Wardens responded quickly and evacuation was completed safely | Staff were unclear on the assembly point location and reporting process | Assembly point information has not been reinforced recently and signage was not prominent | Initial evacuation maps and assembly point information were unclear for occupants. | Update evacuation maps and assembly point signage. Brief staff at the next safety meeting | A-001 | Facilities Manager | Medium | Open | 2026-02-28 | Contractor engaged to update maps on xx/xx/xxxx New assembly point signage design approved on xx/xx/xxxx Role out scheduled for xx/xx/xxxx
Purpose
Record lessons identified from incidents, exercises and reviews, and track improvement actions to support ongoing preparedness and continuous improvement.
Instruction Notes
Use this register to:
Record lessons identified and improvement opportunities
Assign actions and responsible owners
Track progress and completion of actions
Monitor recurring issues and capability gaps
Inform future planning, training and exercises
Review the register regularly to ensure actions are progressing and improvements are implemented.