ACKNOWLEDGEMENT 
OF COUNTRY

The Victorian Department of Treasury and Finance acknowledges that Aboriginal and Torres Strait Islander peoples are the First Peoples and Traditional Custodians of Australia, and the oldest continuing culture in human history. We proudly acknowledge Victoria’s Aboriginal communities and recognise the value and ongoing contribution of Aboriginal people and communities to Victorian life. We pay our respect to Elders past and present and emerging.

As we work to ensure Victorian Aboriginal communities continue to thrive, the Government acknowledges the invaluable contributions of generations that have come before us, who have fought tirelessly for the rights of their people and communities towards self-determination. We reflect on the continuing impact of government policies and practices and recognise our responsibility to work together with and for Aboriginal and Torres Strait Islander peoples towards improved cultural, social and economic outcomes.

‘lim-ba nindee thana warn-ga-ilee’ 
(Preserve our Dreaming Lore) – Gunnai Language

Bitja (Dixon Patten Jnr) Yorta Yorta, Gunnai, 
Gunditjmara and Dhudhuroa of Bayila Creative

The Secretary

Department of Treasury and Finance

1 Treasury Place

Melbourne, Victoria, 3002

Australia

Tel: +61 3 9651 5111

Website: budget.vic.gov.au

Authorised by the Victorian Government

1 Treasury Place, Melbourne, 3002

Printed by Valiant Doculink, Mulgrave

This publication makes reference to the 2026/27 Budget paper set which includes:

Budget Paper No. 1 – Treasurer’s Speech

Budget Paper No. 2 – Strategy and Outlook

Budget Paper No. 3 – Service Delivery

Budget Paper No. 4 – State Capital Program

Budget Paper No. 5 – Statement of Finances

(incorporating Quarterly Financial Report No. 3)

© State of Victoria 2026

(Department of Treasury and Finance)

You are free to re-use this work under a Creative Commons Attribution 4.0 licence, provided you credit the State of Victoria (Department of Treasury and Finance) as author, indicate if changes were made and comply with the other licence terms. The licence does not apply to any branding, including Government logos.

Copyright queries may be directed to information@dtf.vic.gov.au

ISSN 2204-9185 (print)

ISSN 2204-9177 (online)

Published May 2026

State Capital Program

2026-27

Presented by

Jaclyn Symes MP

Treasurer of the State of Victoria

for the information of Honourable Members

Budget Paper No. 4

TABLE OF CONTENTS

Chapter 1 – State capital program 2026-27	1

A sustainable infrastructure program	2

New investments in the 2026-27 Budget	8

Existing infrastructure projects underway	13

Ensuring infrastructure delivery remains efficient and delivers value for money	23

Summary financial tables and coverage of Budget Paper No. 4	25

Chapter 2 – General government capital program 2026-27	33

Department of Education	33

Department of Energy, Environment and Climate Action	49

Department of Families, Fairness and Housing	51

Department of Government Services	53

Department of Health	54

Department of Jobs, Skills, Industry and Regions	61

Department of Justice and Community Safety	64

Department of Premier and Cabinet	70

Department of Transport and Planning	71

Department of Treasury and Finance	79

Parliament	80

Court Services Victoria	81

Chapter 3 – Public non-financial corporations capital program 2026-27	83

Barwon Region Water Corporation	83

Cemeteries	86

Central Gippsland Region Water Corporation	89

Central Highlands Region Water Corporation	92

Coliban Region Water Corporation	95

East Gippsland Region Water Corporation	98

Gippsland and Southern Rural Water Corporation	102

Goulburn Murray Rural Water Corporation	104

Goulburn Valley Region Water Corporation	107

Grampians Wimmera Mallee Water Corporation	114

Greater Western Water Corporation	117

Homes Victoria	121

Lower Murray Urban Rural Water Corporation	123

Table of contents (continued)

Melbourne Water Corporation	126

North East Region Water Corporation	136

Port of Hastings Development Authority	140

Ports Victoria	141

South East Water Corporation	143

South Gippsland Region Water Corporation	146

State Electricity Commission of Victoria	149

State Tolling Corporation	150

Victorian Rail Track (VicTrack)	151

Wannon Region Water Corporation	156

Westernport Region Water Corporation	159

Yarra Valley Water Corporation	161

Other public non-financial corporations	163

Definitions and style conventions	165

Chapter 1 – State capital program 2026-27

Budget Paper No. 4 State Capital Program summarises the capital projects the Government will be undertaking in 2026-27 and future years.

This Budget paper includes newly announced capital projects, works already under way and those expected to finish by 30 June 2026. The information is current as at 23 April 2026.

This Government’s record capital investment and Big Build have laid the foundations for Victoria’s future productivity, liveability and economic growth.

There is a total of $181 billion in new and existing capital projects under way, with many of these projects in peak construction phase.

Several major projects have recently opened including the city-shaping Metro Tunnel and West Gate Tunnel, which have transformed the way people and goods move around the state and improved access to jobs and vital services.

The New Footscray Hospital and Frankston Hospital Redevelopment have opened to patients in the growing communities of Melbourne’s western and south-eastern suburbs.

The Government has delivered on its commitment to build 100 new schools by 2026.

The 2026-27 Budget includes $4.4 billion total estimated investment (TEI) for targeted new capital investment in critical areas including new and upgraded schools, new trains, maintaining the State’s road and rail networks, and essential health and emergency services infrastructure and equipment.

The Government is committed to a sustainable infrastructure program and returning infrastructure investment to pre-COVID levels.

Government infrastructure investment (GII) peaked at $24.2 billion in 2023-24. GII is projected to be $21.4 billion for 2025-26 and moderate to $15.3 billion by 2029-30, averaging $16.5 billion a year over the budget and forward estimates.

A sustainable pipeline of infrastructure projects will continue to provide certainty to the construction industry and maintain a steady flow of investment in social and economic infrastructure for all Victorians.

The Department of Treasury and Finance (DTF) Capital Investment Dashboard (www.dtf.vic.gov.au/capital-investment-dashboard) provides an overview of major capital projects in Victoria.

A sustainable infrastructure program

Since 2014, the Government has invested heavily in upgrading Victoria’s infrastructure.

With a number of Big Build and major projects opening in 2025-26, the 2026-27 Budget provides an additional $4.4 billion to the Government’s existing infrastructure program focusing on essential public services in locations where they are needed most.

GII is projected to be $21.4 billion for 2025-26 and moderate to $15.3 billion by 2029-30, averaging $16.5 billion a year over the budget and forward estimates.

The Government’s infrastructure program delivers the necessary level of capital investment for Victoria’s future and provides pipeline certainty and confidence to the engineering, construction and manufacturing sectors involved in building new infrastructure.

Chart 1: 	Government infrastructure investment (a)(b)(c)

Notes:

(a)	Includes general government net infrastructure investment and the estimated cash flows for public private partnership projects.

(b)	Includes the estimated private sector construction-related expenditure associated with the North East Link held in the public non-financial corporations (PNFC) sector.

(c)	Excludes the impact of the medium-term lease over the operations of the Port of Melbourne and the divestment of Victoria’s share of Snowy Hydro Limited.

Operationalising the Big Build and major projects

Since the 2025-26 Budget, several Big Build and major projects have moved from construction into operation.

The West Gate Tunnel and Metro Tunnel have transformed the way people and goods move around the state and improved access to jobs and vital services.

The Gippsland Line Upgrade, part of the $4 billion Regional Rail Revival program, is complete. Passengers now have access to 55 new weekday and 32 new weekend services, delivered through new train control systems and new platforms at Morwell and Traralgon stations.

This year marks 10 years since the Level Crossing Removal Project removed the first set of boom gates in January 2016, improving safety and easing congestion across Melbourne. The Government has now removed 88 dangerous and congested level crossings in Melbourne.

The opening of the New Footscray Hospital and the Frankston Hospital Redevelopment has added much needed inpatient capacity to the growing communities of Melbourne’s western and south-eastern suburbs.

The Government has delivered on its commitment to build 100 new schools by 2026 in the communities that need them most, with 19 new schools opened ready for students on the first day of Term 1 2026.

The Best Start, Best Life commitment to deliver 50 Early Learning Victoria centres is progressing, with another 14 centres opening their doors for children in 2026. This is in addition to the four centres that opened in 2025.

The new Nyaal Banyul Geelong Convention and Event Centre is set to host its first events this year. Major construction works have been completed, with the hotel opening on 23 January 2026 and the first events scheduled for July 2026.

Box 1: Opening the Metro Tunnel

The Metro Tunnel opened to passengers on 30 November 2025. The new tunnel has enabled an end-to-end rail line from Sunbury in the west to Cranbourne and Pakenham in the south-east, with five new stations:

Arden Station in North Melbourne

Parkville Station in Parkville

State Library Station in the CBD

Town Hall Station in the CBD

Anzac Station on St Kilda Road.

On 1 February 2026, the Big Switch timetable fully integrated the Metro Tunnel into the wider transport network. This provides 1 200 new weekly services and a turn-up-and-go network on the Sunbury, Cranbourne and Pakenham lines. During peak times, trains arrive at each of the new Metro Tunnel stations up to every three minutes, with trains running at least every 10 minutes between Watergardens and Dandenong stations in both directions for most of the day, seven days a week.

This critical infrastructure investment doubles the size of Melbourne’s underground rail network, creating a second rail line under the city and easing congestion in the City Loop for more services on other lines.

The High Capacity Metro Trains operating on the Sunbury, Cranbourne and Pakenham lines now run through the Metro Tunnel. These trains have capacity for 1 380 people which is 20 per cent more than any other train on the network. They are the only trains to operate in the Metro Tunnel, and the only trains on the network which integrate High Capacity Signalling with an existing signalling system. This is the first rollout of High Capacity Signalling on an existing network in Australia.

Box 2: Opening the West Gate Tunnel

The West Gate Tunnel opened to drivers on 14 December 2025, marking the start of faster, safer and more reliable journeys across the western suburbs.

As Melbourne’s second river crossing, the West Gate Tunnel provides an alternative to the West Gate Bridge giving direct freight access to the Port of Melbourne, reducing congestion and travel times across one of Melbourne’s main cross-city road corridors.

Since its opening, the tunnel has carried more than two and a half million vehicles, offering drivers and freight operators the choice of the tunnel or the bridge. More than 20 per cent of trips through the tunnel have been made by trucks, taking heavy vehicles off local roads and out of residential streets across Melbourne’s inner west.

For local communities, the project has delivered 14 kilometres of new and upgraded cycling and walking paths providing safe and accessible transport connections. Nine hectares of new parks and wetlands and over 17 000 new plants will further contribute to liveability in Melbourne’s west.

Box 3: Opening new health infrastructure

New Footscray Hospital

The New Footscray Hospital opened its doors on 18 February 2026, transferring services from the original Footscray Hospital site. The New Footscray Hospital supports the growing population across Melbourne’s western suburbs and reduces waiting times and pressure on nearby hospitals. The new hospital has the capacity to treat an additional 15 000 patients every year.

The new and improved hospital has more capacity, including an additional mental health and alcohol and other drugs hub as part of the emergency department, specialist facilities and clinical support spaces. It also provides expanded radiology and medical imaging services, new theatres and expanded MRI capacity. The hospital is also home to Victoria’s first fully public pathology service, supporting Western Health’s entire network.

The new hospital incorporates an education and training centre run by Victoria University to train nurses, midwives and allied health workers. It will boost skills training and employment pathways for students studying physiotherapy, speech pathology, dietetics, biomedicine and psychology. The project has also harnessed investment in complementary facilities such as the childcare centre, enhancing the experience for hospital users and the broader community.

The New Footscray Hospital gives families in the western suburbs access to quality care close to home.

Frankston Hospital Redevelopment

The Frankston Hospital Redevelopment (now known as Peninsula University Hospital) opened its new tower on 20 January 2026. It is the largest ever health infrastructure investment in Melbourne’s south-east.

The redevelopment has transformed services at the hospital, delivering a new tower with 12 levels of clinical services and new main entrance, 130 more beds, new spaces for mental health and oncology services and 15 new operating theatres. This includes new maternity, obstetrics and paediatric wards, a women’s clinic and a special care nursery.

An expansion of the emergency department includes a new mental health, alcohol and other drugs hub and a dedicated paediatric zone, providing specialist care for patients, families and carers.

The existing hospital is being refurbished for completion in early 2027 and the childcare centre and community centre will be completed by early 2028.

The redeveloped hospital has capacity to treat approximately 35 000 more patients each year.

Box 4: 10 years of level crossing removals

The Government has now removed 88 dangerous and congested level crossings in Melbourne.

This year marks 10 years since the Level Crossing Removal Project removed the first set of boom gates in January 2016, boosting safety and easing congestion across Melbourne.

The last set of boom gates on the Cranbourne and Pakenham lines at Webster Street, Dandenong were removed in October last year, with construction continuing on a new road underpass.

Four metropolitan lines are now entirely boom gate free – the Lilydale, Pakenham, Cranbourne and Sunbury lines – with the Frankston and Werribee lines set to follow. This is delivering improved safety, upgraded stations and eased congestion, transforming Melbourne's road and rail networks.

Since the 2025-26 Budget, the Government has removed three more level crossings at the following sites:

Calder Park Drive, Calder Park

Old Calder Highway, Diggers Rest

Watsons Road, Diggers Rest.

The Level Crossing Removal Project will remove 110 level crossings.

The Level Crossing Removal Project is one of the largest rail infrastructure programs in the state’s history, delivering major improvements across the rail network. Over the past decade, more than 110 million hours have been worked on level crossing removals, supporting job creation for close to 6 000 workers during peak construction.

Box 5: Best Start, Best Life Infrastructure – more Early Learning Victoria centres open

The Best Start, Best Life commitment to deliver 50 Early Learning Victoria centres is progressing, with another 14 centres opening their doors for children in 2026, in addition to the four centres that opened in 2025. Six more centres are currently in delivery for a 2027 opening.

Early Learning Victoria centres provide long daycare along with integrated Three and Four-Year-Old Kindergarten programs and are being delivered in communities that have the greatest need for more childcare places.

The 14 centres that opened in 2026 are:

Early Learning Victoria Barribina in Teesdale

Early Learning Victoria Bimbit in Werribee

Early Learning Victoria Dupitjin in Wedderburn

Early Learning Victoria Gamadji in Craigieburn

Early Learning Victoria Garrong in Kings Park

Early Learning Victoria Laak in Hallam

Early Learning Victoria Murrum in Weir Views

Early Learning Victoria Ngalambi in Noble Park

Early Learning Victoria Ngawak in Frankston

Early Learning Victoria Numurkah in Numurkah

Early Learning Victoria Shepparton in Shepparton

Early Learning Victoria Thookay Yarkeen in Portland

Early Learning Victoria Umarkoo in Wollert

Early Learning Victoria Wirmal in Clunes.

The six centres opening in 2027 are:

Early Learning Victoria Avoca (Interim Name)

Early Learning Victoria Cohuna (Interim Name)

Early Learning Victoria Meeniyan (Interim Name)

Early Learning Victoria Newborough East (Interim Name)

Early Learning Victoria Nicholson and District (Interim Name)

Early Learning Victoria Red Cliffs (Interim Name).

Box 6: Opening Nyaal Banyul Geelong Convention and Event Centre

The Nyaal Banyul Geelong Convention and Event Centre (Nyaal Banyul) will open to the public in July 2026. Major construction works are complete and finishing activities, fitout and facility testing are under way. The precinct includes a 1 000-seat theatre, exhibition spaces, meeting and conference rooms, food and beverage offerings, and the public Gheringhap Plaza, which incorporates outdoor dining, an event space and an 80-square-metre LED screen.

The build created more than 1 400 jobs, training 250 apprentices and engaging local manufacturing and construction businesses. Beyond construction, Nyaal Banyul will be a major asset and employer for the Geelong region.

The 200 room Crowne Plaza hotel located within the precinct opened in January 2026 and will accommodate event attendees and other visitors to the region. Events already scheduled include national conferences, and the strong event pipeline is expected to increase visitation and support local businesses across hospitality, tourism and other services.

The precinct is being delivered as part of the Geelong City Deal.

New investments in the 2026-27 Budget

The 2026-27 Budget adds $4.4 billion to the Government’s existing infrastructure program focusing on critical new investments in transport, education, health and emergency services.

Essential infrastructure investment in the State’s transport network

The Government continues to invest in Victoria’s passenger and freight transport networks with funding for more trains and critical maintenance and improvements.

Funding of $674 million is provided to deliver 25 additional X’Trapolis 2.0 trains to improve reliability, accessibility and passenger experience across the metropolitan train network. This adds to 25 X’Trapolis 2.0 trains being manufactured in Victoria and will support the retirement of the Comeng fleet on the Craigieburn and Upfield lines, modernising the fleet and increasing network capacity.

Other key investments include:

$181 million for V/Line to deliver control systems renewals, axle counter replacements on the Regional Rail Link and major periodic and routine maintenance works to maintain the sustainability of the regional passenger rail network

$103 million for V/Line to deliver major periodic and routine maintenance on freight rail corridors across Victoria to support the efficient movement of goods across the state

$70 million for a package of works to improve Melbourne’s tram network passenger safety and accessibility, including the delivery of more accessible tram stops and a new power substation at Wattle Park

$26 million for bus infrastructure to enable new and upgraded bus services, including in the Melton South and Casey growth areas, a package of upgraded and extended bus routes to improve coverage and connect passengers in Casey and the rollout of automatic passenger counters across the bus fleet

$10 million to address operational issues on the train network, replacing parts of Melbourne’s public transport network telecommunication assets

$7.1 million to improve connections and safety on Victoria’s public and active transport network

$5.5 million to undertake critical maintenance works on public piers and navigation aid renewals across Victoria to ensure public safety

$2 million to improve safety outcomes for regional rail passengers and staff by installing CCTV cameras at Little River Station, upgrading CCTV cameras at Ballarat Station and designing future CCTV improvements at Ballarat and Beaufort stations.

Further, funding of $124 million is provided to progress environmental approval activities and the procurement process to develop the Victorian Renewable Energy Terminal at the Port of Hastings, in support of Victoria’s offshore wind industry.

Improving roads and road safety

The Government is investing in maintaining and improving Victoria’s roads with key investments including:

$133 million to boost programmed road maintenance activities, including planned pavement renewal works, landslip repairs, routine maintenance and road resurfacing and rehabilitation as part of the total expected output and capital expenditure of $1.04 billion for road maintenance in 2026-27

$91 million for a number of high-priority upgrades on regional and metropolitan roads to improve network efficiency, road safety and travel times for road users.

Delivery is progressing on the joint Victorian and Commonwealth Government $1.2 billion Road Blitz program to upgrade roads across Victoria and better connect Melbourne’s suburbs and Victoria’s regions. The 2026-27 Budget confirms funding for commencing the Calder Park Drive Interchange Upgrade, Donnybrook Road Upgrade, and Mickleham Road Upgrade Stage 2.

Building great local schools, early childhood facilities and TAFEs for all Victorians

The 2026-27 Budget continues the Government’s investment in a quality education for all Victorians with $1 billion provided for new schools, additional stages, and upgrades to existing schools.

Funding of $392 million will be provided to build four new schools and campuses, additional stages at three recently opened schools, and planning and design for a further three new schools.

A further $104 million is provided to acquire sites for new schools and new campuses of existing schools.

Other key education capital investments in the 2026-27 Budget include:

$295 million to upgrade 31 schools across Victoria to improve educational outcomes through the provision of high-quality classrooms and facilities for learning and community use

$174 million for modular classrooms to provide additional functional spaces for learning at schools reaching their capacity

$29 million for the Accessible Buildings Program to continue to improve access to school facilities for students with disabilities and additional needs

$25 million for the Capital Works Fund

$22 million to undertake planning and development activities for new schools.

For a full list of new school and school upgrade projects refer to Chapter 2 General government capital program 2026-27.

The 2026-27 Budget invests in early childhood infrastructure with $305 million to continue the delivery of infrastructure to increase the capacity for early learning as part of the Best Start, Best Life initiative to progressively transition Four-Year-Old Kindergarten to Pre-Prep and build Early Learning Victoria centres across the state.

The 2026-27 Budget continues to invest in training facilities to ensure Victoria has the workforce it needs in critical and emerging industries. Key capital investments include:

- $25 million contributed by the State in a partnership with the Commonwealth Government to deliver the $50 million Victorian Renewable Energy TAFE Centre of Excellence at Gippsland TAFE and to upgrade the Electricity Supply Industry Training Centre at Holmesglen Institute’s Chadstone campus

- $10 million to undertake accessibility works at TAFEs across Victoria to improve access to training facilities for people with disability and additional needs, and for equipment to deliver hydrogen and battery electric vehicle training at Wodonga TAFE.

Maintaining the quality of Victoria’s health system

The 2026-27 Budget invests in sustaining hospital and healthcare services so Victorians can continue to access high quality healthcare.

Key investments include:

$75 million for the Regional Health Infrastructure Fund to renew and upgrade infrastructure across a range of rural and regional health services

$35 million for new and upgraded medical equipment, supporting operating suites, emergency departments, surgical wards, intensive care units and neonatal and maternity services in hospitals across the state

$20 million to continue upgrading and replacing essential engineering infrastructure such as boilers, air handling units and fire risk management systems at hospitals across Victoria to improve safety and reliability

$16 million to upgrade information and communications technology infrastructure to protect health services from cyber-attacks, reducing the vulnerability of hospital operations and patient data

$15 million for the Metropolitan Health Infrastructure Fund to improve the quality and amenity of infrastructure across a range of metropolitan health services, enhancing their service delivery capacity and ability to respond to local priorities

$10 million for the Mental Health and Alcohol and Other Drugs Capital Renewal Fund to improve the quality and amenity of mental health and alcohol and other drugs facilities across Victoria

$7.5 million to improve the quality, safety and amenity of Victoria’s public sector residential aged care facilities.

Box 7: Dandenong, Warragul and Wonthaggi Hospitals

Through the Hospital Infrastructure Delivery Fund announced in the 2023-24 Budget, planning work has progressed on redeveloping the Dandenong Hospital. This budget confirms an investment of $305 million to redevelop the Dandenong Hospital to boost capacity by delivering new operating theatres and an intensive care unit along with improvements to day surgery admissions. The emergency department will also be upgraded to separate paediatric, adult and mental health presentations and boost other support services. This investment will improve the quality of care and provide better access for people in the south-eastern suburbs.

The 2026-27 Budget also invests $65 million in the Wonthaggi and Warragul Hospitals to improve medical imaging, pharmacy and pathology services for Bass Coast locals and to improve amenity and maintain high-quality care for Victorians in West Gippsland.

Safe and liveable local communities

The 2026-27 Budget invests in maintaining safe and liveable local communities including funding for essential digital infrastructure.

Key investments include:

$106 million to begin a phased modernisation of the digital systems that support services for vulnerable children, young people and families

$21 million to equip specialist police with 3 000 mobile devices and upgrade Victoria Police’s evidence recording equipment

$19 million to upgrade Victoria Police’s information system used to regulate firearms, weapons and the private security industry and to integrate with the National Firearms Register

$19 million to build new and replacement Specialist Disability Accommodation homes to accommodate residents across Victoria

$11 million to undertake asset maintenance, repairs and renewal works to court buildings across Victoria.

Box 8: Strengthening our emergency services

Building on the preparation and response to the recent summer bushfire season, the 2026-27 Budget delivers a range of investments to strengthen Victoria’s emergency readiness and response capability. This will keep communities safe and support the frontline workforce and volunteers who protect lives and property.

It ensures emergency service organisations will continue to have access to modern facilities and fit for purpose vehicles and equipment, to respond quickly and safely when Victorians need them most.

Key asset investments include:

$100 million provided over the next 10 years to deliver new firefighting vehicles for the Country Fire Authority

$25 million to replace and operationalise critical fire and emergency vehicle fleet to support Forest Fire Management Victoria’s preventative bushfire service and rapid response to emergency events

$24 million to build four new Country Fire Authority stations at Charlton, Mirboo North, Kingston and Woodvale, upgrade the station at Yarrambat, plan, design and acquire land at Dereel, plan and design new stations at Barongarook West and Lakes Entrance and acquire land for the Nar Nar Goon and Beveridge CFA brigades

$16 million to deliver two Victoria State Emergency Services facilities for the Port Phillip unit and the Corio unit and acquire land for the Whitehorse unit

$10 million for new ultra-large pumper and heavy pumper fire appliances and a fireboat for Fire Rescue Victoria to support firefighting capability for built-up areas

$6 million to continue to install diesel emission capture systems across Fire Rescue Victoria fire stations, upgrade bedroom facilities at Eastern Hill and Richmond fire station and to plan and design remediation work for Eastern Hill to ensure a safe operating environment for firefighters

$2 million to replace two marine search rescue primary response vessels at Port Welshpool and Torquay.

The Government is also providing $68 million to upgrade Victoria’s Triple Zero telephony system so that Triple Zero Victoria can continue to provide timely and reliable response to emergency calls.

To maintain Victoria’s premier sporting and cultural facilities key new investments include:

$20 million to support sporting facility maintenance and asset renewal by Kardinia Park Stadium Trust and the State Sport Centres Trust

$11 million to enhance Hamer Hall to support music events.

Existing infrastructure projects underway

The Government’s existing capital pipeline continues to deliver economic and social infrastructure with many of these projects in peak construction phase.

Work is continuing on Australia’s largest urban housing renewal project as 44 ageing high-rise towers across Melbourne are replaced.

The North East Link is in peak construction with all freeway packages awarded and in delivery.

The Suburban Rail Loop is in construction with tunnelling set to begin later this year.

Manufacturing is underway for new trams and trains which will improve accessibility and cater for the future needs of metropolitan Melbourne commuters.

Twenty-five new X’Trapolis 2.0 trains are being built in regional Victoria, supporting up to 750 local jobs across the supply chain, including up to 150 in the local Ballarat area.

Major project investments over $100 million are included in the Victorian Major Projects Pipeline (Pipeline).

The Pipeline website (http://www.vic.gov.au/victorian-major-projects-pipeline) provides up-to-date information on the Government’s infrastructure pipeline, making it easier for businesses, suppliers and contractors to plan and contribute to forthcoming major projects. The Pipeline will be updated following publication of the 2026-27 Budget.

Box 9: Investment in social and affordable housing

High-rise Redevelopment Program

Australia’s largest urban renewal project, the High-rise Redevelopment Program, continues to progress as 44 ageing high rise towers across Melbourne are replaced with modern, accessible and energy-efficient homes. When complete, the Program will deliver homes for 30 000 people, tripling housing density across 39 hectares of inner-city land.

Residents in North Melbourne, Flemington, South Yarra and Richmond continue to relocate, with around 95 per cent of residents across these towers having already moved into a new home that suits their needs and preferences. From July 2026, relocations at a further seven towers across six sites in Albert Park, Flemington, Kensington, North Melbourne, Prahran and St Kilda will commence.

Demolition and rebuilding of the Elgin Towers in Carlton is being delivered in partnership with the Commonwealth Government. Demolition of the old buildings is now complete, with 95 per cent of materials produced during this process being diverted from landfill. Lendlease Construction (Southern) Pty Ltd has been appointed as the main works contractor to deliver 248 new public housing homes which are anticipated to be completed by 2028.

Big Housing Build and Regional Housing Fund

Through the Government’s $6.3 billion Big Housing Build and Regional Housing Fund, 13 300 homes are being delivered across Victoria. More than 12 000 homes are already complete or underway and over 7 000 Victorians have moved or are preparing to move into their new homes. All homes are on track to be delivered by 30 June 2028.

Targets set as part of the Big Housing Build continue to progress or have already been met. So far:

2 182 regional homes have been completed and 17 of the 18 regional local government areas have met or exceeded the Minimum Investment Guarantee

1 059 victim survivors are in new homes, exceeding the target of 1 000

914 Aboriginal Victorian households have moved in or are in the process of moving into new homes, exceeding the target of 820.

In addition, the $1 billion Regional Housing Fund currently has more than 630 homes under construction or completed. This includes the restoration of 187 previously uninhabitable homes to make them available as homes for people on the Victorian Housing Register. On top of this, the Fund is delivering 72 transitional homes to rapidly house people experiencing homelessness and 70 new social homes to support flood affected areas in Shepparton, Seymour and Rochester. When the Regional Housing Fund is complete, more than 1 300 new homes will have been delivered.

Box 10: North East Link

The North East Link is the largest investment in a road project in Victorian history. It will complete the missing link in Melbourne’s freeway network between an upgraded Eastern Freeway and the M80 Ring Road.

This new road will improve traffic flow, reduce travel time by up to 35 minutes, remove trucks from local streets and increase reliability for up to 135 000 daily freeway users. It will also deliver improved local facilities like the new Monash Tennis Centre, additional community space, Melbourne’s first dedicated busway and thousands of new trees.

Construction is underway and the two tunnel boring machines have completed over 80 per cent of tunnelling.

Major works on the associated freeway upgrades (M80 Ring Road Upgrade and the Eastern Freeway Upgrade) are underway to connect to the broader network.

Completion is expected in 2028.

The new tunnel will be tolled while the upgraded Eastern Freeway and the M80 Ring Road will remain toll free. The Commonwealth Government is contributing $5 billion to the North East Link between 2018-19 and 2029-30, including $3.25 billion for the non-tolled sections of the project.

Box 11: Suburban Rail Loop

The Suburban Rail Loop (SRL) East is being constructed between Cheltenham and Box Hill. With Melbourne’s population expected to reach nine million by the 2050s, the SRL will deliver vital public transport connections, taking cars off our roads and easing congestion on the suburban road network. Activated precincts around the six SRL East stations will deliver 70 000 more homes within walking distance of healthcare, schools and universities, public spaces and major retail and business centres.

Feedback provided through public consultation on draft structure plans for the new precincts will help shape the planning scheme amendments to be finalised in 2026.

Procurement and delivery of rail works are progressing. Tunnel boring machines have arrived and tunnelling will start this year. To date, $13 billion of construction contracts have been awarded to a range of local and international construction companies:

Initial and early works awarded to Laing O’Rourke Australia Construction Pty Ltd for $967 million (excl. GST)

Power works (Regulated Construction Power Connection Works) awarded to United Energy Group Pty Limited for $33 million (excl. GST)

Tunnelling between Cheltenham and Glen Waverley awarded to Suburban Connect, a global consortium comprising CPB Contractors, Ghella and Acciona Construction for $3.6 billion (excl. GST)

Tunnelling between Glen Waverley and Box Hill awarded to Terra Verde, a global consortium comprising WeBuild S.p.A, GS Engineering and Construction Australia, and Bouygues Construction Australia for $1.7 billion (excl. GST)

The Linewide package including tunnel fit-out, signalling, operational systems, trains, system integration and operational readiness activities awarded to John Holland Pty Ltd, TransitLinX Pty Ltd, Alstom Transport Australia Pty Ltd, Kellogg Brown & Root Pty Ltd and WSP Australia Pty Ltd for $6.7 billion (excl. GST)

The Franchise contract awarded to TransitLinX Pty Ltd, a joint venture between RATP Dev and John Holland for the operations and maintenance of the SRL East for an estimated value of $1.7 billion (net present value, excl. GST) with payments to be made over the Franchise term (2035 to 2050) and subject to a performance regime and indexation adjustments. This contract is separate to the delivery of the construction works.

There are two station contract packages in the procurement phase which will be finalised in 2026 and 2027.

SRL East is expected to cost between $30 billion and $34.5 billion. This project will be funded by one-third contributions from the State and Commonwealth governments and one-third from value-capture arrangements.

The Commonwealth Government has already committed $2.2 billion over three years and has committed to additional funding as part of the Federal Budget in May 2026. Announced State funding to date totals $11.8 billion.

The value capture arrangements to apply in SRL East precincts were announced in December 2025, and comprise existing land and windfall gains tax, infrastructure contributions, a car parking levy on car park owners from 2035, and state-initiated development. The revenue from these five value-capture mechanisms will repay up-front state borrowing over a 40-year period.

Key project achievements in 2025-26 include:

completion of the Initial and Early Works package

the arrival of several tunnel boring machines, project development, environmental and planning approvals, land acquisition, geotechnical investigations, power connection works, and works at all six station sites and the train stabling facility in Heatherton

contract award of the Linewide package which will build the fleet of high-tech SRL trains in Victoria, deliver the signalling system, and operate and maintain the SRL East network

progressing the procurement for the two station contracts – the first contract to build the stations at Glen Waverley, Burwood and Box Hill, and the second contract to build the stations at Cheltenham, Clayton and Monash

completion of the SRL East Advisory Committee hearings on the draft structure plans and draft planning scheme amendments for the areas around the future SRL East stations.

Box 12: New tram and train rolling stock

Manufacturing is underway in Dandenong for the Government’s order of 100 Next Generation Trams, which will improve accessibility and cater for the future needs of a growing Melbourne.

The Next Generation Trams will be rolled out from this year, with routes 57, 59 and 82 the first to receive these new trams. The Next Generation Trams will progressively replace the older high-floor trams, with the new trams offering more space and better accessibility for up to 150 passengers – almost double the capacity of trams currently operating in Melbourne’s west.

The purpose-built Maidstone Tram Maintenance Facility is now complete and will help maintain, clean and house the new tram fleet. The facility features rainwater collection and reuse, solar panels and recycled materials – supporting 280 local jobs during construction and ongoing maintenance.

Twenty-five new X’Trapolis 2.0 trains are being built in regional Victoria, supporting up to 750 local jobs across the supply chain, including up to 150 jobs in the local Ballarat area.

The new trains will enter passenger service this year, supporting the retirement of the Comeng fleet on the Craigieburn, Upfield and Frankston Lines, modernising the fleet and increasing network capacity.

The 2026-27 Budget provides funding for an additional 25 X’Trapolis 2.0 trains to improve reliability, accessibility and passenger experience across the metropolitan train network.

The 23 VLocity trains announced in the 2023-24 Budget have been progressively added to V/Line’s fleet. This brings the total fleet to 141 VLocity trains once completed, which will continue to help support growing demand and increasing reliability on the V/Line passenger network.

Partnerships Victoria projects

Partnerships Victoria projects continue to deliver value for money outcomes for Victorians, with more than $50 billion invested in 40 contracted projects.

Partnerships Victoria is partnering with industry across a range of sectors, including transport, energy, health, and the delivery of social housing.

Project finance will continue to play an important role in supporting the state to deliver its infrastructure pipeline, with opportunities to partner with investors to deliver social and economic infrastructure and support precinct development.

Partnering with investors brings developer expertise to complement existing state capability, unlocks supply chains and introduces new players and more competition to the Victorian infrastructure market.

The 2026-27 Budget provides funding to undertake planning and development activities for a package of new schools to be delivered under the Partnerships Victoria framework opening in 2030-31. This is supported by funding for land acquisition of new school sites required to meet enrolment demand.

Table 1 lists Partnerships Victoria projects in procurement and construction.

Table 1:	Partnerships Victoria projects in procurement and construction

Projects

Frankston Hospital Redevelopment (Stage 1 operations commenced) (a)

Gippsland Transmission (in procurement)

High Capacity Metro Trains (operations commenced) (a)

High-rise Redevelopment Program – North Melbourne (in procurement)

Homes Victoria Ground Lease Model Project 1

Homes Victoria Ground Lease Model Project 2

Metro Tunnel (operations commenced) (a)

New Footscray Hospital (operations commenced) (a)

New Melton Hospital

North East Link – Primary Package (Tunnels)

Nyaal Banyul Geelong Convention and Event Centre (operations to commence)

West Gate Tunnel (operations commenced) (a)

Note:

- Projects where operations have commenced in 2025-26.

Frankston Hospital Redevelopment (Stage 1 operations commenced)

The Frankston Hospital Redevelopment (now known as Peninsula University Hospital) is being delivered as an availability public private partnership (PPP). The Exemplar Health consortium, comprising Lendlease, Honeywell, Compass and Capella Capital, was awarded the contract. The consortium will finance, design, construct and maintain the hospital for 25 years.

The main works were completed in December 2025, with operations of the new clinical tower commencing on 20 January 2026. The existing hospital is being refurbished for completion in early 2027 and the childcare centre and community centre will be completed by early 2028.

The project is being managed by the Victorian Infrastructure Delivery Authority in conjunction with Bayside Health.

Gippsland Transmission (in procurement)

The Gippsland Transmission project presents an opportunity for energy market and infrastructure partners to design, build, finance, operate and maintain the transmission infrastructure required to connect offshore wind energy to the National Electricity Market grid.

The project is being procured as a PPP under an adaptation of the Partnerships Victoria Framework. The procurement model seeks to balance the complexity of energy infrastructure with incentives for on-time delivery that will deliver value for money to Victorian energy users.

The project is in the planning and procurement phase, with a tender process underway.

The project is being managed by VicGrid.

High Capacity Metro Trains (operations commenced)

The full fleet of 70 High Capacity Metro Trains (HCMT) has been delivered, with the trains operating on the Pakenham–Cranbourne Corridor and Sunbury Corridor. The trains now run through the Metro Tunnel to Sunbury following commissioning of the Melbourne Metro Tunnel in 2025.

The HCMT project was procured as an availability PPP. The Evolution Rail consortium, comprising Downer EDI, CRRC Changchun and Plenary, was awarded the contract. The consortium will finance, design, construct and maintain the trains for 35 years.

This project is being managed by the Department of Transport and Planning.

High-rise Redevelopment Program – North Melbourne (in procurement)

The High-rise Redevelopment Program – North Melbourne project will deliver up to 800 dwellings including at least 300 social homes.

The project is being delivered as an availability PPP under a ground lease model. The successful consortium will be responsible for designing, constructing, financing, operating and maintaining all dwellings for a period of 40 years, with Homes Victoria retaining ownership of the land and dwellings.

The State’s request for proposals for the redevelopment has closed, with appointment of a preferred strategic partner expected in 2026. Main construction works are expected to be completed by 2031.

The project is being managed by Homes Victoria.

Homes Victoria Ground Lease Model Project 1

The Homes Victoria Ground Lease Model Project 1 has delivered 1 084 dwellings at existing housing sites at Brighton, Flemington and Prahran. The project features a mix of 619 social, 119 affordable and 346 market rental dwellings, including specialist disability accommodation.

The project is being delivered as an availability PPP under a ground lease model. The Building Communities consortium comprising Tetris Capital, ICON SI (Aust) and Community Housing (Vic) Limited was awarded the contract. The consortium is responsible for designing, constructing, financing, operating and maintaining all dwellings for a period of 40 years, with Homes Victoria retaining ownership of the land and dwellings.

In August 2023, the project was expanded to deliver an additional 286 social and affordable dwellings in Flemington which are expected to be completed by the end of 2026.

A further augmentation is also underway to deliver 400 social homes and up to 300 affordable homes as part of the High-rise Redevelopment Program at the Flemington Estate. Planning is underway and main construction works are expected to be completed by 2031.

The project is being managed by Homes Victoria.

Homes Victoria Ground Lease Model Project 2

The Homes Victoria Ground Lease Model Project 2 will deliver 1 370 new dwellings at four existing housing sites in South Yarra, Prahran, Port Melbourne and Hampton East. The project features a mix of 659 social, 182 affordable and 529 market homes, including 56 specialist disability accommodation dwellings.

The project is being delivered as an availability PPP under a ground lease model. The Building Even Better Communities consortium, comprising Tetris Capital, ICON SI (Aust), Community Housing (Vic) Limited, Women’s Property Initiative and Aboriginal Community Housing (Vic) Limited, was awarded the contract. The consortium is responsible for designing, constructing, financing, operating and maintaining all dwellings for a period of 40 years, with Homes Victoria retaining ownership of the land and dwellings.

The project is currently under construction, with all sites expected to be completed by the end of 2026.

The project is being managed by Homes Victoria.

Metro Tunnel (operations commenced)

The Metro Tunnel is being delivered as an availability PPP. The Cross Yarra Partnership consortium (CYP), comprising Bouygues Construction, Capella Capital, John Holland, John Laing and Lendlease, was awarded the contract in December 2017. The consortium will finance, design, construct and maintain specific services for 25 years.

The Metro Tunnel PPP reached a major milestone in 2025-26, with the commencement of passenger services through the new twin tunnels and five underground stations on 30 November 2025.

The State continues to work with CYP to complete remaining activities, including transition to performance monitoring by the Department of Transport and Planning.

New Footscray Hospital (operations commenced)

The New Footscray Hospital is being delivered as an availability PPP.

The Plenary Health consortium, comprising Multiplex, Honeywell, Compass and Plenary, was awarded the contract. The consortium will finance, design, construct and maintain the hospital for 25 years.

Main works construction was completed in 2025 and the New Footscray Hospital commenced operations on 18 February 2026, transferring services from the original Footscray Hospital.

The project has transitioned to performance monitoring by the Department of Health.

New Melton Hospital

The New Melton Hospital will deliver high-quality care for the growing and diverse communities of Caroline Springs, Rockbank, Melton, Bacchus Marsh and Gisborne. It will include a 24-hour emergency department, with 274 beds, an intensive care unit, maternity and neonatal services, mental health services, radiology services and ambulatory care, and have the capacity to treat 130 000 patients each year.

The New Melton Hospital was procured as an availability PPP. The Exemplar Health consortium, comprising Capella Capital, Lend Lease, Invesis, Honeywell and Compass, was awarded the contract. The consortium will finance, design, construct and maintain the hospital for 25 years.

The project is currently under construction and due for completion in 2029.

The project is being managed by the Victorian Infrastructure Delivery Authority in conjunction with Western Health.

North East Link – Primary Package (Tunnels)

The Primary Package (Tunnels) is being delivered as an availability PPP incorporating an incentivised target cost regime. The Spark consortium, comprising WeBuild, GS Engineering and Construction, CPB Contractors, China Construction Oceania, Ventia, Capella Capital, John Laing Investments, DIF and Pacific Partnerships, was awarded the contract. The consortium will finance, design, construct and maintain the tunnels for 25 years.

A state-owned tolling company, the North East Link State Tolling Corporation (STC), has been established to collect tolls for the project, with toll revenue going towards repaying the cost of building and maintaining the project.

The project is currently under construction and due for completion in 2028.

The project is being managed by the Victorian Infrastructure Delivery Authority in conjunction with the Department of Transport and Planning and the STC.

Nyaal Banyul Geelong Convention and Event Centre (operations to commence)

The Nyaal Banyul was procured as an availability PPP precinct partnership. The Plenary Conventions consortium, comprising Plenary Group, Built, BGIS, Woods Bagot, WSP and 4D Workshop, was awarded the contract. The consortium will finance, design, construct and maintain the centre for 25 years.

Conventions and events will be operated by the Victorian Convention and Exhibition Trust (VCET), which also operates the Melbourne Convention and Exhibition Centre.

Major construction works have been completed, the hotel opened on 23 January 2026 and first events are scheduled for July 2026.

The project is being managed by Development Victoria and Regional Development Victoria, as part of the Geelong City Deal.

West Gate Tunnel (operations commenced)

The Transurban Group will design, construct, operate and maintain the upgraded West Gate Freeway and the new West Gate Tunnel for a 28-year period.

The project opened to traffic on 14 December 2025. The project is being managed by the Victorian Infrastructure Delivery Authority, with transition to performance monitoring by the Department of Transport and Planning.

Ensuring infrastructure delivery remains efficient and delivers value for money

Victoria continues to apply a robust assurance framework for high value and high risk government projects.

High value high risk projects

Projects identified as being high value and/or high risk (HVHR) are subject to additional rigorous scrutiny, independent review, and government approval processes in accordance with the Government’s HVHR Framework.

A number of the Government’s new investments will be assured under the HVHR Framework. The DTF website (www.dtf.vic.gov.au/infrastructure-investment) provides further information on the HVHR Framework and Gateway review process.

DTF also monitors progress and undertakes regular and targeted assurance activities on infrastructure projects. Assurance activities occur at key decision points throughout the project lifecycle, from project inception through to design, development, procurement, delivery and operations.

Table 2 lists 3 new and 51 existing projects that are monitored under the framework.

Table 2: 	New and existing high value and high risk projects

| New projects |  |
| --- | --- |
| Communities and families information technology transformation program | More new trains |
| Dandenong Hospital Redevelopment |  |

| Existing projects |  |
| --- | --- |
| Additional acute mental health beds in regional Victoria | Murray Basin Rail Project |
| Austin Hospital Emergency Department Upgrade | New Melton Hospital |
| Ballarat Health Services expansion and redevelopment | New metropolitan trains |
| Barwon Women’s and Children’s Hospital | New trains for Sunbury |
| Best Start, Best Life: Infrastructure | Next generation computer aided dispatch system for Triple Zero |
| Big Housing Build | Next Generation Trams |
| Clyde Road Upgrade | North East Link – Primary Package (Tunnels) |
| Community hospitals to give patients the best care | North East Link Connections |
| Courts case management system | Northern Hospital Redevelopment |
| Eastern Freeway Upgrade | Pakenham Roads Upgrade |
| E-Class Tram Infrastructure Program | Parkville Precinct Redevelopment |
| Enrolment Growth and New Schools (a) | Public Housing Renewal Program |
| Forensic Mental Health Expansion Project (Thomas Embling Hospital) | Public transport ticketing asset renewal |
| Frankston Hospital Redevelopment | Regional Housing Fund |
| Gippsland Transmission | Road Blitz |
| High-rise Redevelopment Program | Road Blitz to Get Families Home Sooner and Safer (Barwon Heads Road Upgrade Stage 2) |
| Homes Victoria Ground Lease Model Project 1 | Social Housing Accelerator Program |
| Homes Victoria Ground Lease Model Project 2 | South Dynon Train Maintenance Facility Stage 2 |
| M80 Ring Road Upgrade (part of North East Link packages) | Suburban Rail Loop East |
| Melbourne Airport Rail | Suburban Roads Upgrade |
| Melbourne Arts Precinct Transformation | Sunshine Station Superhub |
| Melbourne Indoor Sports Centre (Albert Park) | Technology and resources to support Victoria’s fines system |
| Melton Line Upgrade | Twenty‑five more level crossing removals |
| Men’s prison system capacity | Warrnambool Base Hospital redevelopment |
| Monash Medical Centre Redevelopment | Western Highway duplication – Ballarat to Stawell |
| More VLocity trains |  |

Note:

(a)	This includes Land acquisition for new schools, New schools construction, Relocatable Buildings Program/Modular Classrooms Program and School upgrades: growth.

Table 3 lists 12 projects that have been completed or reclassified as non HVHR since the 2025-26 Budget.

Table 3: 	Completed or reclassified high value and high risk projects

| Completed or reclassified projects |  |
| --- | --- |
| 85 by 2025 (Level Crossing Removal) | Metro Tunnel |
| Casey Hospital Emergency Department Expansion Project (a) | New Footscray Hospital |
| Gippsland Line Upgrade Stage 1 | Nyaal Banyul Geelong Convention and Event Centre |
| High Capacity Metro Trains | Shepparton Line Upgrade – Stage 3 |
| Hospital Infrastructure Delivery Fund (a) | Tram infrastructure upgrades |
| Kananook Train Maintenance Facility Stage 2 | West Gate Tunnel |

Note:

(a)	Projects that have been reclassified as non HVHR since the 2025-26 Budget.

Summary financial tables and coverage of Budget Paper No. 4

In the 2026-27 Budget, a total of $181 billion of capital projects are either commencing or already under way (refer to Table 4). These include projects in both the general government and public non-financial corporations (PNFC) sectors.

Table 4:	Infrastructure investment by total estimated investment – Summary (a)

($ thousand)

| Sector | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure |
| --- | --- | --- | --- | --- |
| General government |  |  |  |  |
| New projects | 3 056 064 | 177 497 | 1 274 117 | 1 604 450 |
| Existing projects | 51 935 903 | 27 251 421 | 10 086 029 | 15 290 283 |
| Public non-financial corporations |  |  |  |  |
| New projects | 4 541 396 | 355 341 | 1 279 010 | 2 907 047 |
| Existing projects | 120 951 533 | 31 777 766 | 14 170 024 | 75 003 743 |
| Total new projects | 7 597 460 | 532 838 | 2 553 127 | 4 511 497 |
| Total existing projects | 172 887 436 | 59 029 187 | 24 256 053 | 90 294 027 |
| Total projects (b) | 181 404 066 | 59 642 403 | 26 885 180 | 94 876 482 |

Notes:

(a)	Table may not add due to rounding.

(b)	Totals include expenditure for projects with ‘tbc’ TEIs and cash flows.

Chapter 2 General government capital program 2026-27 and Chapter 3 Public non-financial corporations capital program 2026-27 detail the general government and PNFC sector projects respectively.

The chapters list capital investments as either:

new – projects announced since the 2025-26 Budget

existing – projects that have previously been announced and construction is continuing as at 1 July 2026

completed (or expected to be completed by 30 June 2026) – for each sector, department or agency, projects which have reached practical completion since the 2025-26 Budget.

Note that the project TEIs do not include associated output funding, which may be included in other budget papers.

Expected completion dates are listed in financial years. Estimated practical completion dates are listed for new and existing projects and estimated financial completion dates are listed for completed projects.

Budget Paper No. 4 does not include capital grants paid to entities outside the Victorian Government.

In Chapter 2 General government capital program 2026-27 and Chapter 3 Public non-financial corporations capital program 2026-27, there can be differences between cash flows and the estimated completion date. These can arise because of differences between practical and financial completion dates or where funding from non-State Government sources, including the Commonwealth Government, is received in the later stages of the project after State Government funding ceases.

Movements in the state capital program

Budget Paper No. 4 2026-27 State Capital Program includes 458 projects that are funded by the Government and have been classified as either existing, completed or discontinued projects since they were last reported in the 2025-26 Budget.

Analysis of all 458 budget-funded projects shows a 0.2 per cent net increase in project costs measured since the 2025-26 Budget, and a 29 per cent variance of three months or more on project completion timeframes measured since the 2025-26 Budget.

Analysis of 123 budget-funded major projects with a TEI above $100 million shows a 0.2 per cent net increase in project costs and a 27 per cent variance of three months or more on project completion timeframes since the 2025-26 Budget.

Performance across the capital program continues to be strong in the context of elevated construction material costs in recent years. Recent cost increases in fuel and other key supply chain inputs will create escalation pressure across the construction program of all jurisdictions. The potential for such cost pressures to materialise during construction is the reason projects in Victoria include provisions for cost escalation.

Further discussion on the economic outlook is contained in Budget Paper No. 2 Economic Outlook.

Extensions to project completion timeframes reflect factors including supply chain constraints of labour, equipment and materials.

The variances to project-specific estimated completion dates and TEI amounts are explained in footnotes included in the tables in Chapter 2 General government capital program 2026-27 and Chapter 3 Public non-financial corporations capital program 2026-27.

Project TEI and estimated completion date reporting

In Chapter 2 General government capital program 2026-27 and Chapter 3 Public non-financial corporations capital program 2026-27, completion timeframes and details of project TEI are provided with estimated expenditure to 30 June 2026 and beyond, except for some project information which may not be reported where:

a project is subject to further planning, design development and early works

disclosure of capital costs may affect potential pricing of tenders from the market under a procurement process, or the cost and construction schedule is yet to be contracted

commercial arrangements affecting a project’s delivery schedule are yet to be finalised

funding consideration of future works packages is yet to occur

a project’s continuation may be subject to a review

funding based on a preliminary cost estimate has been placed in contingency and not specifically disclosed and will require final consideration before the TEI is confirmed.

Summary table of the general government capital program

The individual new and existing capital projects listed in Chapter 2 General government capital program 2026-27 and summarised in Table 5 mainly comprise projects funded by the Government through the annual budget process, where the resulting asset or infrastructure is owned and managed by a general government sector agency.

Total capital expenditure recorded in each agency’s financial statements may differ in some cases due to the agency’s reporting of other capital expenditure. This includes expenditure relating to an agency’s ongoing capital programs (such as minor works, refurbishments and vehicle fleet purchases), and capital expenditure of outer budget entities (such as individual schools and hospitals) funded through their own revenue sources, such as donations.

The Government also funds infrastructure (including major public transport infrastructure) where the resulting assets are accounted for in the PNFC sector. These projects, although funded through the annual budget process, are listed in Chapter 3 Public non-financial corporations capital program 2026-27 against the relevant PNFC entity.

The measure of general government infrastructure investment includes:

net investment in assets for the general government sector (which appears in the general government sector financial statements as cash flows from investments in non-financial assets)

capital funding provided through the budget for PNFC sector infrastructure (which appears in the general government sector financial statements as cash flows from investments in financial assets for policy purposes)

estimated private sector construction-related cash outflows on PPP projects.

Table 5: 	General government capital program 2026-27 – Summary (a)(b) 	($ thousand)

| Department/entity | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure |
| --- | --- | --- | --- | --- |
| Education |  |  |  |  |
| New projects | 1 362 346 | 17 801 | 519 157 | 825 388 |
| Existing projects | 6 870 851 | 3 814 113 | 1 786 730 | 1 270 008 |
| Energy, Environment and Climate Action |  |  |  |  |
| New projects | 68 921 | 33 942 | 34 979 | .. |
| Existing projects | 465 160 | 342 142 | 81 468 | 41 551 |
| Families, Fairness and Housing |  |  |  |  |
| New projects | 134 662 | 750 | 25 264 | 108 648 |
| Existing projects | 23 200 | 2 600 | 5 400 | 15 200 |
| Government Services |  |  |  |  |
| New projects | 17 003 | 10 000 | 7 003 | .. |
| Existing projects | 32 650 | 14 694 | 17 956 | .. |
| Health |  |  |  |  |
| New projects | 566 904 | .. | 214 277 | 352 627 |
| Existing projects | 13 086 123 | 6 065 928 | 2 217 837 | 4 802 358 |
| Jobs, Skills, Industry and Regions |  |  |  |  |
| New projects | 49 400 | 15 050 | 22 250 | 12 100 |
| Existing projects | 276 654 | 178 146 | 87 816 | 10 692 |
| Justice and Community Safety (c) |  |  |  |  |
| New projects | 389 658 | 22 467 | 147 763 | 219 428 |
| Existing projects | 2 043 466 | 1 465 537 | 368 531 | 209 398 |
| Premier and Cabinet |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 18 000 | 3 000 | 3 000 | 12 000 |
| Transport and Planning |  |  |  |  |
| New projects | 425 154 | 56 016 | 288 744 | 80 394 |
| Existing projects | 28 820 178 | 15 119 146 | 5 478 140 | 8 914 721 |
| Treasury and Finance |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 55 171 | 36 480 | 9 224 | 9 467 |
| Parliament |  |  |  |  |
| New projects | 4 060 | 1 235 | 960 | 1 865 |
| Existing projects | 18 816 | 12 706 | 1 222 | 4 888 |
| Court Services Victoria |  |  |  |  |
| New projects | 37 956 | 20 236 | 13 720 | 4 000 |
| Existing projects | 225 634 | 196 929 | 28 705 | .. |
| Total new projects | 3 056 064 | 177 497 | 1 274 117 | 1 604 450 |
| Total existing projects | 51 935 903 | 27 251 421 | 10 086 029 | 15 290 283 |
| Total projects | 54 991 967 | 27 428 918 | 11 360 146 | 16 894 733 |

Notes:

(a)	New projects funded under the Housing output are disclosed under Homes Victoria in Table 7: Public non-financial corporations capital program 2026-27 – Summary.

(b)	Table may not add due to rounding.

(c)	New, existing and completed projects previously disclosed under the Country Fire Authority and Fire Rescue Victoria have been incorporated into the Department of Justice and Community Safety.

The reconciliation of GII for the general government sector (as shown in Table 6) outlines key measures of the general government sector’s budget and forecast capital expenditure in the 2026-27 Budget.

Table 6: 	Reconciliation of general government sector capital expenditure aggregates – 2026-27 to 2029-30	($ million)

|  | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Reference |
| --- | --- | --- | --- | --- | --- |
| Estimated expenditure on general government sector projects identified in Budget Paper No. 4 | 11 360.1 | n.a. | n.a. | n.a. | Budget Paper No. 4, Chapter 1, Table 5 |
| Plus |  |  |  |  |  |
| Other capital expenditure (a) | 3 591.5 | n.a. | n.a. | n.a. |  |
| Equals |  |  |  |  |  |
| Cash flows from purchases of non-financial assets | 14 951.6 | 14 367.7 | 14 955.5 | 15 738.3 | Budget Paper No. 5, EFS cash flow statement |
| Less |  |  |  |  |  |
| Sales of non-financial assets | (770.7) | (957.4) | (922.9) | (1 126.3) | Budget Paper No. 5, EFS cash flow statement |
| Equals |  |  |  |  |  |
| Cash flows from investments in non-financial assets | 14 180.9 | 13 410.4 | 14 032.5 | 14 611.9 | Budget Paper No. 5, EFS cash flow statement |
| Plus |  |  |  |  |  |
| Net cash flows from investments in financial assets for policy purposes | 2 636.4 | 326.1 | 271.8 | 49.3 | Budget Paper No. 5, EFS cash flow statement |
| Equals |  |  |  |  |  |
| Total net investment in fixed assets | 16 817.3 | 13 736.4 | 14 304.4 | 14 661.3 | Budget Paper No. 5, EFS cash flow statement |
| Plus |  |  |  |  |  |
| PPP and other private sector co-investment (b) | 2 587.6 | 2 169.6 | 1 236.2 | 613.7 | Department of Treasury and Finance |
| Equals |  |  |  |  |  |
| Government infrastructure investment | 19 405.0 | 15 906.0 | 15 540.5 | 15 275.0 | Budget Paper No. 2, Chapter 4, Table 4.1 |

Notes:

(a)	Other capital expenditure includes: minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department; investment through regulatory bodies and part-budget-funded agencies not listed in Budget Paper No. 4; and remaining expenditure in 2026-27 for ‘Completed’ projects in addition to general government sector funded capital projects reported in Chapter 3 Public non-financial corporations capital program 2026-27. This is partially offset by factors including funding held in contingency pending confirmation of project planning and development and capital expenditure associated with public private partnerships.

(b)	Includes PPP infrastructure investment, Victorian Transport Fund-related transactions and other commercially sensitive items.

Summary table for public non-financial corporations capital program

The PNFC sector entities primarily fund infrastructure and other investments from cash flows arising from their operating activities, borrowings, proceeds from asset sales and Victorian and Commonwealth Government funding and grants.

For significant investments, PNFC entities are required to submit a detailed business case for the Treasurer’s approval. The threshold above which business cases are required is set for each entity according to a five-tiered approach, being $6 million, $20 million, $40 million, $100 million or $125 million, depending on the relative size of the PNFC entity. The five thresholds have been developed to ensure that the business case review and approval process focuses on those projects that are complex, high value and/or high risk.

Table 7 summarises the value of the capital program for PNFC entities.

Project detail is included in Chapter 3. Changes in TEI and project priorities, for example estimated completion dates, may occur from year to year, subject to approval by the entity’s board. Information for ongoing projects, such as upgrades or maintenance works, is provided by the entity based on the budget estimates period, using planning data where appropriate.

Table 7: 	Public non-financial corporations capital program 2026-27 – Summary (a)(b)

($ thousand)

| Department/entity | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure |
| --- | --- | --- | --- | --- |
| Barwon Water |  |  |  |  |
| New projects | 705 778 | 3 561 | 7 064 | 695 154 |
| Existing projects | 4 236 592 | 156 588 | 128 931 | 3 951 068 |
| Cemeteries |  |  |  |  |
| New projects | 91 110 | 3 898 | 37 704 | 49 508 |
| Existing projects | 160 646 | 38 938 | 73 966 | 47 742 |
| Central Gippsland Region Water Corporation |  |  |  |  |
| New projects | 19 430 | 863 | 953 | 17 615 |
| Existing projects | 1 032 786 | 64 219 | 98 127 | 870 440 |
| Central Highlands Region Water Corporation |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 964 595 | 83 585 | 55 511 | 825 499 |
| Coliban Region Water Corporation |  |  |  |  |
| New projects | 224 279 | 48 889 | 43 149 | 132 241 |
| Existing projects | 1 398 597 | 261 418 | 166 073 | 971 106 |
| East Gippsland Region Water Corporation |  |  |  |  |
| New projects | 13 186 | 38 | 1 000 | 12 148 |
| Existing projects | 349 440 | 50 707 | 30 583 | 268 150 |
| Gippsland and Southern Rural Water Corporation |  |  |  |  |
| New projects | 20 489 | 6 033 | 7 591 | 6 865 |
| Existing projects | 103 938 | 79 494 | 19 728 | 4 716 |
| Goulburn Murray Rural Water Corporation |  |  |  |  |
| New projects | 4 547 | .. | .. | 4 547 |
| Existing projects | 207 064 | 21 528 | 26 340 | 159 200 |
| Goulburn Valley Region Water Corporation |  |  |  |  |
| New projects | 5 581 | 36 | 35 | 5 510 |
| Existing projects | 953 414 | 92 849 | 85 979 | 774 587 |
| Grampians Wimmera Mallee Water Corporation |  |  |  |  |
| New projects | 30 187 | 16 468 | 13 719 | .. |
| Existing projects | 193 896 | 96 592 | 56 631 | 40 672 |
| Greater Western Water |  |  |  |  |
| New projects | 94 256 | 6 775 | 36 225 | 51 256 |
| Existing projects | 6 166 191 | 62 142 | 376 008 | 5 728 039 |
| Homes Victoria |  |  |  |  |
| New projects | 17 600 | 5 600 | 12 000 | .. |
| Existing projects | 6 487 625 | 4 178 124 | 1 549 580 | 759 923 |
| Lower Murray Urban and Rural Water Corporation |  |  |  |  |
| New projects | 187 360 | 76 579 | 15 499 | 95 282 |
| Existing projects | 384 002 | 21 627 | 32 478 | 329 897 |
| Melbourne Water Corporation |  |  |  |  |
| New projects | 581 649 | .. | 105 412 | 476 236 |
| Existing projects | 22 421 825 | 1 916 458 | 1 264 115 | 19 241 251 |
| North East Region Water Corporation |  |  |  |  |
| New projects | 39 500 | 2 408 | 1 778 | 35 314 |
| Existing projects | 373 241 | 127 868 | 58 230 | 187 145 |
| Port of Hastings Development Authority |  |  |  |  |
| New projects | 7 628 | 2 628 | 1 735 | 3 265 |
| Existing projects | 623 | 473 | 90 | 60 |
| Ports Victoria |  |  |  |  |
| New projects | 5 438 | 445 | 930 | 4 063 |
| Existing projects | 33 179 | 8 058 | 3 822 | 21 300 |
| South East Water Corporation |  |  |  |  |
| New projects | 517 286 | 46 379 | 16 481 | 454 426 |
| Existing projects | 3 089 386 | 383 247 | 486 337 | 2 219 802 |
| South Gippsland Region Water Corporation |  |  |  |  |
| New projects | 5 950 | .. | .. | 5 950 |
| Existing projects | 424 091 | 80 193 | 37 735 | 306 163 |
| State Electricity Commission of Victoria |  |  |  |  |
| New projects | 789 300 | 128 692 | 511 918 | 148 690 |
| Existing projects | 363 925 | 231 351 | 91 947 | 40 628 |
| State Tolling Corporation |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 14 034 000 | 9 997 524 | 2 653 866 | 1 382 610 |
| Victorian Rail Track (VicTrack) |  |  |  |  |
| New projects | 1 115 994 | .. | 418 005 | 697 990 |
| Existing projects | 52 446 036 | 12 305 343 | 5 644 801 | 34 495 893 |
| Wannon Region Water Corporation |  |  |  |  |
| New projects | 20 214 | 5 899 | 13 878 | 437 |
| Existing projects | 147 809 | 50 551 | 57 503 | 39 755 |
| Westernport Region Water Corporation |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 43 449 | 23 902 | 10 054 | 9 493 |
| Yarra Valley Water Corporation |  |  |  |  |
| New projects | .. | .. | .. | .. |
| Existing projects | 2 813 574 | 452 305 | 600 189 | 1 761 078 |
| Other public non-financial corporations |  |  |  |  |
| New projects | 44 634 | 150 | 33 934 | 10 550 |
| Existing projects | 2 121 608 | 992 682 | 561 400 | 567 526 |
| Total new projects | 4 541 396 | 355 341 | 1 279 010 | 2 907 047 |
| Total existing projects | 120 951 533 | 31 777 766 | 14 170 024 | 75 003 743 |
| Total projects | 125 492 929 | 32 133 107 | 15 449 034 | 77 910 790 |

Notes:

(a)	Totals include expenditure for projects with ‘tbc’ TEIs and cash flows.

(b)	Table may not add due to rounding.

Chapter 2 – General government capital program 2026-27

Department of Education

New projects

($ thousand)

|  |  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 |  | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Early childhood |  |  |  |  |  |  |  |
| Best Start, Best Life: Infrastructure 2026-27 (statewide) |  | 305 184 | .. | 13 554 |  | 291 630 | qtr 4 2030-31 |
| The TEI includes $300.000 million reallocated from the Best Start, Best Life: Infrastructure initiative funded in the 2023-24 Budget. |  |  |  |  |  |  |  |
| Early Childhood Worker Register (statewide) |  | 6 000 | 4 600 | 1 400 |  | .. | qtr 4 2026-27 |
| This initiative was announced in the 2025-26 Budget Update as a component of the Immediate uplift and overhaul of child safety and early childhood sector initiative. |  |  |  |  |  |  |  |
| Schools |  |  |  |  |  |  |  |
| Accessible Buildings Program (statewide) |  | 28 800 | 8 000 | 11 550 |  | 9 250 | qtr 4 2027-28 |
| Ararat Primary School – modernisation – upgrade existing school facilities (Ararat) |  | 9 358 | .. | 178 |  | 9 180 | qtr 1 2029-30 |
| Bacchus Marsh College – modernisation – upgrade existing school facilities (Bacchus Marsh) |  | 19 478 | 745 | 6 490 |  | 12 243 | qtr 1 2028-29 |
| The TEI includes $0.745 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Boroondara Park Primary School – modernisation – upgrade existing school facilities (Balwyn North) |  | 16 542 | 641 | 5 512 |  | 10 389 | qtr 1 2028-29 |
| The TEI includes $0.641 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Brighton Beach Primary School – modernisation – upgrade existing school facilities (Brighton) |  | 16 846 | .. | 326 |  | 16 520 | qtr 1 2029-30 |
| Capital Works Fund – funding for small-scale capital projects and the next round of the Fund (2026-27) (statewide): |  | 25 410 | .. | 12 702 |  | 12 708 | qtr 4 2027-28 |
| - Boronia K-12 College - Briagolong Primary School - Bundarra Primary School - Cambridge Primary School - Cardross Primary School - Carwatha College P-12 - Diamond Creek East Primary School - Drysdale Primary School | - Dunkeld Consolidated School - Essendon Keilor College - Fountain Gate Primary School - Heathmont East Primary School - Hesket Primary School - Manor Lakes P-12 College - Mansfield Primary School - Melbourne High School |  |  |  | - Miners Rest Primary School - Monbulk College - Sherbourne Primary School - Southern Cross Primary School - Stratford Primary School - Toolangi Primary School - Wheelers Hill Secondary College - Wonga Park Primary School |  |  |
| Cheltenham East Primary School – modernisation – upgrade existing school facilities (Cheltenham) |  | 10 584 | .. | 402 |  | 10 182 | qtr 1 2029-30 |
| Daylesford Primary School – modernisation – upgrade existing school facilities (Daylesford) |  | 6 786 | .. | 154 |  | 6 632 | qtr 4 2028-29 |
| Eaglehawk Primary School – modernisation – upgrade existing school facilities (Eaglehawk) |  | 694 | .. | 44 |  | 650 | qtr 2 2028-29 |
| Edithvale Primary School – modernisation – upgrade existing school facilities (Edithvale) |  | 1 341 | .. | 1 341 |  | .. | qtr 3 2028-29 |
| Essendon North Primary School – modernisation – upgrade existing school facilities (Essendon North) |  | 24 005 | .. | 452 |  | 23 553 | qtr 1 2029-30 |
| Hastings Primary School – modernisation – upgrade existing school facilities (Hastings) |  | 1 652 | .. | 1 652 |  | .. | qtr 3 2028-29 |
| Keilor Heights Primary School – modernisation – upgrade existing school facilities (Keilor East) |  | 10 567 | .. | 394 |  | 10 173 | qtr 1 2029-30 |
| Keysborough Gardens Primary School – modernisation – upgrade existing school facilities (Keysborough) |  | 8 064 | .. | 328 |  | 7 736 | qtr 3 2028-29 |
| Kismet Park Primary School – modernisation – upgrade existing school facilities (Sunbury) |  | 11 068 | .. | 208 |  | 10 860 | qtr 1 2029-30 |
| Land acquisition (various) |  | 104 022 | .. | 61 212 |  | 42 810 | qtr 4 2028-29 |
| The TEI includes $1.880 million reprioritised from the Land acquisition (2025-26) initiative. The TEI includes $10.000 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |  |  |
| Locally driven education programs (various) |  | 315 | .. | 180 |  | 135 | qtr 2 2029-30 |
| Maribyrnong College – modernisation – upgrade existing school facilities (Maribyrnong) |  | 14 306 | 554 | 4 767 |  | 8 985 | qtr 2 2028-29 |
| The TEI includes $0.554 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Maryborough Education Centre – modernisation – upgrade existing school facilities (Maryborough) |  | 18 097 | 664 | 6 041 |  | 11 392 | qtr 1 2028-29 |
| The TEI includes $0.664 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Melton Primary School – modernisation – upgrade existing school facilities (Melton) |  | 11 290 | 454 | 3 772 |  | 7 064 | qtr 2 2028-29 |
| The TEI includes $0.454 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Merri-bek Primary School – modernisation – upgrade existing school facilities (Coburg) |  | 6 179 | .. | 143 |  | 6 036 | qtr 4 2028-29 |
| Modular Classrooms Program (statewide) |  | 173 699 | .. | 173 699 |  | .. | qtr 4 2026-27 |
| Moomba Park Primary School – modernisation – upgrade existing school facilities (Fawkner) |  | 314 | .. | 314 |  | .. | qtr 1 2027-28 |
| Mornington Park Primary School – modernisation – upgrade existing school facilities (Mornington) |  | 331 | .. | 36 |  | 295 | qtr 4 2027-28 |
| Mount Waverley North Primary School – modernisation – upgrade existing school facilities (Mount Waverley) |  | 10 660 | 437 | 3 560 |  | 6 663 | qtr 2 2028-29 |
| The TEI includes $0.437 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| New schools construction (statewide) |  | 391 759 | .. | 178 085 |  | 213 674 | qtr 1 2029-30 |
| To open in 2028: - Rockbank Toolern Road Primary School (Interim Name) - Thompsons East Primary School (Interim Name) - Wollahra Secondary School (Interim Name) |  |  | New campus construction to open in 2029: - South Melbourne Primary School |  |  |  |  |
| Additional stages of new schools: - Homestead Senior Secondary College - Wulerrp Secondary College - Yubup Primary School |  |  | Planning and early works: - Arden Secondary School (Interim Name) - Pattersons Road Secondary School (Interim Name) - Preston High School (New Campus) |  |  |  |  |
| The TEI includes $107.652 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |  |  |
| Pakenham Consolidated School – modernisation – upgrade existing school facilities (Pakenham) |  | 450 | .. | 450 |  | .. | qtr 3 2027-28 |
| Planning for future new schools (statewide) |  | 21 600 | .. | 8 140 |  | 13 460 | qtr 1 2028-29 |
| Planning for school upgrades (statewide): - Bendigo Senior Secondary College - Eltham East Primary School - Glenroy College - Marlborough Primary School |  | 1 000 | .. | 1 000 |  | .. | qtr 3 2026-27 |
| Rebuilding the Victorian Curriculum and Assessment Authority (VCAA) (statewide) |  | 870 | .. | 870 |  | .. | qtr 4 2026-27 |
| Replacement of VRQA State Register (statewide) |  | 3 700 | .. | 3 700 |  | .. | qtr 4 2026-27 |
| Sherbrooke Community School – modernisation – upgrade existing school facilities (Sassafras) |  | 9 719 | 429 | 3 675 |  | 5 615 | qtr 2 2028-29 |
| The TEI includes $0.429 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Spensley Street Primary School – modernisation – upgrade existing school facilities (Clifton Hill) |  | 1 038 | .. | 52 |  | 986 | qtr 3 2028-29 |
| St Kilda Primary School – modernisation – upgrade existing school facilities (St Kilda) |  | 13 173 | .. | 493 |  | 12 680 | qtr 1 2029-30 |
| Stawell Primary School – modernisation – upgrade existing school facilities (Stawell) |  | 12 397 | .. | 248 |  | 12 149 | qtr 1 2029-30 |
| Surfside Primary School – modernisation – upgrade existing school facilities (Ocean Grove) |  | 11 645 | .. | 234 |  | 11 411 | qtr 1 2029-30 |
| Vermont Primary School – modernisation – upgrade existing school facilities (Vermont) |  | 15 514 | 596 | 5 173 |  | 9 745 | qtr 2 2028-29 |
| The TEI includes $0.596 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Wales Street Primary School – modernisation – upgrade existing school facilities (Thornbury) |  | 21 286 | .. | 404 |  | 20 882 | qtr 1 2029-30 |
| Warragul North Primary School – modernisation – upgrade existing school facilities (Warragul) |  | 6 965 | 299 | 2 659 |  | 4 007 | qtr 2 2028-29 |
| The TEI includes $0.299 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Warranwood Primary School – modernisation – upgrade existing school facilities (Warranwood) |  | 344 | .. | 36 |  | 308 | qtr 4 2027-28 |
| Yarrawonga College P-12 – modernisation – upgrade existing school facilities (Yarrawonga) |  | 9 294 | 382 | 3 527 |  | 5 385 | qtr 2 2028-29 |
| The TEI includes $0.382 million reprioritised from the Planning future school upgrades initiative funded in the 2025-26 Budget. |  |  |  |  |  |  |  |
| Total new projects |  | 1 362 346 | 17 801 | 519 157 |  | 825 388 |  |

Source: Department of Education

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Early childhood |  |  |  |  |  |
| Best Start, Best Life: Infrastructure 2023-24 (statewide) | 1 942 791 | 485 382 | 356 896 | 1 100 513 | qtr 4 2030-31 |
| The TEI has decreased by $276.901 million due to $300.000 million being reprioritised to the Best Start, Best Life: Infrastructure 2026-27 initiative and $1.001 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by $24.100 million Commonwealth Government funding from the Building Early Education Fund (BEEF). The Pre-Prep element of Best Start, Best Life is a 15-year infrastructure program with an overall program completion date of 2036-37. |  |  |  |  |  |
| Ready for school: Kinder for every three-year-old 2019-20 (statewide) | 273 009 | 240 649 | 32 360 | .. | qtr 4 2026-27 |
| The TEI has decreased by $4.645 million due to $4.651 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by a TEI increase of $0.006 million due to a revised project scope, funded by co-contributions from local councils. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. The TEI includes $0.576 million in co-contributions from schools and a total of $3.488 million in co-contributions from local councils. |  |  |  |  |  |
| Ready for school: kinder for every three-year-old 2023-24 (statewide) | 208 402 | 64 151 | 133 798 | 10 453 | qtr 3 2027-28 |
| The TEI has decreased by $0.027 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Schools |  |  |  |  |  |
| Accessible Buildings Program 2025-26 (statewide) | 18 153 | 8 903 | 9 250 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.347 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Albert Park College and the Victorian College of the Arts Secondary School 2021-22 (Albert Park) | 17 489 | 2 805 | 12 502 | 2 182 | qtr 2 2027-28 |
| The estimated completion date has been revised to quarter 2 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Ashwood High School 2020-21 (Ashwood) | 15 995 | 14 624 | 1 097 | 274 | qtr 1 2027-28 |
| The estimated completion date has been revised to quarter 1 2027-28 in line with a revised project schedule. The TEI includes a total of $2.501 million in co-contributions from the school. |  |  |  |  |  |
| Beechworth Secondary College 2024-25 (Beechworth) | 6 400 | 3 526 | 2 863 | 11 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Belmont High School 2025-26 (Belmont) | 11 200 | 3 301 | 6 834 | 1 065 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Bethal Primary School 2023-24 (Meadow Heights) | 11 000 | 2 838 | 7 289 | 873 | qtr 1 2027-28 |
| The estimated completion date has been revised to quarter 1 2027-28 in line with a revised project schedule. The TEI includes a total of $0.500 million in co-contributions from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Broadford Primary School 2025-26 (Broadford) | 13 700 | 1 405 | 11 064 | 1 231 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Buckley Park College 2025-26 (Essendon) | 19 286 | 2 428 | 16 360 | 498 | qtr 1 2027-28 |
| Camberwell Primary School 2024-25 (Camberwell) | 9 700 | 7 710 | 1 974 | 16 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Camp Hill Primary School 2024-25 (Bendigo) | 4 100 | 985 | 3 074 | 41 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Capital Works Fund 2024-25 (statewide) | 24 199 | 21 746 | 2 453 | .. | qtr 2 2026-27 |
| The TEI has decreased by $0.801 million due to $0.964 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by $0.163 million to extend the scope for additional school requirements, funded by co-contributions from schools. |  |  |  |  |  |
| Capital Works Fund 2025-26 (statewide) | 25 000 | 1 634 | 23 366 | .. | qtr 4 2026-27 |
| Carrington Primary School 2025-26 (Knoxfield) | 13 900 | 2 648 | 8 264 | 2 988 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Caulfield South Primary School 2025-26 (Caulfield South) | 9 000 | 1 741 | 7 034 | 225 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Clayton South Primary School 2024-25 (Clayton South) | 12 450 | 5 237 | 6 989 | 224 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Cobden Technical School 2024-25 (Cobden) | 6 947 | 1 944 | 4 889 | 114 | qtr 4 2026-27 |
| The TEI has increased by $0.347 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2024-25. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Colac West Primary School 2025-26 (Colac) | 10 200 | 2 038 | 8 026 | 136 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Collingwood College 2025-26 (Collingwood) | 6 890 | 1 308 | 5 543 | 39 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Contingency fund for school upgrades 2023-24 (statewide) | 8 843 | 3 871 | 3 881 | 1 091 | qtr 3 2027-28 |
| The TEI has decreased by $1.268 million due to a reprioritisation of funds to the Emerald Secondary College 2023-24 initiative. The estimated completion date has been revised to quarter 3 2027-28 in line with a revised schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Contingency fund for school upgrades 2024-25 (statewide) | 6 202 | 2 578 | 3 549 | 75 | qtr 4 2026-27 |
| The TEI has decreased by $2.323 million due to a reprioritisation of funds to five school upgrades projects. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised schedule. This initiative is part of Labor's Financial Statement 2022. |  |  |  |  |  |
| Contingency fund for school upgrades 2025-26 (statewide) | 10 722 | 1 396 | 7 698 | 1 628 | qtr 1 2027-28 |
| The TEI has decreased by $1.685 million due to a reprioritisation of funds to the White Hills Primary School 2025-26 initiative. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Cranbourne Secondary College 2024-25 (Cranbourne) | 9 137 | 7 490 | 1 637 | 10 | qtr 1 2026-27 |
| The TEI has increased by $0.137 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2024-25. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Diggers Rest Primary School 2022-23 (Diggers Rest) | 13 443 | 6 322 | 7 054 | 67 | qtr 3 2026-27 |
| Drouin Secondary College 2025-26 (Drouin) | 11 700 | 3 170 | 7 984 | 546 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Eastbourne Primary School 2024-25 (Capel Sound) | 9 500 | 4 492 | 4 989 | 19 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Edenhope College 2025-26 (Edenhope) | 13 100 | 1 761 | 10 237 | 1 102 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Eildon Primary School 2024-25 (Eildon) | 4 800 | 3 686 | 1 107 | 7 | qtr 1 2026-27 |
| The estimated completion date has been revised to quarter 1 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Emerald Secondary College 2023-24 (Emerald) | 10 038 | 2 312 | 6 772 | 954 | qtr 4 2026-27 |
| The TEI has increased by $1.268 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2023-24. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Epsom Primary School 2020-21 (Epsom) | 573 | 114 | 385 | 74 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Essential maintenance and compliance 2024-25 (statewide) | 5 702 | 4 884 | 818 | .. | qtr 4 2026-27 |
| Exford Primary School 2020-21 (Exford) | 27 745 | 26 725 | 996 | 24 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Feasibility study for a maths and science school in the north-west of Melbourne 2025-26 (metropolitan various) | 1 000 | 20 | 100 | 880 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Fighting for students with disability and their families 2023-24 (statewide) | 25 000 | 3 025 | 21 562 | 413 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Gardenvale Primary School 2025-26 (Brighton East) | 11 700 | 1 548 | 7 217 | 2 935 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Gladstone Park Secondary College 2024-25 (Gladstone Park) | 11 700 | 4 464 | 7 124 | 112 | qtr 2 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Hallam Secondary College 2023-24 (Hallam) | 28 114 | 4 795 | 15 098 | 8 221 | qtr 3 2027-28 |
| The TEI has increased by $3.914 million due to a reprioritisation from the Contingency for school upgrades re-tendering 2023-24 initiative completed in the 2025-26 Budget. The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Hampton Primary School 2025-26 (Hampton) | 10 100 | 2 070 | 6 902 | 1 128 | qtr 4 2026-27 |
| The TEI has increased by $0.300 million to extend the scope for additional school requirements, funded by a co-contribution from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Hazel Glen College 2025-26 (Doreen) | 2 400 | 1 919 | 397 | 84 | qtr 2 2026-27 |
| The TEI has increased by $1.600 million to extend the scope for additional school requirements, funded by a co-contribution from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Heidelberg Primary School 2024-25 (Heidelberg) | 14 070 | 8 365 | 5 584 | 121 | qtr 2 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| James Cook Primary School 2024-25 (Endeavour Hills) | 9 100 | 2 622 | 6 423 | 55 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| John Fawkner Secondary College 2023-24 (Fawkner) | 15 535 | 11 517 | 4 000 | 18 | qtr 2 2026-27 |
| The TEI has increased by $1.035 million due to a reprioritisation from the Contingency for school upgrades re-tendering 2023-24 initiative completed in the 2025-26 Budget. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Koonung Secondary College 2023-24 (Mont Albert North) | 8 900 | 5 854 | 3 033 | 13 | qtr 1 2026-27 |
| The estimated completion date has been revised to quarter 1 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Kurunjang Secondary College 2025-26 (Kurunjang) | 10 700 | 1 367 | 8 131 | 1 202 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Lakes Entrance Primary School 2025-26 (Lakes Entrance) | 6 600 | 1 113 | 4 733 | 754 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Land Acquisition 2021-22 (various) | 290 008 | 223 580 | 47 000 | 19 428 | qtr 4 2027-28 |
| The TEI has decreased by $5.495 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 due to land acquisition timelines. |  |  |  |  |  |
| Land acquisition 2022-23 (various) | 250 546 | 238 242 | .. | 12 304 | qtr 4 2027-28 |
| The TEI has decreased by $0.085 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 due to land acquisition timelines. The TEI includes $16.700 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |
| Land acquisition 2024-25 (various) | 68 924 | 46 918 | 21 472 | 534 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29 due to land acquisition timelines. The TEI includes $44.528 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |
| Land acquisition 2025-26 (various) | 235 496 | 60 114 | 156 452 | 18 930 | qtr 1 2028-29 |
| The TEI has decreased by $1.880 million due to a reprioritisation to the Land acquisition 2026-27 initiative. |  |  |  |  |  |
| Leongatha Secondary College 2025-26 (Leongatha) | 11 700 | 2 577 | 6 402 | 2 721 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Lismore Primary School 2025-26 (Lismore) | 1 800 | 499 | 1 071 | 230 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Lyndhurst Secondary College 2024-25 (Cranbourne) | 15 175 | 2 252 | 12 541 | 382 | qtr 4 2026-27 |
| The TEI has increased by $1.575 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2024-25. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Manorvale Primary School 2025-26 (Werribee) | 12 100 | 2 071 | 8 681 | 1 348 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| McKinnon Primary School 2025-26 (McKinnon) | 12 600 | 1 988 | 9 165 | 1 447 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Melba Secondary College 2025-26 (Croydon) | 12 700 | 2 213 | 9 019 | 1 468 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Melton South Primary School 2025-26 (Melton South) | 21 300 | 4 342 | 13 495 | 3 463 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Merri Creek Primary School 2022-23 (Fitzroy North) | 5 352 | 1 079 | 4 151 | 122 | qtr 4 2026-27 |
| Middle Park Primary School 2024-25 (Middle Park) | 8 800 | 6 424 | 2 363 | 13 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mordialloc College 2025-26 (Mordialloc) | 12 600 | 1 419 | 8 005 | 3 176 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mount Eliza North Primary School 2025-26 (Mount Eliza) | 11 700 | 590 | 7 014 | 4 096 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mount Erin Secondary College 2025-26 (Frankston) | 5 000 | 812 | 3 603 | 585 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mount Waverley Primary School 2023-24 (Mount Waverley) | 5 860 | 2 647 | 2 202 | 1 011 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mullauna Secondary College 2025-26 (Mitcham) | 17 600 | 2 538 | 10 274 | 4 788 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| New schools construction 2023-24 (statewide) | 755 866 | 630 726 | 124 325 | 815 | qtr 3 2026-27 |
| The TEI has decreased by $4.505 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The 2025 opening schools included in this initiative opened at the start of 2025, and the 2026 opening schools included in this initiative opened at the start of 2026. |  |  |  |  |  |
| New schools construction 2024-25 (statewide) | 928 779 | 797 464 | 130 757 | 558 | qtr 2 2026-27 |
| The TEI has decreased by $5.853 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $35.472 million from the Growth Areas Infrastructure Contribution. The 2026 opening schools included in this initiative opened at the start of 2026. |  |  |  |  |  |
| New schools construction 2025-26 (statewide) | 336 406 | 126 861 | 205 525 | 4 020 | qtr 3 2026-27 |
| Orchard Grove Primary School 2025-26 (Blackburn South) | 13 500 | 2 394 | 9 599 | 1 507 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Pakenham Secondary College 2023-24 (Pakenham) | 11 300 | 8 425 | 2 854 | 21 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Place-based education and wellbeing programs 2024-25 (various) | 300 | 180 | 120 | .. | qtr 4 2026-27 |
| Planning for inner city growth and minor works 2024-25 (metropolitan Melbourne) | 1 639 | 1 056 | 582 | 1 | qtr 4 2026-27 |
| The TEI has increased by $0.027 million due to a TEI increase of $0.111 million due to a revised project scope, funded by co-contributions from the school, partially offset by $0.084 million being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Planning future school upgrades 2025-26 (statewide) | 4 799 | 4 517 | .. | 282 | qtr 4 2025-26 |
| The TEI has decreased by $5.201 million due to a reprioritisation to 10 school upgrades projects. |  |  |  |  |  |
| Preston Primary School 2023-24 (Preston) | 3 700 | 1 329 | 2 339 | 32 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Rangebank Primary School 2025-26 (Cranbourne) | 6 300 | 1 205 | 4 372 | 723 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Relocatable Buildings Program 2024-25 (statewide) | 160 413 | 159 578 | 835 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.588 million to extend the scope for additional school requirements, funded by a co-contribution from the school. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| San Remo Primary School 2025-26 (San Remo) | 5 300 | 1 522 | 3 202 | 576 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| School upgrades – established area growth for 2027 (statewide) | 91 614 | 56 255 | 34 734 | 625 | qtr 4 2026-27 |
| The TEI has increased by $1.858 million due to a reprioritisation from the Contingency for school upgrades re-tendering 2023-24 initiative completed in the 2025-26 Budget. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| School upgrades – expansions 2024-25 (statewide) | 46 381 | 16 137 | 28 006 | 2 238 | qtr 3 2027-28 |
| School upgrades: expansions – upgrade three schools to provide additional permanent capacity (metropolitan various) | 47 774 | 1 009 | 21 870 | 24 895 | qtr 1 2027-28 |
| School upgrades – growth for 2025 (statewide) | 56 350 | 39 254 | 13 905 | 3 191 | qtr 2 2027-28 |
| The estimated completion date has been revised to quarter 2 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Seaford North Primary School 2024-25 (Seaford) | 18 200 | 15 092 | 3 078 | 30 | qtr 2 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Special school upgrades 2022-23 (statewide) | 332 969 | 315 133 | 12 237 | 5 599 | qtr 4 2027-28 |
| The TEI has increased by $1.651 million to extend the scope for additional school requirements, funded by co-contributions from schools. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. The TEI includes a total of $7.006 million of co-contributions from schools. |  |  |  |  |  |
| Stawell West Primary School 2025-26 (Stawell) | 4 700 | 912 | 3 216 | 572 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Tallangatta Primary School 2023-24 (Tallangatta) | 4 100 | 3 143 | 949 | 8 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Thornbury Primary School 2024-25 (Thornbury) | 17 600 | 10 581 | 6 921 | 98 | qtr 2 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Toolern Vale and District Primary School 2024-25 (Toolern Vale) | 6 420 | 2 510 | 3 871 | 39 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Traralgon (Kosciuszko Street) Primary School 2024-25 (Traralgon) | 6 800 | 4 302 | 2 487 | 11 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| University Park Primary School 2023-24 (St Albans) | 7 400 | 3 906 | 3 454 | 40 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Victorian College For The Deaf 2020-21 (Melbourne) | 11 600 | 3 919 | 7 577 | 104 | qtr 2 2026-27 |
| The TEI has increased by $1.600 million to extend the scope for additional school requirements, funded by a co-contribution from the school. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Wangaratta High School 2025-26 (Wangaratta) | 11 700 | 3 003 | 7 521 | 1 176 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Warringa Park School 2021-22 (Werribee South) | 3 000 | 3 | 2 000 | 997 | qtr 1 2028-29 |
| The estimated completion date has been revised to quarter 1 2028-29 due to land acquisition timelines. |  |  |  |  |  |
| White Hills Primary School 2025-26 (White Hills) | 10 915 | 543 | 8 280 | 2 092 | qtr 4 2026-27 |
| The TEI has increased by $1.685 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2025-26. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Whittlesea Secondary College 2024-25 (Whittlesea) | 11 700 | 6 963 | 4 214 | 523 | qtr 2 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Yarraville West Primary School 2025-26 (Yarraville) | 493 | .. | 493 | .. | qtr 1 2027-28 |
| Yinnar Primary School 2022-23 (Yinnar) | 7 337 | 1 403 | 5 161 | 773 | qtr 1 2027-28 |
| The estimated completion date has been revised to quarter 1 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Total existing projects | 6 870 851 | 3 814 113 | 1 786 730 | 1 270 008 |  |
| Total Education projects | 8 233 197 | 3 831 914 | 2 305 887 | 2 095 396 |  |
| Other capital expenditure | n.a. | n.a. | 125 686 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department in addition to remaining expenditure in 2026-27 for Completed projects. |  |  |  |  |  |
| Total 2026-27 Education capital expenditure |  |  | 2 431 573 |  |  |

Source: Department of Education

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Early childhood |  |  |  |
| Ready for school: kinder for every three-year-old 2021-22 (statewide) | 44 819 | 44 819 | qtr 4 2026-27 |
| Schools |  |  |  |
| Accessible Buildings Program 2024-25 (statewide) | 15 000 | 15 000 | qtr 4 2026-27 |
| Aldercourt Primary School 2023-24 (Frankston North) | 3 800 | 3 800 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Ararat Secondary College 2023-24 (Ararat) | 4 690 | 4 269 | qtr 1 2027-28 |
| The TEI includes a total of $0.090 million in co-contributions from the school. |  |  |  |
| Bayswater South Primary School 2023-24 (Bayswater) | 11 070 | 7 768 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Carlton North Primary School 2024-25 (Carlton North) | 9 250 | 8 323 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Cheltenham Secondary College 2023-24 (Cheltenham) | 7 300 | 6 452 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Darley Primary School 2022-23 (Darley) | 10 678 | 10 678 | qtr 1 2026-27 |
| Eltham High School 2023-24 (Eltham) | 8 940 | 8 872 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Essendon Primary School 2024-25 (Essendon) | 2 783 | 2 598 | qtr 4 2026-27 |
| The TEI has increased by $0.183 million due to a revised project scope, including $0.055 million funded by a co-contribution from the school and $0.128 million reprioritised from the Contingency fund for school upgrades 2024-25. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Essential maintenance and compliance 2023-24 (statewide) | 80 468 | 80 468 | qtr 4 2026-27 |
| The TEI has increased by $0.243 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. |  |  |  |
| Fitzroy Primary School 2024-25 (Fitzroy) | 6 600 | 5 382 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Footscray West Primary School 2023-24 (West Footscray) | 9 400 | 9 229 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Forest Hill College 2023-24 (Burwood East) | 10 900 | 7 675 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Geelong East Primary School 2023-24 (Geelong East) | 3 390 | 3 346 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Gisborne Secondary College 2023-24 (Gisborne) | 5 800 | 5 744 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Grasmere Primary School 2022-23 (Grasmere) | 2 580 | 2 470 | qtr 4 2026-27 |
| Heathmont East Primary School 2023-24 (Heathmont) | 5 690 | 5 690 | qtr 3 2026-27 |
| The TEI has increased by $0.250 million to extend the scope for additional school requirements, funded by a co-contribution from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Inclusive Schools Fund 2023-24 (statewide) | 9 800 | 8 643 | qtr 2 2026-27 |
| Kananook Primary School 2025-26 (Seaford) | 521 | 472 | qtr 4 2026-27 |
| Keysborough Gardens Primary School 2023-24 (Keysborough) | 5 340 | 5 340 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Mahogany Rise Primary School 2023-24 (Frankston North) | 950 | 949 | qtr 4 2026-27 |
| The TEI includes a total of $0.250 million in co-contributions from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Meadow Heights Primary School 2025-26 (Meadow Heights) | 362 | 328 | qtr 4 2026-27 |
| Melton Secondary College 2023-24 (Melton) | 8 870 | 6 893 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Minor Capital Works Fund 2023-24 (statewide) | 10 000 | 10 000 | qtr 4 2026-27 |
| Modular Classrooms Program 2025-26 (statewide) | 148 472 | 148 472 | qtr 4 2026-27 |
| The TEI has increased by $0.043 million to extend the scope for additional school requirements, funded by a co-contribution from a school. |  |  |  |
| Moe Primary School 2023-24 (Moe) | 5 300 | 4 375 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Mount Duneed Regional Primary School 2023-24 (Mount Duneed) | 3 600 | 3 600 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Mulgrave Primary School 2024-25 (Mulgrave) | 6 175 | 5 861 | qtr 3 2026-27 |
| The TEI has increased by $0.175 million to extend the scope for additional school requirements, funded by a co-contribution from the school. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Murrayville Community College 2023-24 (Murrayville) | 4 680 | 4 680 | qtr 3 2026-27 |
| New schools – planning and site analysis 2024-25 (statewide) | 1 558 | 1 558 | qtr 4 2026-27 |
| The TEI has decreased by $1.082 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |
| Parkhill Primary School 2023-24 (Ashwood) | 5 300 | 5 300 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Paynesville Primary School 2024-25 (Paynesville) | 4 536 | 3 974 | qtr 1 2027-28 |
| The TEI has increased by $0.136 million due to a reprioritisation of funds from the Contingency fund for school upgrades 2024-25. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Pinewood Primary School 2024-25 (Mount Waverley) | 8 560 | 6 105 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Rainbow P-12 College 2020-21 (Rainbow) | 14 072 | 14 072 | qtr 3 2026-27 |
| Roberts McCubbin Primary School 2025-26 (Box Hill South) | 349 | 316 | qtr 4 2026-27 |
| School upgrades – growth for 2024 (statewide) | 99 167 | 95 904 | qtr 4 2026-27 |
| The TEI includes a total of $4.201 million in co-contributions from the schools. |  |  |  |
| St Albans Heights Primary School 2022-23 (St Albans) | 13 447 | 11 747 | qtr 2 2025-26 |
| Stawell Secondary College 2020-21 (Stawell) | 12 352 | 12 218 | qtr 4 2026-27 |
| Streeton Primary School 2025-26 (Yallambie) | 498 | 450 | qtr 4 2026-27 |
| Swan Hill North Primary School 2024-25 (Swan Hill) | 8 900 | 7 095 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Sydenham – Hillside Primary School 2023-24 (Sydenham) | 9 500 | 9 441 | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Wallington Primary School 2023-24 (Wallington) | 2 100 | 2 100 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Wandong Primary School 2023-24 (Wandong) | 10 100 | 9 671 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Wantirna College 2022-23 (Wantirna) | 15 173 | 15 173 | qtr 2 2026-27 |
| Wedderburn College 2022-23 (Wedderburn) | 12 886 | 12 886 | qtr 2 2026-27 |
| Western Heights College 2023-24 (Hamlyn Heights) | 7 550 | 6 513 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Wonthaggi Primary School 2023-24 (Wonthaggi) | 6 700 | 5 423 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Woodmans Hill Secondary College 2023-24 (Ballarat East) | 8 590 | 5 560 | qtr 1 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Yarra Primary School 2022-23 (Richmond) | 7 208 | 7 208 | qtr 2 2026-27 |

Source: Department of Education

Department of Energy, Environment and Climate Action

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Emergency Preparedness Package (regional) | 28 162 | 18 132 | 10 030 | .. | qtr 4 2026-27 |
| This initiative was announced in the 2025-26 Budget Update. |  |  |  |  |  |
| Establishing VicGrid (statewide) | 15 810 | 15 810 | .. | .. | qtr 4 2025-26 |
| Maintaining critical assets for emergency and land management (regional) | 24 949 | .. | 24 949 | .. | qtr 4 2026-27 |
| Total new projects | 68 921 | 33 942 | 34 979 | .. |  |

Source: Department of Energy, Environment and Climate Action

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Addressing recovery needs from the Western Victoria Bushfires (regional) | 6 630 | 4 580 | 2 050 | .. | qtr 4 2026-27 |
| The TEI has decreased by $1.500 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Bendigo mine impacted groundwater long-term management (Bendigo) | 38 846 | 5 778 | 33 069 | .. | qtr 4 2026-27 |
| The TEI has decreased by $5.552 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Continue the establishment of Liwik Barring conservation area and protect Victoria’s faunal emblems (Yellingbo) | 760 | 380 | 380 | .. | qtr 4 2026-27 |
| Efficient and strengthened earth resources regulation (statewide) | 2 500 | .. | 2 000 | 500 | qtr 4 2027-28 |
| Improving Victoria’s water resources knowledge and access (statewide) | 800 | .. | 400 | 400 | qtr 4 2027-28 |
| The TEI has decreased by $1.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Investing in Serendip Sanctuary and the You Yangs (Wurdi Youang) (Lara) | 10 900 | 5 400 | 5 500 | .. | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| National water grid fund (statewide) | 190 161 | 112 672 | 36 838 | 40 651 | qtr 4 2028-29 |
| Suburban parks program (creating a ring of new parkland) (metropolitan) | 212 257 | 211 794 | 463 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule to reflect timing of land acquisitions. |  |  |  |  |  |
| Supporting nature‑based tourism and the environment along the Great Ocean Road (regional) | 2 306 | 1 538 | 768 | .. | qtr 4 2026-27 |
| Total existing projects | 465 160 | 342 142 | 81 468 | 41 551 |  |
| Total Energy, Environment and Climate Action projects | 534 081 | 376 084 | 116 447 | 41 551 |  |
| Other capital expenditure | n.a. | n.a. | 88 057 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Energy, Environment and Climate Action capital expenditure |  |  | 204 504 |  |  |

Source: Department of Energy, Environment and Climate Action

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Additional recovery support for summer 2023-24 floods and storms (statewide) | 6 090 | 6 090 | qtr 4 2025-26 |
| The TEI has decreased by $0.042 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Critical bushfire and emergency asset maintenance and replacement (statewide) | 18 920 | 18 920 | qtr 4 2025-26 |
| The TEI has decreased by $1.080 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |
| Improving amenities for regional tourism (regional) | 11 600 | 11 600 | qtr 4 2025-26 |
| Maintaining critical assets essential for emergency response (regional) | .. | .. | .. |
| The previous TEI of $10.000 million has been reduced to nil due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |
| New and improved suburban parks (statewide) | 9 775 | 9 775 | qtr 4 2025-26 |
| Protecting Victoria’s park heritage icons (statewide) | 16 500 | 16 500 | qtr 4 2025-26 |

Source: Department of Energy, Environment and Climate Action

Department of Families, Fairness and Housing

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Child Safety Reform Program (statewide) | 5 000 | 750 | 4 250 | .. | qtr 4 2026-27 |
| This initiative was announced in the 2025-26 Budget Update as a component of the Immediate uplift and overhaul of child safety and early childhood sector initiative. |  |  |  |  |  |
| Communities and families information technology transformation program (statewide) | 105 934 | .. | 14 236 | 91 698 | qtr 4 2028-29 |
| Delivering on Rapid Child Safety Review recommendations (statewide) | 5 075 | .. | 2 475 | 2 600 | qtr 4 2027-28 |
| Specialist Disability Accommodation Replacement Program (statewide) | 18 653 | .. | 4 303 | 14 350 | qtr 4 2029-30 |
| Total new projects | 134 662 | 750 | 25 264 | 108 648 |  |

Source: Department of Families, Fairness and Housing

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Family violence victim survivors supports (statewide) | 4 000 | 2 400 | 900 | 700 | qtr 4 2027-28 |
| Specialist Disability Accommodation (SDA) safety: SDA home and fire panel replacements (statewide) | 19 200 | 200 | 4 500 | 14 500 | qtr 4 2029-30 |
| The estimated completion date has been revised to quarter 4 2029-30 in line with a revised schedule of works to accommodate a revised delivery model. |  |  |  |  |  |
| Total existing projects | 23 200 | 2 600 | 5 400 | 15 200 |  |
| Total Families, Fairness and Housing projects | 157 862 | 3 350 | 30 664 | 123 848 |  |
| Other capital expenditure |  | n.a. | 42 083 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Families, Fairness and Housing capital expenditure |  |  | 72 747 |  |  |

Source: Department of Families, Fairness and Housing

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| National Disability Insurance Scheme Stage 2 (statewide) | 11 803 | 11 803 | qtr 2 2025-26 |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Support for people with forensic disability and complex needs (statewide) | 480 | 480 | qtr 2 2026-27 |

Source: Department of Families, Fairness and Housing

Department of Government Services

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Children’s Agenda priority workstream – Children’s digital roadmap (statewide) | 17 003 | 10 000 | 7 003 | .. | qtr 4 2026-27 |
| This initiative was announced in the 2025-26 Budget Update. |  |  |  |  |  |
| Total new projects | 17 003 | 10 000 | 7 003 | .. |  |

Source: Department of Government Services

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Addressing the security and workplace requirements of government buildings (East Melbourne) | 32 650 | 14 694 | 17 956 | .. | qtr 4 2026-27 |
| Total existing projects | 32 650 | 14 694 | 17 956 | .. |  |
| Total Government Services projects | 49 653 | 24 694 | 24 959 | .. |  |
| Other capital expenditure | n.a. | n.a. | 71 128 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Government Services capital expenditure |  |  | 96 087 |  |  |

Source: Department of Government Services

Discontinued projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Centralised Accommodation Management (Melbourne) | 9 810 | 1 480 | qtr 4 2025-26 |
| This initiative has been discontinued. |  |  |  |

Source: Department of Government Services

Department of Health

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Better outcomes through early endoscopy detection (statewide) | 10 000 | .. | 10 000 | .. | qtr 4 2026-27 |
| Dandenong Hospital Redevelopment (Dandenong) | 305 000 | .. | 13 675 | 291 325 | qtr 4 2031-32 |
| The TEI includes $86.872 million provided in the 2023-24 Budget in the Hospital Infrastructure Delivery Fund (statewide) initiative. |  |  |  |  |  |
| Engineering Infrastructure Replacement Program 2026-27 (statewide) | 20 000 | .. | 20 000 | .. | qtr 4 2026-27 |
| Gippsland hospitals upgrade program (regional) | 65 000 | .. | 3 698 | 61 302 | qtr 2 2029-30 |
| Medical Equipment Replacement Program 2026-27 (statewide) | 35 000 | .. | 35 000 | .. | qtr 4 2026-27 |
| Mental Health and Alcohol and Other Drugs Capital Renewal Fund 2026-27 (statewide) | 10 000 | .. | 10 000 | .. | qtr 4 2026-27 |
| Metropolitan Health Infrastructure Fund 2026-27 (statewide) | 15 000 | .. | 15 000 | .. | qtr 4 2026-27 |
| Minor Capital Works Renewal Program – public sector residential aged care 2026-27 (statewide) | 7 500 | .. | 7 500 | .. | qtr 4 2026-27 |
| Regional Health Infrastructure Fund 2026-27 (statewide) | 75 000 | .. | 75 000 | .. | qtr 4 2026-27 |
| Safe births for every Victorian woman and baby (statewide) | 8 251 | .. | 8 251 | .. | qtr 4 2026-27 |
| Safer digital healthcare program 2026-27 (statewide) | 16 153 | .. | 16 153 | .. | qtr 4 2026-27 |
| Total new projects | 566 904 | .. | 214 277 | 352 627 |  |

Source: Department of Health

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| A new ambulance station for Armstrong Creek (Armstrong Creek) | 30 400 | 839 | 17 435 | 12 126 | qtr 2 2028-29 |
| The estimated completion date has been revised to quarter 2 2028-29 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Additional acute mental health beds in regional Victoria (various) | 195 834 | 26 537 | 33 456 | 135 841 | qtr 4 2028-29 |
| Austin Hospital Emergency Department Upgrade (Heidelberg) | 275 000 | 75 698 | 83 339 | 115 962 | qtr 2 2028-29 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Ballarat Base Hospital mental health, alcohol and other drugs emergency department hub (Ballarat) | 5 400 | .. | 2 300 | 3 100 | qtr 4 2027-28 |
| Ballarat Health Services expansion and redevelopment and the new Central Energy Plant (Ballarat) | 650 388 | 438 128 | 138 860 | 73 400 | qtr 2 2027-28 |
| Barwon Women’s and Children’s Hospital (Geelong) | 514 102 | 210 102 | 154 000 | 150 000 | qtr 2 2028-29 |
| The estimated completion date has been revised to quarter 2 2028-29 in line with a revised project schedule. The TEI includes $50.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement. |  |  |  |  |  |
| Better aged care services for regional Victorians (regional various) | 162 246 | 45 625 | 84 548 | 32 073 | qtr 1 2028-29 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Building a world class hospital for Frankston families (Frankston) | 1 120 084 | 1 055 982 | 42 315 | 21 787 | qtr 3 2027-28 |
| Building emergency departments kids and families can count on (statewide) | 46 517 | 22 216 | 19 301 | 5 000 | qtr 2 2028-29 |
| The estimated completion date has been revised to quarter 2 2028-29 in line with a revised project schedule. |  |  |  |  |  |
| Community hospitals to give patients the best care (statewide) | 869 986 | 752 269 | 116 990 | 727 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Contemporary information architecture for mental health and wellbeing (statewide) | 60 761 | 30 416 | 18 800 | 11 545 | qtr 4 2027-28 |
| COVID catch-up plan (statewide) | 121 637 | 119 559 | 2 078 | .. | qtr 4 2026-27 |
| The TEI has decreased by $85.939 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with the removal of non-capitalised components. |  |  |  |  |  |
| Dandenong and Districts Aborigines Co‑operative accommodation (Dandenong) | 9 710 | 1 942 | 7 768 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Early Parenting Centre – Shepparton (Shepparton) | 25 000 | 10 056 | 14 944 | .. | qtr 2 2026-27 |
| Emergency Departments Expansion Program – Casey Hospital and Werribee Mercy Hospital (Casey) (Werribee) | 279 921 | 152 295 | 127 626 | .. | qtr 4 2026-27 |
| Engineering infrastructure and medical equipment replacement program 2020-21 (statewide) | 85 000 | 83 611 | 1 389 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Engineering infrastructure and medical equipment replacement program 2021-22 (statewide) | 85 000 | 79 384 | 5 616 | .. | qtr 4 2026-27 |
| Engineering infrastructure replacement program 2022-23 (statewide) | 20 000 | 18 468 | 1 532 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Engineering infrastructure replacement program 2024-25 (statewide) | 40 000 | 16 373 | 16 027 | 7 600 | qtr 4 2029-30 |
| Engineering infrastructure replacement program 2025-26 (statewide) | 61 750 | 60 970 | 780 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Forensic Mental Health Expansion Project Stage 1 and 2 (Fairfield) | 462 457 | 429 666 | 30 186 | 2 605 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with complex decanting activities associated with refurbishment works and completion of required town planning approvals. |  |  |  |  |  |
| Harm reduction initiatives (metropolitan) | 36 400 | 17 589 | 18 811 | .. | qtr 4 2026-27 |
| - Hospital Infrastructure Delivery Fund (statewide) | 15 691 | 15 691 | .. | .. | qtr 2 2026-27 |
| - A new hospital for West Gippsland to put patients first - A new Queen Elizabeth II Hospital in Melbourne’s East - Dandenong Hospital and Wonthaggi Hospital redevelopment |  |  |  |  |  |
| The TEI has decreased to reflect $86.872 million provided to deliver the Dandenong Hospital Redevelopment initiative. Planning continues on the development of priority hospital infrastructure projects. |  |  |  |  |  |
| Improving Energy Efficiency in Public Hospitals (Melbourne) | 40 000 | 34 288 | 5 712 | .. | qtr 4 2026-27 |
| Improving safety in mental health intensive care areas (various) | 61 138 | 52 410 | 8 728 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with works staged around clinical service requirements. |  |  |  |  |  |
| Medical Equipment Replacement Program 2024-25 (statewide) | 35 000 | 29 595 | 4 705 | 700 | qtr 4 2027-28 |
| Medical Equipment Replacement Program 2025-26 (statewide) | 52 250 | 51 470 | 780 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Meeting ambulance response times (statewide) | 177 317 | 163 431 | 13 886 | .. | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Mental health and alcohol and other drugs residential rehabilitation facility – Mildura (Mildura) | 36 000 | 5 554 | 30 056 | 390 | qtr 4 2026-27 |
| Mental Health and Alcohol and Other Drugs Capital Renewal Fund 2023-24 (statewide) | 10 000 | 8 684 | 1 316 | .. | qtr 4 2026-27 |
| The project name has changed from ‘Mental Health Capital Renewal Fund 2023-24 (statewide)’ when it was published in the 2025-26 Budget to better reflect scope of the grants program. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Mental Health and Alcohol and Other Drugs Capital Renewal Fund 2024-25 (statewide) | 10 000 | 2 195 | 7 805 | .. | qtr 4 2027-28 |
| The project name has changed from ‘Mental Health Capital Renewal Fund 2024-25 (statewide)’ when it was published in the 2025-26 Budget to better reflect scope of the grants program. |  |  |  |  |  |
| Mental Health and Alcohol and Other Drugs Capital Renewal Fund 2025-26 (statewide) | 10 000 | 10 000 | .. | .. | qtr 4 2026-27 |
| The project name has changed from ‘Mental Health Capital Renewal Fund 2025-26 (statewide)’ when it was published in the 2025-26 Budget to better reflect scope of the grants program. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Metropolitan Health Infrastructure Fund 2020-21 (metropolitan various) | 187 000 | 157 464 | 29 536 | .. | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 to accommodate delivery of a recently funded additional project. |  |  |  |  |  |
| Metropolitan Health Infrastructure Fund 2022-23 (metropolitan various) | 25 000 | 22 948 | 991 | 1 061 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Metropolitan Health Infrastructure Fund 2023-24 (metropolitan various) | 40 000 | 26 819 | 12 902 | 279 | qtr 4 2027-28 |
| Minor Capital Renewal Program – public sector residential aged care (statewide) | 7 500 | 7 500 | .. | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Monash Medical Centre Redevelopment (Clayton) | 535 000 | 50 034 | 141 401 | 343 565 | qtr 4 2028-29 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| More hospital and aged care beds for Melbourne’s East (Angliss Hospital Expansion Stage 2) (Upper Ferntree Gully) | 112 000 | 98 170 | 13 830 | .. | qtr 4 2026-27 |
| More PET scanners for Victorian hospitals (statewide) | 69 623 | 24 519 | 8 072 | 37 032 | qtr 4 2029-30 |
| The TEI has increased by $25.623 million as a result of project cost increases. The estimated completion date has been revised to quarter 4 2029-30 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| New Melton Hospital (Cobblebank) | 1 487 719 | 314 248 | 325 910 | 847 561 | qtr 1 2029-30 |
| Northcote – Early Parenting Centre (Northcote) | 20 000 | 2 397 | 12 603 | 5 000 | qtr 4 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Northern Hospital Redevelopment (Epping) | 812 500 | 126 811 | 114 689 | 571 000 | qtr 2 2029-30 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Parkville Precinct Redevelopment (Parkville) | 2 338 000 | 184 766 | 170 151 | 1 983 083 | tbc |
| Redevelopment of Thomas Embling Hospital Stage 3 (Fairfield) | 53 196 | 7 917 | 45 279 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Regional Health Infrastructure Fund (regional various) | 250 000 | 240 986 | 9 014 | .. | qtr 4 2026-27 |
| Regional Health Infrastructure Fund 2019-20 (regional various) | 100 000 | 93 303 | 6 697 | .. | qtr 4 2026-27 |
| Regional Health Infrastructure Fund 2020-21 (regional various) | 120 000 | 105 790 | 14 210 | .. | qtr 4 2026-27 |
| Regional Health Infrastructure Fund 2022-23 (regional various) | 300 000 | 142 297 | 30 358 | 127 344 | qtr 4 2027-28 |
| Royal Children’s Hospital expansion (Parkville) | 55 812 | 47 067 | 8 745 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.588 million due to lower than expected cost. |  |  |  |  |  |
| Royal Melbourne Hospital Critical Infrastructure Works (Melbourne) | 57 439 | 2 288 | 12 317 | 42 834 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule. |  |  |  |  |  |
| Rural and Regional PSRACS Revitalisation Strategy Stage 1 2022-23 (regional various) | 142 845 | 123 105 | 17 098 | 2 642 | qtr 4 2027-28 |
| Rural residential aged care facilities renewal 2020-21 (regional various) | 10 000 | 9 741 | 259 | .. | qtr 4 2026-27 |
| Supporting the next generation of paramedics (statewide) | 3 200 | 2 100 | 1 100 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with revised program delivery timelines. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Sustaining statewide health service delivery at The Alfred (Prahran) | 118 000 | 3 583 | 59 618 | 54 800 | qtr 2 2029-30 |
| Swan Hill District Hospital emergency department upgrade (Swan Hill) | 65 700 | 63 681 | 2 019 | .. | qtr 2 2026-27 |
| The TEI includes $30.000 million of Commonwealth Government funding under the Community Health and Hospitals Program agreement. |  |  |  |  |  |
| The Alfred Hospital urgent infrastructure (Prahran) | 174 500 | 30 682 | 35 182 | 108 635 | qtr 4 2029-30 |
| Warrnambool Base Hospital redevelopment (incl Warrnambool Logistics Hub) (Warrnambool) | 396 100 | 156 668 | 134 768 | 104 665 | qtr 3 2027-28 |
| The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Total existing projects | 13 086 123 | 6 065 928 | 2 217 837 | 4 802 358 |  |
| Total Health projects | 13 653 027 | 6 065 928 | 2 432 114 | 5 154 985 |  |
| Other capital expenditure | n.a | n.a | (328 155) | n.a |  |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department in addition to remaining expenditure in 2026-27 for Completed projects. This is offset by factors including funding held in contingency pending confirmation of project planning and development and capital expenditure associated with public private partnerships. |  |  |  |  |  |
| Total 2026-27 Health capital expenditure |  |  | 2 103 959 |  |  |

Source: Department of Health

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Additional acute mental health beds in Warrnambool (Warrnambool) | 10 872 | 10 872 | qtr 2 2026-27 |
| Building a better hospital for Melbourne’s inner west (Footscray) | 1 998 605 | 1 996 498 | qtr 2 2026-27 |
| Building a new rehabilitation centre for Bendigo (Bendigo) | 63 500 | 61 347 | qtr 3 2026-27 |
| More help for Victorian mums and dads (statewide) | 124 565 | 124 565 | qtr 2 2026-27 |
| Quadra scanner Paula Fox Melanoma and Cancer Centre (Melbourne) | 24 000 | 24 000 | qtr 4 2025-26 |
| The TEI includes $12.000 million of Commonwealth Government funding and an additional $5.000 million of funding from The Alfred Foundation. |  |  |  |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Backing our paramedics to keep saving lives (statewide) | 55 700 | 52 589 | qtr 4 2026-27 |
| Building a World Class Hospital in Maryborough (Maryborough) | 115 000 | 110 532 | qtr 4 2026-27 |
| Equitable cancer care and prevention (statewide) | 13 712 | 13 712 | qtr 4 2026-27 |
| Expanding mental health treatment facilities for Victoria’s youth (statewide) | 141 000 | 109 519 | qtr 4 2026-27 |
| Guaranteeing Future Energy Supply (statewide) | 80 000 | 80 000 | qtr 4 2026-27 |
| Medical equipment replacement program 2022-23 (statewide) | 35 000 | 32 892 | qtr 4 2026-27 |
| Publicly led fertility care services for Victoria (statewide) | 12 000 | 9 365 | qtr 4 2026-27 |
| The TEI has decreased by $8.000 million due to revised project scope. |  |  |  |
| Regional Health Infrastructure Fund 2021-22 (regional various) | 20 000 | 15 113 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule. |  |  |  |
| Rural residential aged care facilities renewal 2019-20 (regional various) | 10 000 | 7 873 | qtr 4 2026-27 |
| Safer Digital Healthcare Program 2025-26 (statewide) | 15 759 | 15 759 | qtr 4 2026-27 |

Source: Department of Health

Department of Jobs, Skills, Industry and Regions

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Cultural infrastructure maintenance (statewide) | 4 280 | .. | 2 280 | 2 000 | qtr 4 2027-28 |
| Delivering a Digital, AI and Technology TAFE Centre of Excellence (Frankston) | 10 120 | 7 250 | 2 370 | 500 | qtr 4 2027-28 |
| The TEI includes $5.060 million of Commonwealth Government funding under the National Skills Agreement. |  |  |  |  |  |
| Delivering a Victorian Renewable Energy TAFE Centre of Excellence (statewide) | 25 000 | 7 800 | 7 600 | 9 600 | qtr 2 2029-30 |
| The TEI includes $25.000 million reprioritised from the Building Better TAFE Fund – Clean Energy TAFE Fund initiative funded in the 2023-24 Budget. |  |  |  |  |  |
| TAFE accessibility works and infrastructure (statewide) | 10 000 | .. | 10 000 | .. | qtr 4 2027-28 |
| The TEI includes $5.000 million reprioritised from the Building Better TAFE Fund – Clean Energy TAFE Fund initiative funded in the 2023-24 Budget and $0.639 million of Commonwealth Government funding under the National Skills Agreement. |  |  |  |  |  |
| Total new projects | 49 400 | 15 050 | 22 250 | 12 100 |  |

Source: Department of Jobs, Skills, Industry and Regions

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Building Better TAFE Fund – Clean Energy TAFE Fund (statewide) | 15 800 | 11 800 | 4 000 | .. | qtr 2 2028-29 |
| The TEI has decreased by $30.000 million due to $25.000 million being reprioritised to the Victorian Renewable Energy TAFE Centre of Excellence initiative and $5.000 million being reprioritised to the TAFE accessibility works and infrastructure initiative. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Building Better TAFE Fund – Melton (New TAFE Campus) (Melton) | 55 000 | 27 140 | 27 860 | .. | qtr 4 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Building Better TAFE Fund – Sunbury (New TAFE Campus) (Sunbury) | 25 000 | 17 824 | 5 610 | 1 566 | qtr 4 2027-28 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Building Better TAFE Fund – The Gordon TAFE (Geelong – Disability Services Hub and Student Hub Redevelopment) (Geelong) | 36 000 | 36 000 | .. | .. | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Conserving the Royal Exhibition Building (Melbourne) | 9 639 | 5 000 | 4 639 | .. | qtr 4 2028-29 |
| Cultural Facilities Maintenance Fund (statewide) | 14 500 | 7 500 | 3 500 | 3 500 | qtr 4 2027-28 |
| The TEI has decreased by $1.500 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Delivering a Future of Housing Construction TAFE Centre of Excellence (Heidelberg) | 24 994 | 541 | 18 827 | 5 626 | qtr 3 2028-29 |
| This initiative is part of the Economic Growth Statement 2024. |  |  |  |  |  |
| Geelong City Deal (regional) | 86 921 | 69 681 | 17 240 | .. | qtr 2 2026-27 |
| The TEI has decreased by $22.626 million due to $24.736 million of budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards, offset by an increase of $2.110 million of Commonwealth Government funding. The TEI includes Commonwealth Government funding of $66.281 million. |  |  |  |  |  |
| Recreational boating infrastructure improvements (Neerim South) | 3 900 | 700 | 3 200 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| TAFE Asset Strategy (statewide) | 4 900 | 1 960 | 2 940 | .. | qtr 2 2027-28 |
| Total existing projects | 276 654 | 178 146 | 87 816 | 10 692 |  |
| Total Jobs, Skills, Industry and Regions projects | 326 054 | 193 196 | 110 066 | 22 792 |  |
| Other capital expenditure | n.a. | n.a. | 3 636 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Jobs, Skills, Industry and Regions capital expenditure |  |  | 113 702 |  |  |

Source: Department of Jobs, Skills, Industry and Regions

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Building Better TAFE Fund – Bendigo Kangan Institute (Castlemaine – Community Health and Learning Hub) (Castlemaine) | 4 000 | 4 000 | qtr 1 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Creative Industries Portfolio Agencies Recovery (metropolitan) | 4 345 | 4 345 | qtr 4 2026-27 |
| Go Fishing Victoria (regional various) | 15 000 | 15 000 | qtr 3 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Research and development cash flow loans (statewide) | 1 306 | 1 306 | qtr 4 2024-25 |
| The TEI has decreased by $0.218 million due to a reduced funding requirement to fulfill the loan assignment obligations. |  |  |  |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Nyaal Banyul Geelong Convention and Event Centre (Geelong) | 449 100 | 449 100 | qtr 4 2025-26 |
| The TEI includes $30.000 million of Commonwealth Government funding and $3.000 million of City of Greater Geelong funding. The TEI excludes financing, land acquisition and ongoing operating costs. |  |  |  |

Source: Department of Jobs, Skills, Industry and Regions

Discontinued projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Victorian Industry Development Fund (statewide) | .. | .. | n.a. |
| The TEI has decreased by $5.000 million as the initiative will be discontinued. |  |  |  |

Source: Department of Jobs, Skills, Industry and Regions

Department of Justice and Community Safety

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| A stronger, safer Country Fire Authority (statewide) | 272 | .. | 116 | 156 | qtr 4 2027-28 |
| Backing Victoria’s marine search and rescue and delivering new vessels (statewide) | 2 440 | .. | 2 440 | .. | qtr 4 2026-27 |
| Building more Country Fire Authority stations (statewide) | 23 524 | .. | 10 891 | 12 633 | qtr 4 2029-30 |
| Critical cybercrime and digital forensic storage and software (statewide) | 2 389 | .. | 1 753 | 636 | qtr 4 2029-30 |
| Delivering new Country Fire Authority fleet (statewide) | 100 000 | .. | 10 000 | 90 000 | qtr 4 2035-36 |
| Delivering new Fire Rescue Victoria fleet (statewide) | 10 000 | .. | 10 000 | .. | qtr 4 2026-27 |
| Delivering on bail reform for Victoria Police (statewide) | 8 626 | .. | 2 404 | 6 222 | qtr 4 2029-30 |
| Delivering serious consequences and keeping the community safe (statewide) | 32 494 | 20 167 | 12 207 | 120 | qtr 4 2030-31 |
| The TEI includes $10.896 million announced in the 2025-26 Budget Update in the Community Safety Package initiative. |  |  |  |  |  |
| Emergency Preparedness Package (DJCS) (statewide) | 1 210 | .. | 1 210 | .. | qtr 4 2026-27 |
| This initiative was announced in the 2025-26 Budget Update as a component of the Emergency Preparedness Package initiative. |  |  |  |  |  |
| Increasing PSO capacity and funding for Operation Pulse – Operation Pulse component only (statewide) | 2 596 | .. | 2 596 | .. | qtr 4 2026-27 |
| Mobile technology for police and evidence recording upgrade (statewide) | 21 258 | .. | 11 917 | 9 341 | qtr 4 2028-29 |
| Opening new Victoria State Emergency Service units (statewide) | 1 952 | .. | 1 952 | .. | qtr 4 2026-27 |
| Police information technology refresh (statewide) | 25 905 | .. | 19 753 | 6 152 | qtr 4 2028-29 |
| Prosecutions at Wyndham Law Courts (statewide) | 870 | .. | 870 | .. | qtr 4 2026-27 |
| Strengthening Fire Rescue Victoria’s fire station safety (statewide) | 5 609 | .. | 4 000 | 1 609 | qtr 4 2027-28 |
| Strengthening Victoria State Emergency Service (statewide) | 16 384 | .. | 7 962 | 8 422 | qtr 4 2028-29 |
| Supporting a safe and effective corrections system (statewide) | 669 | .. | 319 | 350 | qtr 4 2027-28 |
| Supporting bail reform implementation in the adult correctional and youth justice systems (statewide) | 2 300 | 2 300 | .. | .. | qtr 4 2025-26 |
| Supporting Victoria Police operations (statewide) | 3 112 | .. | 2 612 | 500 | qtr 4 2029-30 |
| Upgrading Fire Rescue Victoria’s human resources information system (statewide) | 26 994 | .. | 17 903 | 9 091 | qtr 4 2027-28 |
| Upgrading Victoria’s Triple Zero telephony (statewide) | 67 535 | .. | 6 510 | 61 025 | qtr 4 2028-29 |
| Victoria Police capital maintenance investment (statewide) | 15 000 | .. | 12 000 | 3 000 | qtr 4 2027-28 |
| Victoria Police licensing and registration management system (statewide) | 18 519 | .. | 8 348 | 10 171 | qtr 4 2028-29 |
| Total new projects | 389 658 | 22 467 | 147 763 | 219 428 |  |

Source: Department of Justice and Community Safety

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Building more Country Fire Authority stations (CFA-led) (statewide) (a) | 701 | 165 | 172 | 364 | qtr 4 2028-29 |
| The TEI of $0.701 million has been disaggregated from the Building more Country Fire Authority stations (regional) initiative to reflect the CFA-led projects. |  |  |  |  |  |
| CFA Capital Upgrades Program (statewide) | 108 786 | 76 406 | 15 261 | 17 119 | qtr 4 2028-29 |
| The TEI has increased by $27.663 million, $9.500 million due to funds being reprioritised from the Delivering Emergency Services Upgrades (statewide) initiative, $17.663 million reprioritised from the Building more Country Fire Authority stations (regional) initiative, and $0.500 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule. |  |  |  |  |  |
| Community Safety Package (statewide) | 4 830 | 4 630 | 200 | .. | qtr 1 2026-27 |
| Compressed air foam systems (CFA) (statewide) (a) | 1 530 | 820 | 710 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with revised project scope. |  |  |  |  |  |
| Continuity of the Road Safety Camera Network (statewide) | 20 000 | .. | 5 000 | 15 000 | qtr 4 2029-30 |
| Country Fire Authority – New urban pumpers (statewide) (a) | 16 750 | 6 489 | 10 261 | .. | qtr 4 2026-27 |
| Critical police infrastructure (Melbourne) | 49 949 | 38 584 | 11 030 | 335 | qtr 1 2026-27 |
| The TEI has increased by $3.000 million due to funds being reprioritised from the Delivering new police station infrastructure (statewide) initiative. The estimated completion date has been revised to quarter 1 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Delivering new police station infrastructure (statewide) | 150 134 | 113 648 | 23 025 | 13 461 | qtr 3 2027-28 |
| The TEI has decreased by $3.000 million due to funds being reprioritised to the Critical police station infrastructure (Melbourne) initiative. The estimated completion date has been revised to quarter 3 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Emergency response capability uplift (CFA) (statewide) (a) | 8 960 | 5 056 | 3 904 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a more accurate forecast. |  |  |  |  |  |
| Emergency Services High-priority infrastructure (statewide) | 181 687 | 126 367 | 22 800 | 32 520 | qtr 4 2027-28 |
| The TEI has increased by $13.861 million, with $13.261 million due to funds being reprioritised from the Delivering a new Victoria State Emergency Service Footscray unit (Maidstone) initiative, $0.100 million reprioritised from the Delivering Emergency Services Upgrades (statewide) initiative, and $0.500 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 in line with the revised delivery program. |  |  |  |  |  |
| Fire Rescue Victoria – New aerial platform pumpers (metropolitan) (b) | 13 714 | 7 133 | 6 581 | .. | qtr 4 2026-27 |
| Fire Rescue Victoria – Rolling fleet replacement program (statewide) (b) | 40 000 | 2 594 | 21 685 | 15 721 | qtr 4 2028-29 |
| FRV Capital Upgrades Program (statewide) (b) | 103 909 | 53 246 | 13 775 | 36 888 | qtr 4 2027‑28 |
| FRV Security System Platform (statewide) (b) | 4 400 | 1 370 | 3 030 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Further supporting our emergency services and volunteers – Country Fire Authority (statewide) | 51 220 | 695 | 16 651 | 33 874 | qtr 4 2028-29 |
| This initiative was formerly published as ‘Further supporting our emergency services and volunteers (statewide)’. The TEI has increased by $46.034 million to $99.094 million due to funds being reclassified as capital instead of operating expenditure, in line with accounting standards. The initiative has then been disaggregated into Further supporting our emergency services and volunteers – Country Fire Authority (statewide), Further supporting our emergency services and volunteers – Emergency Management Victoria (statewide) and Further supporting our emergency services and volunteers – Victoria State Emergency Service (statewide). |  |  |  |  |  |
| Further supporting our emergency services and volunteers – Emergency Management Victoria (statewide) | 15 300 | .. | 14 300 | 1 000 | qtr 4 2028-29 |
| This initiative was formerly published as ‘Further supporting our emergency services and volunteers (statewide)’. The TEI has increased by $46.034 million to $99.094 million due to funds being reclassified as capital instead of operating expenditure, in line with accounting standards. The initiative has then been disaggregated into Further supporting our emergency services and volunteers – Country Fire Authority (statewide), Further supporting our emergency services and volunteers – Emergency Management Victoria (statewide) and Further supporting our emergency services and volunteers – Victoria State Emergency Service (statewide). |  |  |  |  |  |
| Further supporting our emergency services and volunteers – Victoria State Emergency Service (statewide) | 32 574 | 3 158 | 3 570 | 25 846 | qtr 4 2028-29 |
| This initiative was formerly published as ‘Further supporting our emergency services and volunteers (statewide)’. The TEI has increased by $46.034 million to $99.094 million due to funds being reclassified as capital instead of operating expenditure, in line with accounting standards. The initiative has then been disaggregated into Further supporting our emergency services and volunteers – Country Fire Authority (statewide), Further supporting our emergency services and volunteers – Emergency Management Victoria (statewide) and Further supporting our emergency services and volunteers – Victoria State Emergency Service (statewide). |  |  |  |  |  |
| Hose Deployment Bag (FRV) (metropolitan various) (b) | 1 310 | 935 | 375 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised vehicle modification schedule. |  |  |  |  |  |
| Men’s prison system capacity (statewide) | 809 118 | 690 895 | 113 223 | 5 000 | qtr 4 2026-27 |
| Next generation computer aided dispatch system for Triple Zero (statewide) | 92 893 | 51 191 | 37 118 | 4 584 | qtr 4 2027-28 |
| Prison system capacity expansion and security upgrades (metropolitan) | 19 327 | 10 565 | 8 762 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Repair of Rochester and Heathcote VICSES Emergency Hub (Rochester/Heathcote) | 26 766 | 11 514 | 12 695 | 2 557 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Road Safety Action Plan 2 (statewide) | 527 | 215 | 110 | 202 | qtr 4 2028-29 |
| Station alteration and major maintenance 2021-22 (FRV) (statewide) (b) | 10 083 | 9 141 | 942 | .. | qtr 4 2026-27 |
| Strengthening Marine Search and Rescue and delivering new vessels (statewide) | 4 290 | .. | 4 090 | 200 | qtr 4 2028-29 |
| The TEI has increased by $0.277 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. |  |  |  |  |  |
| Strengthening of youth justice precincts (statewide) | 58 329 | 54 835 | 3 494 | .. | qtr 2 2026-27 |
| The TEI has decreased by $1.118 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised program schedule. |  |  |  |  |  |
| Supporting a safe and effective Youth Justice system (statewide) | 552 | .. | 276 | 276 | qtr 4 2027-28 |
| Supporting vulnerable Victorians (statewide) | 1 497 | 611 | 508 | 378 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Technology and resources to support Victoria’s fines system (statewide) | 190 328 | 185 328 | 5 000 | .. | qtr 4 2026-27 |
| The TEI has increased by $10.000 million reflecting increased delivery complexity. The completion date has been revised to quarter 4 2026–27 in line with a revised program schedule. |  |  |  |  |  |
| VICSES Facilities, fleet, emergency risk assessments and volunteer health and safety (statewide) | 8 925 | 5 685 | 2 740 | 500 | qtr 3 2027-28 |
| VICSES fleet capability (statewide) | 15 077 | 4 261 | 7 243 | 3 573 | qtr 4 2029-30 |
| Total existing projects | 2 043 466 | 1 465 537 | 368 531 | 209 398 |  |
| Total Justice and Community Safety projects | 2 433 124 | 1 488 004 | 516 294 | 428 826 |  |
| Other capital expenditure | n.a. | n.a. | (152 403) | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department in addition to remaining expenditure in 2026-27 for Completed projects. This is offset by factors including funding held in contingency pending confirmation of project planning and development in addition to general government sector-funded capital projects delivered by regulatory bodies. |  |  |  |  |  |
| Total 2026-27 Justice and Community Safety capital expenditure |  |  | 363 891 |  |  |

Source: Department of Justice and Community Safety

Notes:

(a)	This item was previously disclosed under the Country Fire Authority and has now been incorporated into the Department of Justice and Community Safety.

(b)	This item was previously disclosed under Fire Rescue Victoria and has now been incorporated into the Department of Justice and Community Safety.

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Building more Country Fire Authority stations (regional) | .. | .. | qtr 4 2025-26 |
| The TEI of $18.364 million for this initiative is now included in the CFA Capital Upgrades Program (statewide) initiative ($17.663 million) and Building more Country Fire Authority stations (CFA-led) (statewide) initiative ($0.701 million). |  |  |  |
| Computer equipment and software upgrade/replacement 2019-20 (metropolitan various) (a) | 10 024 | 10 024 | qtr 4 2025-26 |
| Computer equipment and software upgrade/replacement 2021-22 (FRV) (statewide) (a) | 5 711 | 5 711 | qtr 4 2025-26 |
| Delivering a new Victoria State Emergency Service Footscray unit (Maidstone) | .. | .. | qtr 4 2025-26 |
| The TEI of $13.261 million is now included in the Emergency Services High-priority infrastructure (statewide) initiative. |  |  |  |
| Delivering Emergency Services Upgrades (statewide) | .. | .. | qtr 4 2025-26 |
| The TEI of $9.600 million for this initiative is now included in the CFA Capital Upgrades Program (statewide) initiative ($9.500 million) and Emergency Services High-priority infrastructure (statewide) ($0.100 million). This initiative is part of Labor’s Financial Statement 2022. |  |  |  |
| Diesel Emission Exhaust Source Capture System (FRV) (statewide) (a) | 4 200 | 4 200 | qtr 4 2025-26 |
| Equipping frontline police officers with conducted energy devices (statewide) | 43 641 | 38 903 | qtr 2 2026-27 |
| The TEI has decreased by $0.649 million due to revised costings. |  |  |  |
| Operational Station Connectivity (FRV) (statewide) (a) | 18 508 | 18 508 | qtr 4 2025-26 |
| Supporting the State’s forensic capability (statewide) | 50 810 | 50 810 | qtr 1 2025‑26 |
| Vehicles – Passenger car and light commercial upgrade/ replacement 2021-22 (FRV) (statewide) (a) | 13 093 | 13 093 | qtr 4 2025-26 |
| Victoria Police system enhancements and resources (statewide) | 5 777 | 5 777 | qtr 4 2026-27 |
| The TEI has decreased by $1.856 million due to reduced project contingency. |  |  |  |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Delivery of prosecution services (statewide) | 5 116 | 5 116 | qtr 4 2025-26 |
| The TEI has decreased by $0.550 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |

Source: Department of Justice and Community Safety

Note:

(a)	This item was previously disclosed under Fire Rescue Victoria and has now been incorporated into the Department of Justice and Community Safety.

Department of Premier and Cabinet

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Supporting the Office of the Governor and protecting Government House heritage (statewide) | 18 000 | 3 000 | 3 000 | 12 000 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Total existing projects | 18 000 | 3 000 | 3 000 | 12 000 |  |
| Total Premier and Cabinet projects | 18 000 | 3 000 | 3 000 | 12 000 |  |
| Other capital expenditure | n.a. | n.a. | 8 960 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Premier and Cabinet capital expenditure |  |  | 11 960 |  |  |

Source: Department of Premier and Cabinet

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Housing Support Program – Priority Works (metropolitan) | .. | .. | qtr 4 2025-26 |
| The TEI has decreased to nil due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |

Source: Department of Premier and Cabinet

Department of Transport and Planning

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Critical public and active transport upgrades (statewide) | 7 136 | .. | 2 018 | 5 118 | qtr 4 2028-29 |
| Delivering a bus service for the Avalon Airport precinct (metropolitan) | 300 | 300 | .. | .. | qtr 4 2025-26 |
| This initiative was announced in the 2025-26 Budget Update. |  |  |  |  |  |
| Improving bus and ferry services (statewide) | 25 923 | .. | 16 253 | 9 670 | qtr 4 2027-28 |
| The TEI includes $8.893 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |
| Local ports critical maintenance (statewide) | 5 530 | .. | 1 813 | 3 717 | qtr 4 2029-30 |
| Metropolitan roads upgrade program (metropolitan) | 23 050 | .. | 20 210 | 2 840 | qtr 4 2028-29 |
| Regional roads upgrade program (regional) | 67 665 | .. | 19 446 | 48 219 | qtr 4 2029-30 |
| The TEI includes $17.477 million of Commonwealth Government funding. |  |  |  |  |  |
| Reinstatement of the state transport network following emergency events (regional) | 37 700 | 21 450 | 16 250 | .. | qtr 4 2026-27 |
| Road maintenance (statewide) | 133 396 | .. | 133 396 | .. | qtr 4 2026-27 |
| Victorian Renewable Energy Terminal (metropolitan) | 124 454 | 34 266 | 79 358 | 10 830 | tbc |
| The estimated completion date is pending environmental approval processes. The TEI includes $7.328 million from Port of Hastings Corporation. |  |  |  |  |  |
| Total new projects | 425 154 | 56 016 | 288 744 | 80 394 |  |

Source: Department of Transport and Planning

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Twenty-five more level crossing removals (Level Crossing Removal) (metropolitan various) | 6 410 604 | 1 702 105 | 981 595 | 3 726 903 | qtr 4 2031-32 |
| The TEI has decreased by $38.238 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2031-32 to align Highett Road and Wickham Road, Highett and Latrobe Street, Mentone level crossing removals with the Suburban Rail Loop delivery schedule to realise construction efficiencies and minimise disruption for Frankston line passengers. |  |  |  |  |  |
| Arden Precinct Redevelopment (metropolitan) | tbc | tbc | tbc | tbc | tbc |
| The TEI and estimated completion date for this initiative cannot be disclosed at this time to protect commercial-in-confidence information. |  |  |  |  |  |
| Ballarat West Employment Zone Freight Hub (Ballarat) | 54 122 | 7 366 | 45 427 | 1 329 | qtr 3 2026-27 |
| The TEI has decreased by $0.878 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $27.750 million of Commonwealth Government funding. |  |  |  |  |  |
| Bus service improvements and reform (metropolitan various) | 13 556 | 12 355 | 1 201 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 to deliver additional improvements to bus services in Fishermans Bend. |  |  |  |  |  |
| Camerons Lane Interchange development (Beveridge) | 30 000 | 8 232 | 16 639 | 5 129 | qtr 4 2026-27 |
| The TEI is funded by $30.000 million of Commonwealth Government funding. |  |  |  |  |  |
| Clyde Road Upgrade (metropolitan southeast) | 277 700 | 194 008 | 60 458 | 23 234 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with favourable weather conditions for construction at critical stages. The TEI is funded by $277.700 million of Commonwealth Government funding. |  |  |  |  |  |
| Critical public and active transport upgrades 2024-25 (metropolitan) | 18 691 | 1 599 | 8 786 | 8 307 | qtr 4 2026-27 |
| Critical public and active transport upgrades 2025-26 (statewide) | 14 501 | 2 752 | 11 749 | .. | qtr 4 2026-27 |
| Delivering better local roads (metropolitan various) | 54 466 | 9 756 | 9 746 | 34 964 | qtr 4 2027-28 |
| The TEI has increased by $4.400 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Delivering the Road Safety Action Plan (statewide) | 270 928 | 158 732 | 57 611 | 54 585 | qtr 4 2027-28 |
| The TEI has decreased by $0.125 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $184.887 million of Commonwealth Government funding. |  |  |  |  |  |
| Delivering Victoria’s Bus Plan 2022-23 (statewide) | 28 926 | 25 710 | 3 216 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.152 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 to deliver additional wayfinding and bus stop treatments. |  |  |  |  |  |
| Fishermans Bend Innovation Precinct at the former General Motors Holden Site – Stage 1 (Melbourne) | 197 743 | 184 243 | 8 500 | 5 000 | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with delays arising from external utilities authorities. |  |  |  |  |  |
| Great Ocean Road Renewal (Barwon South West) | 252 569 | 195 707 | 44 577 | 12 284 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with further development on Beauty Gully Road, Maits Rest Safety Improvements and landslip works. |  |  |  |  |  |
| Improving bus and ferry services 2024-25 (statewide) | 4 891 | 4 476 | 415 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with additional planning and design works following consultation on the Bass region bus service improvements. |  |  |  |  |  |
| Improving bus and ferry services 2025-26 (statewide) | 39 724 | 2 421 | 37 303 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with time required to confirm ongoing operational arrangements. The TEI includes $37.149 million from the Growth Areas Infrastructure Contribution. |  |  |  |  |  |
| Keeping Trams Moving (statewide) | 35 717 | 29 066 | 6 651 | .. | qtr 2 2026-27 |
| The TEI has decreased by $1.000 million due to works now being delivered directly by the City of Melbourne. The estimated completion date has been revised to quarter 2 2026-27 due to revised design requirements for kerb separation. |  |  |  |  |  |
| Kilmore Bypass (Kilmore) | 35 270 | 28 193 | 5 476 | 1 601 | qtr 2 2026-27 |
| Local ports critical maintenance (regional various) | 7 000 | .. | 1 000 | 6 000 | qtr 4 2029-30 |
| The estimated completion date has been revised to quarter 4 2029-30 in line with a revised project schedule. |  |  |  |  |  |
| Maintaining Victoria’s road network (statewide) | 145 425 | 142 014 | 3 411 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.392 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 due to finalisation of pavement rehabilitation works. |  |  |  |  |  |
| Mallacoota – Genoa Road Upgrade (East Gippsland) | 10 000 | 3 000 | 5 000 | 2 000 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. The TEI is funded by $10.000 million of Commonwealth Government funding. |  |  |  |  |  |
| Metropolitan Road and Intersection Upgrades (metropolitan various) | 120 417 | 94 646 | 20 719 | 5 052 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 to reflect safety improvements for the South Gippsland Highway and Lynbrook Boulevard projects. |  |  |  |  |  |
| Metropolitan road upgrades 2021-22 (metropolitan various) | 49 930 | 34 820 | 4 691 | 10 419 | qtr 1 2026-27 |
| The estimated completion date has been revised to quarter 1 2026-27 to reflect safety standards requirements. The TEI includes $30.000 million of Commonwealth Government funding. |  |  |  |  |  |
| Metropolitan road upgrades 2022-23 (metropolitan various) | 102 961 | 59 748 | 36 962 | 6 251 | qtr 3 2027-28 |
| The TEI has increased by $4.212 million due to additional developer contributions. The estimated completion date has been revised to quarter 3 2027-28 in line with approved scope and scheduling for the Derrimut Road and Boundary Intersection Upgrade project. |  |  |  |  |  |
| Metropolitan roads upgrade program 2024-25 (metropolitan various) | 24 195 | 13 620 | 8 762 | 1 813 | qtr 4 2026-27 |
| The TEI includes $7.652 million of Commonwealth Government funding. |  |  |  |  |  |
| Metropolitan roads upgrade program 2025-26 (metropolitan various) | 15 672 | 175 | 1 325 | 14 171 | qtr 4 2027-28 |
| The TEI has increased by $2.000 million reprioritised from the Regional roads upgrade program 2025-26 initiative. The estimated completion date has been revised to quarter 4 2027-28 in line with a change in scope and additional projects being delivered under this initiative. |  |  |  |  |  |
| More piers, jetties and opportunities (statewide) | 40 000 | 29 950 | 10 050 | .. | qtr 4 2026-27 |
| North East Link (State and Freeway Packages) |  |  |  |  |  |
| Eastern Freeway Upgrade (Springvale to Hoddle) | 5 708 993 | 2 935 092 | 1 694 270 | 1 079 630 | qtr 2 2028-29 |
| The estimated expenditure has now been disclosed following contract award. The Commonwealth Government is contributing $5.000 billion to the North East Link program. |  |  |  |  |  |
| M80 Ring Road Upgrade (Greensborough) | 3 824 210 | 2 387 391 | 785 007 | 651 812 | qtr 2 2028-29 |
| The Commonwealth Government is contributing $5.000 billion to the North East Link program. |  |  |  |  |  |
| North East Link Connections (Bulleen/Watsonia) | 2 642 257 | 1 854 891 | 481 087 | 306 279 | qtr 2 2028-29 |
| The Commonwealth Government is contributing $5.000 billion to the North East Link program. |  |  |  |  |  |
| Pakenham Roads Upgrade (Pakenham) | 416 321 | 367 757 | 46 914 | 1 649 | qtr 1 2026-27 |
| The TEI has increased by $0.621 million due to additional developer contributions. The estimated completion date has been revised to quarter 1 2026-27 in line with accelerated progress. The TEI includes $415.700 million of Commonwealth Government funding. |  |  |  |  |  |
| Planning Shepparton bypass and improving links in Shepparton (Shepparton) | 7 640 | 2 781 | 3 424 | 1 435 | qtr 1 2027-28 |
| The estimated completion date has been revised to quarter 1 2027-28 in line with funding approvals from the Commonwealth Government. |  |  |  |  |  |
| Port-Rail shuttle (metropolitan intermodal system) (metropolitan various) | 58 000 | 39 428 | 11 772 | 6 800 | qtr 4 2029-30 |
| The TEI includes $38.000 million of Commonwealth Government funding. |  |  |  |  |  |
| Princes Highway Corridor (regional various) | 155 813 | 103 730 | 45 466 | 6 616 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 due to interdependencies with the relocation of the existing rail level crossing. The TEI includes $145.328 million of Commonwealth Government funding. |  |  |  |  |  |
| Public transport accessibility and amenity upgrades (statewide) | 13 739 | 10 119 | 2 119 | 1 501 | qtr 1 2027-28 |
| The estimated completion date has been revised to quarter 1 2027-28 in line with comprehensive planning of safety and accessibility treatments to be delivered. |  |  |  |  |  |
| Regional road upgrades 2021-22 (regional various) | 39 191 | 21 842 | 9 165 | 8 184 | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. The TEI includes $22.480 million of Commonwealth Government funding. |  |  |  |  |  |
| Regional road upgrades 2022-23 (regional) | 100 885 | 34 074 | 17 472 | 49 339 | qtr 4 2027-28 |
| The TEI has decreased by $0.500 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $38.798 million of Commonwealth Government funding. |  |  |  |  |  |
| Regional road upgrades 2024-25 (regional) | 60 542 | 6 014 | 26 140 | 28 388 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29 in line with planning scheme amendments. The TEI includes $28.446 million of Commonwealth Government funding. |  |  |  |  |  |
| Regional roads upgrade program 2025-26 (regional various) | 21 455 | 265 | 50 | 21 140 | qtr 4 2027-28 |
| The TEI has decreased by $7.150 million due to a $2.000 million reprioritisation to the Metropolitan roads upgrade program 2025-26 initiative, a $5.000 million reduction in Commonwealth Government funding and $0.150 million being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $11.552 million of Commonwealth Government funding. |  |  |  |  |  |
| Road Blitz (statewide) | 1 210 389 | 70 878 | 100 191 | 1 039 320 | tbc |
| The TEI has increased by $10.389 million due to additional developer contributions of $11.866 million, partially offset by a $1.477 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $1.000 billion of Commonwealth Government funding. The estimated expenditure for the program is now disclosed following project development activities. The estimated completion date will be disclosed following further project development activities. |  |  |  |  |  |
| Road Blitz to Get Families Home Sooner and Safer (statewide) | 766 412 | 296 588 | 273 229 | 196 595 | qtr 4 2028-29 |
| The TEI has decreased by $1.138 million due to $6.390 million being reclassified as operating instead of capital expenditure, in line with accounting standards. This decrease is partially offset by an increase of $1.277 million from additional third-party contributions and $3.918 million reprioritised from the Safer and Better Connected Communities. The TEI includes $361.008 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Road maintenance 2024-25 (statewide) | 105 000 | 98 155 | 6 845 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 due to finalisation of pavement rehabilitation works. |  |  |  |  |  |
| Road maintenance 2025-26 (statewide) | 53 340 | 49 582 | 3 758 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 due to finalisation of pavement rehabilitation works. |  |  |  |  |  |
| Road Maintenance and Renewal (statewide) | 1 080 990 | 160 410 | 70 579 | 850 000 | qtr 4 2032-33 |
| The TEI has decreased by $10.300 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Roads of Strategic Importance |  |  |  |  |  |
| Roads of Strategic Importance – Green Triangle (Glenelg) | 25 772 | 13 765 | 7 645 | 4 362 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026‑27 in line with a revised project schedule. The TEI includes $24.066 million of Commonwealth Government funding. |  |  |  |  |  |
| Roads of Strategic Importance – Calder Highway (regional various) | 22 674 | 12 910 | 8 524 | 1 239 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. The TEI is funded by $22.674 million of Commonwealth Government funding. |  |  |  |  |  |
| Roads of Strategic Importance – Western Highway – Stawell to SA Border (regional various) | 25 681 | 18 921 | 6 760 | .. | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with service relocation works. The TEI includes $23.222 million of Commonwealth Government funding. |  |  |  |  |  |
| Road Safety Action Plan 2 – Infrastructure Program (statewide) | 140 541 | .. | 35 629 | 104 912 | qtr 4 2027-28 |
| This initiative has been separated into two projects. The TEI has decreased by $13.276 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $140.541 million of funding from the Transport Accident Commission. |  |  |  |  |  |
| Road Safety Action Plan 2 – Commonwealth Road Safety Program | 89 127 | 27 190 | 47 995 | 13 942 | qtr 4 2027-28 |
| This initiative was reported as part of the ‘Road Safety Action Plan 2’ in the 2025-26 Budget and has been separated into two projects. The TEI has increased by $3.950 million due to additional funding from the Transport Accident Commission of $5.000 million, partially offset by a decrease of $1.050 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI is funded by $44.563 million of Commonwealth Government funding and $44.563 million of funding from the Transport Accident Commission. |  |  |  |  |  |
| Rural and Regional Roads Package |  |  |  |  |  |
| Rural and Regional Roads Package – Western Highway – Ararat bypass – Planning and preconstruction (Ararat) | 31 358 | 6 093 | 500 | 24 764 | tbc |
| The TEI has decreased by $16.720 million which has been reprioritised to the Western Highway duplication – Ballarat to Stawell initiative. The estimated completion date is to be confirmed following further project development. The TEI includes $24.039 million of Commonwealth Government funding. |  |  |  |  |  |
| Rural and Regional Roads Package – Western Highway – Beaufort bypass – Planning and preconstruction (Pyrenees) | 29 321 | 8 486 | 500 | 20 335 | tbc |
| The TEI has decreased by $18.757 million which has been reprioritised to the Western Highway duplication – Ballarat to Stawell initiative. The estimated completion date is to be confirmed following further project development. The TEI includes $24.039 million of Commonwealth Government funding. |  |  |  |  |  |
| San Remo Bridge rehabilitation (Newhaven) | 50 413 | 4 103 | 22 443 | 23 866 | qtr 4 2027-28 |
| Securing the safety and productivity of Victoria’s road network (statewide) | 42 036 | 39 378 | 2 658 | .. | qtr 3 2026-27 |
| The TEI has decreased by $0.009 million due to savings from completed stages of works. The estimated completion date has been revised to quarter 3 2026-27 in line with pending environmental approvals for the Maryborough Bridge. |  |  |  |  |  |
| Strengthening Our Dairy Supply Chain (statewide) | 18 900 | 8 821 | 8 384 | 1 695 | qtr 2 2027-28 |
| The TEI has increased by $1.400 million due to additional Commonwealth Government funding. The TEI is funded by $18.900 million of Commonwealth Government funding. |  |  |  |  |  |
| Suburban Roads Upgrade – Northern Roads Upgrade and South Eastern Roads Upgrade (statewide) | 3 320 896 | 2 773 350 | 246 439 | 301 107 | qtr 4 2028-29 |
| The TEI has increased by $2.405 million due to additional developer contributions of $2.643 million and $0.088 million in Commonwealth Government funding, partially offset by a $0.326 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $1 577.369 million of Commonwealth Government funding. |  |  |  |  |  |
| Targeted Road Safety Works (statewide) | 122 334 | 80 860 | 24 832 | 16 642 | qtr 4 2026-27 |
| The TEI has decreased by $0.337 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with approved scope and scheduling for the Western Highway Realignment at Pykes Creek project. The TEI includes $85.295 million of Commonwealth Government funding. |  |  |  |  |  |
| Urban Congestion Fund (statewide) | 152 182 | 83 519 | 16 488 | 52 176 | tbc |
| The estimated completion date is to be confirmed following approval of the scope by the Commonwealth Government. The TEI is funded by $152.182 million of Commonwealth Government funding. |  |  |  |  |  |
| Walking and cycling upgrades – Stage 2 (metropolitan various) | 14 670 | 7 045 | 3 140 | 4 485 | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with the change of delivery model for the Calder Highway-Kings Road Interchange. |  |  |  |  |  |
| Werribee Main Road Interchange Upgrade (Werribee) | 190 067 | 23 209 | 46 209 | 120 649 | qtr 1 2029-30 |
| The TEI has decreased by $59.933 million due to an updated project business case. The estimated completion date is now disclosed following the completion of project development activities. The TEI includes $95.033 million of Commonwealth Government funding. |  |  |  |  |  |
| West Gate Bridge resilience 2025-26 (metropolitan) | 24 020 | 11 242 | 12 778 | .. | qtr 4 2026-27 |
| Western Highway duplication – Ballarat to Stawell (regional various) | tbc | 616 562 | 18 457 | 56 815 | tbc |
| The TEI has been revised to ‘tbc’ and is to be confirmed following further project development and engagement with the Commonwealth Government. The estimated completion date will be confirmed following further project development. The TEI includes $499.380 million of Commonwealth Government funding. |  |  |  |  |  |
| Total existing projects | 28 820 178 | 15 119 146 | 5 478 140 | 8 914 721 |  |
| Total Transport and Planning projects | 29 245 332 | 15 175 162 | 5 766 884 | 8 995 115 |  |
| Other capital expenditure | n.a. | n.a. | 3 635 656 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department, remaining expenditure in 2026-27 for Completed projects in addition to general government sector-funded capital projects reported in Chapter 3 Public non-financial corporations capital program related to the portfolio. This is partially offset by factors including funding held in contingency pending confirmation of project planning and development and capital expenditure associated with public private partnerships. |  |  |  |  |  |
| Total 2026-27 Transport and Planning capital expenditure |  |  | 9 402 540 |  |  |

Source: Department of Transport and Planning

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| 85 by 2025 (Level Crossing Removal) (metropolitan various) | 8 591 666 | 8 314 367 | qtr 4 2027-28 |
| The TEI has decreased by $55.735 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |
| Active Transport (statewide) | 14 886 | 10 163 | qtr 1 2026-27 |
| Building Our Regions (regional various) | 61 950 | 61 889 | qtr 4 2026-27 |
| The TEI includes $13.130 million of Commonwealth Government funding. |  |  |  |
| East Werribee Precinct (metropolitan) | 45 000 | 36 491 | qtr 4 2027-28 |
| Gippsland Lakes port access (regional) | 4 523 | 4 523 | qtr 4 2025-26 |
| Greener Government Buildings (Melbourne) | 59 900 | 59 900 | qtr 1 2025-26 |
| Ison Road Rail Overpass (Werribee) | 109 093 | 87 285 | qtr 4 2026-27 |
| The TEI has increased by $0.119 million due to additional Commonwealth Government funding. The TEI includes $57.019 million of Commonwealth Government funding. |  |  |  |
| Keeping Victorians moving (metropolitan) | 173 127 | 173 127 | qtr 4 2025-26 |
| Market Street Laneway Breakthrough (Barwon South West) | 2 300 | 2 250 | qtr 2 2026-27 |
| Mickleham Road Upgrade – Stage 1 (Greenvale) | 192 221 | 189 612 | qtr 2 2026-27 |
| The TEI has increased by $1.444 million due to an increase of $1.500 million, reprioritised from existing funds. This increase is partially offset by a $0.056 million decrease due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $109.540 million of Commonwealth Government funding. |  |  |  |
| Regional road upgrades 2017-18 (regional various) | 42 232 | 38 070 | qtr 4 2027-28 |
| The TEI includes $11.161 million of Commonwealth Government funding. |  |  |  |
| Strong bridges, stronger economy (statewide) | 41 854 | 40 325 | qtr 4 2027-28 |
| The TEI includes $14.617 million of Commonwealth Government funding. |  |  |  |
| West Gate Bridge resilience 2024-25 (metropolitan) | 24 760 | 24 760 | qtr 2 2025-26 |
| West Gate Tunnel (metropolitan various) | 10 159 204 | 9 999 644 | qtr 2 2027-28 |
| West Gate Tunnel readiness – truck ban enforcement (metropolitan) | 2 982 | 1 514 | qtr 2 2027-28 |

Source: Department of Transport and Planning

Department of Treasury and Finance

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| State Revenue Office (SRO) Expanded Compliance Program 2024 (statewide) | 13 965 | 3 974 | 2 874 | 7 117 | ongoing |
| The estimated completion date has been revised to ongoing to more accurately reflect the schedule of works. |  |  |  |  |  |
| State Revenue Office Advanced Revenue Management Program (Melbourne) | 22 280 | 19 780 | 2 500 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with the revised project schedule. |  |  |  |  |  |
| State Revenue Office Compliance Program (statewide) | 18 926 | 12 726 | 3 850 | 2 350 | ongoing |
| As an ongoing program of works, the TEI varies from year to year. |  |  |  |  |  |
| Total existing projects | 55 171 | 36 480 | 9 224 | 9 467 |  |
| Total Treasury and Finance projects | 55 171 | 36 480 | 9 224 | 9 467 |  |
| Other capital expenditure | n.a. | n.a. | 710 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Treasury and Finance capital expenditure |  |  | 9 934 |  |  |

Source: Department of Treasury and Finance

Parliament

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Supporting the operations of the Independent Broad-based Anti-corruption Commission (statewide) | 4 060 | 1 235 | 960 | 1 865 | qtr 4 2028-29 |
| Total new projects | 4 060 | 1 235 | 960 | 1 865 |  |

Source: Parliament

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Electorate office safety and security upgrades (East Melbourne) | 18 816 | 12 706 | 1 222 | 4 888 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Total existing projects | 18 816 | 12 706 | 1 222 | 4 888 |  |
| Total Parliament projects | 22 876 | 13 941 | 2 182 | 6 753 |  |
| Other capital expenditure | n.a. | n.a. | 2 271 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Parliament capital expenditure |  |  | 4 453 |  |  |

Source: Parliament

Court Services Victoria

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Delivering serious consequences and keeping the community safe (metropolitan) | 25 856 | 20 236 | 1 620 | 4 000 | qtr 4 2026-27 |
| The TEI includes $7.756 million announced in the 2025-26 Budget Update. |  |  |  |  |  |
| Maintaining our court buildings (statewide) | 10 600 | .. | 10 600 | .. | qtr 4 2026-27 |
| Meeting the requirements of the Bail Further Amendment Act 2025 (statewide) | 1 500 | .. | 1 500 | .. | qtr 4 2026-27 |
| Total new projects | 37 956 | 20 236 | 13 720 | 4 000 |  |

Source: Court Services Victoria

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Courts case management system (statewide) | 98 360 | 93 149 | 5 211 | .. | qtr 2 2026-27 |
| The TEI has increased by $18.882 million, $16.812 million due to increased delivery complexity and $2.070 million reprioritised from the New federal jurisdiction matters in the Magistrates’ Court of Victoria (Melbourne) initiative. The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Keeping Courts Open (statewide) | 21 146 | 18 746 | 2 400 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule and a development application to Heritage Victoria for the Supreme Court site. |  |  |  |  |  |
| Specialist family violence integrated court (statewide) | 73 892 | 69 892 | 4 000 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised project schedule for the Broadmeadows site. Construction of the Geelong and Melbourne sites achieved practical completion in quarter 2 2025-26. |  |  |  |  |  |
| Supporting a safe and effective Youth Justice system (Parkville) | 3 236 | 201 | 3 035 | .. | qtr 4 2026-27 |
| The TEI has increased by $1.136 million reprioritised from the Children’s Court of Victoria Clinic and Conference Centre (Melbourne) initiative to support works at the Melbourne Children’s Court to enhance service delivery capability. The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Victorian Civil and Administrative Tribunal digital service transformation (statewide) | 29 000 | 14 941 | 14 059 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a revised project schedule to deliver new requirements following the establishment of Rental Dispute Resolution Victoria. |  |  |  |  |  |
| Total existing projects | 225 634 | 196 929 | 28 705 | .. |  |
| Total Court Services Victoria projects | 263 590 | 217 165 | 42 425 | 4 000 |  |
| Other capital expenditure | n.a. | n.a. | 25 728 | n.a. | n.a. |
| Other capital expenditure includes minor projects and recurrent investment to maintain and upgrade the existing asset base being undertaken and funded by the Department. |  |  |  |  |  |
| Total 2026-27 Court Services Victoria capital expenditure |  |  | 68 153 |  |  |

Source: Court Services Victoria

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Children’s Court of Victoria Clinic and Conference Centre (Melbourne) | 4 553 | 4 553 | qtr 4 2025-26 |
| The TEI has decreased by $1.136 million which has been reprioritised to the Supporting a safe and effective Youth Justice system (Parkville) initiative. |  |  |  |
| New federal jurisdiction matters in the Magistrates’ Court of Victoria (Melbourne) | 1 730 | 1 730 | qtr 4 2025-26 |
| The TEI has decreased by $2.070 million which has been reprioritised to the Courts case management system (statewide) initiative. |  |  |  |

Source: Court Services Victoria

Chapter 3 – Public non-financial corporations capital program 2026-27

Barwon Region Water Corporation

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Recycled water (regional various) | 146 958 | 870 | 205 | 145 883 | various |
| Sewer collection – main sewers (regional various) | 323 253 | 615 | 3 715 | 318 923 | various |
| Sewer collection – reticulation and other works (regional various) | 59 750 | 407 | 2 281 | 57 062 | various |
| Sewer collection – water reclamation and disposal (regional various) | 44 241 | 1 | 513 | 43 728 | various |
| Water supply – reticulation systems (regional various) | 2 448 | .. | .. | 2 448 | various |
| Water supply – transfer and major distribution systems (regional various) | 126 056 | .. | .. | 126 056 | various |
| All remaining projects with a TEI less than $1 million | 3 072 | 1 668 | 350 | 1 054 | various |
| Total new projects | 705 778 | 3 561 | 7 064 | 695 154 |  |

Source: Barwon Region Water Corporation

Note:

(a)	Barwon Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Other works and services – corporate (regional various) (Geelong) | 297 223 | 20 663 | 23 473 | 253 086 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Recycled water (regional various) | 162 594 | 26 576 | 4 915 | 131 102 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Sewer collection – main sewers (regional various) | 557 944 | 20 614 | 23 975 | 513 355 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Sewer collection – reticulation and other works (regional various) | 649 259 | 17 241 | 12 696 | 619 321 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Sewer collection – water reclamation and disposal (regional various) | 1 063 921 | 10 550 | 14 999 | 1 038 372 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water supply – headworks (regional various) | 281 949 | 9 117 | 5 521 | 267 311 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water supply – reticulation systems (regional various) | 347 864 | 7 239 | 10 525 | 330 099 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water supply – transfer and major distribution systems (regional various) | 792 887 | 37 008 | 25 512 | 730 367 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water supply – treatment and quality improvements (regional various) | 63 383 | 5 230 | 3 739 | 54 414 | various |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 19 568 | 2 350 | 3 576 | 13 641 | various |
| Total existing projects | 4 236 592 | 156 588 | 128 931 | 3 951 068 |  |
| Total Barwon Region Water Corporation projects | 4 942 370 | 160 149 | 135 995 | 4 646 222 |  |

Source: Barwon Region Water Corporation

Note:

(a)	Barwon Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Other works and services – corporate (regional various) | 2 812 | 2 812 | various |
| Recycled water (regional various) | 1 499 | 1 499 | various |
| Sewer collection – main sewers (regional various) | 1 815 | 1 815 | various |
| Sewer collection – reticulation and other works (regional various) | 1 791 | 1 791 | various |
| Sewer collection – water reclamation and disposal (regional various) | 4 945 | 4 945 | various |
| Water supply – headworks (regional various) | 1 594 | 1 594 | various |
| Water supply – reticulation systems (regional various) | 8 226 | 8 226 | various |
| Water supply – transfer and major distribution systems (regional various) | 4 147 | 4 147 | various |
| Water supply – treatment and quality improvements (regional various) | 29 | 29 | various |

Source: Barwon Region Water Corporation

Note:

(a)	Barwon Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

Cemeteries

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Altona East Depot Infrastructure (Altona Memorial Park) | 12 000 | .. | 500 | 11 500 | qtr 4 2028-29 |
| BD Arnold Lawn Extension (Springvale) | 1 700 | .. | 460 | 1 240 | qtr 4 2027- 28 |
| Depot Construction (Springvale) | 17 100 | .. | 4 650 | 12 450 | qtr 4 2028-29 |
| East Monumental Development Project Infrastructure (Northern Memorial Park) | 7 077 | .. | 7 077 | .. | qtr 4 2026-27 |
| East Monumental Development Project Inventory (Northern Memorial Park) | 12 143 | 500 | 6 366 | 5 277 | qtr 4 2027-28 |
| Harmony (Springvale) | 1 400 | .. | 451 | 949 | qtr 4 2027- 28 |
| Lilydale Memorial Park Inventory Development (Lilydale) | 6 500 | .. | 500 | 6 000 | qtr 4 2027-28 |
| New Song He Yuan Final Extension (Springvale) | 4 400 | .. | 3 025 | 1 375 | qtr 4 2027- 28 |
| Project Horizon (Springvale) | 1 800 | .. | 1 800 | .. | qtr 4 2027-28 |
| Spoilyard Inventory (Altona Memorial Park) | 11 000 | .. | 500 | 10 500 | qtr 4 2028-29 |
| All remaining new projects with a TEI less than $1 million | 15 990 | 3 398 | 12 375 | 217 | various |
| Total new projects | 91 110 | 3 898 | 37 704 | 49 508 |  |

Source: Cemeteries

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| All Souls mausoleum stage 2 (Springvale) | 4 520 | 359 | 4 161 | .. | qtr 2 2026-27 |
| AMP Altona Eastern Reserve (Altona) | 13 500 | 500 | 3 000 | 10 000 | qtr 4 2027-28 |
| The TEI has decreased by $1.492 million following budget allocation review. The estimated completion date of the project has been revised to quarter 4 2027-28. |  |  |  |  |  |
| Cemetery Development – burial/ memorial areas (various) | 1 671 | 420 | 452 | 799 | qtr 4 2029-30 |
| Crematorium Upgrade Project (Geelong Memorial Park) | 3 100 | 1 000 | 1 500 | 600 | qtr 3 2027-28 |
| The project name has changed from ‘Building Rectification/Expansion – Crematorium (Geelong)’ when it was published in the 2025-26 Budget. The TEI has increased by $1.600 million as the design scope has been expanded to meet existing and projected future service levels. The estimated completion date has been revised to quarter 3 2027-28 in line with expanded scope. |  |  |  |  |  |
| Emerald South Stage 1 (Avonsleigh) | 11 800 | 510 | 11 290 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.651 million following budget allocation review. |  |  |  |  |  |
| Footpath renewal program (statewide) | 1 789 | 180 | 180 | 1 429 | ongoing |
| The TEI has decreased by $0.255 million following budget allocation review. |  |  |  |  |  |
| HRK Harkness Stage 1A (Harkness) | 41 600 | 18 816 | 22 784 | .. | qtr 4 2026-27 |
| The TEI has decreased by $2.439 million due to revision of this project as a program of work noting the projects for this development will be undertaken in stages. |  |  |  |  |  |
| Plant and Equipment Replacement Program (statewide) | 26 600 | 2 300 | 2 300 | 22 000 | ongoing |
| The TEI has increased by $3.793 million to align with latest planned asset renewal forecasts. |  |  |  |  |  |
| River Red Gum Stage 2 Inventory (Northern Memorial Park) (Glenroy) | 7 430 | 2 630 | 4 800 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.570 million following budget allocation review. |  |  |  |  |  |
| Road rehabilitation program (statewide) | 7 129 | 1 729 | 450 | 4 950 | ongoing |
| The TEI has decreased by $0.419 million following budget allocation review. |  |  |  |  |  |
| Superlot 3 wetland and habitat restoration (Dandenong South) | 18 000 | 1 200 | 11 800 | 5 000 | qtr 3 2027-28 |
| The TEI includes a $8.200 million grant from Department of Climate Change, Energy, the Environment and Water. |  |  |  |  |  |
| The Garden of No Distant Place development and reflections garden rectification (Springvale) | 1 408 | 200 | 1 208 | .. | qtr 2 2026-27 |
| Werribee Mausoleum Extension (Werribee) | 6 190 | 3 888 | 2 302 | .. | qtr 4 2026-27 |
| All remaining existing projects with a TEI less than $1 million | 15 909 | 5 206 | 7 739 | 2 964 | various |
| Total existing projects | 160 646 | 38 938 | 73 966 | 47 742 |  |
| Total Cemeteries projects | 251 756 | 42 836 | 111 670 | 97 250 |  |

Source: Cemeteries

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Botanical Hill stage 2 (Springvale) | 9 152 | 9 152 | qtr 4 2025-26 |
| Customer portal creation and retail system replacement (statewide) | .. | .. | .. |
| This project has been cancelled after management review. |  |  |  |
| Dam hardstand (Springvale) | 1 100 | 1 100 | qtr 4 2025-26 |
| The TEI has decreased by $0.900 million due to lower than anticipated costs and reduction to project scope. |  |  |  |
| Islamic lawn development (Dandenong South) | 1 505 | 1 505 | qtr 3 2025-26 |
| Keilor Administration Building Repurposing (Keilor) | .. | .. | .. |
| This project has been cancelled after management review. |  |  |  |
| Non-denominational monumental (Dandenong South) | 1 392 | 1 392 | qtr 1 2025-26 |
| The TEI has decreased by $0.115 million due to lower than anticipated costs. |  |  |  |
| Project cultivate horticultural uplift phase 1C (Melbourne) | 1 500 | 1 500 | qtr 4 2025-26 |
| River Red Gum Stage 2 Infrastructure Development (Northern Memorial Park) (Glenroy) | 23 600 | 23 600 | qtr 4 2025-26 |
| The Glades ornamental lawn (Dandenong South) | 1 223 | 1 223 | qtr 1 2025-26 |
| The TEI has decreased by $0.653 million due to lower than anticipated costs. |  |  |  |
| All remaining completed projects with a TEI less than $1 million | 19 462 | 19 462 | qtr 4 2025-26 |

Source: Cemeteries

Central Gippsland Region Water Corporation

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Other works and services – corporate (regional various) | 4 557 | 300 | 159 | 4 098 | various |
| Sewer treatment (regional various) | 4 453 | 51 | 53 | 4 349 | various |
| Water supply – raw water headworks (regional various) | 8 438 | .. | 265 | 8 174 | various |
| All remaining projects with a TEI less than $1 million | 1 982 | 512 | 476 | 994 | various |
| Total new projects | 19 430 | 863 | 953 | 17 615 |  |

Source: Central Gippsland Region Water Corporation

Note:

(a)	Central Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Non prescribed – Gippsland regional Agribusiness (regional various) | 2 811 | 520 | 333 | 1 958 | various |
| The TEI has increased by $0.991 million due to a project Dutson Plantation Seedling and Replanting Program being reclassified from All remaining projects with a TEI less than $1 million. |  |  |  |  |  |
| Non prescribed – Gippsland regional organics (Dutson) | 29 538 | 3 051 | 2 033 | 24 455 | various |
| The TEI has decreased by $2.386 million, reflecting the completion of projects and adjustments to the prior year’s TEI. |  |  |  |  |  |
| Other works and services – corporate (regional various) | 104 552 | 15 790 | 7 322 | 81 440 | various |
| The TEI has increased by $10.023 million due to revised project scope. |  |  |  |  |  |
| Sewer collection – branch sewer and sewer rising main (regional various) | 104 099 | 2 290 | 5 650 | 96 159 | various |
| The TEI has increased by $18.095 million due to expanded scope relating to sewer network improvements around the western region. |  |  |  |  |  |
| Sewer collection – reticulation and other collection works (regional various) | 173 750 | 9 999 | 26 099 | 137 652 | various |
| The TEI has increased by $10.918 million due to revised scope and updated delivery requirements. |  |  |  |  |  |
| Sewer treatment (regional various) | 214 461 | 8 945 | 9 395 | 196 121 | various |
| The TEI has decreased by $14.160 million due to revised scheduling and scope for the Gippsland water factory. |  |  |  |  |  |
| Water supply – mains and transfer (regional various) | 87 839 | 4 356 | 21 271 | 62 212 | various |
| The TEI has increased by $17.066 million due to revised schedule and additional scope for connecting Traralgon and Morwell water networks. |  |  |  |  |  |
| Water supply – raw water headworks (regional various) | 17 347 | 963 | 1 602 | 14 783 | various |
| The TEI has increased by $0.733 million due to updated scope requirements for raw water headworks. |  |  |  |  |  |
| Water supply – reticulation (regional various) | 83 510 | 4 741 | 4 132 | 74 636 | various |
| The TEI has increased by $16.758 million due to revised planning and scope. |  |  |  |  |  |
| Water treatment and quality (regional various) | 178 683 | 11 739 | 15 079 | 151 864 | various |
| The TEI has decreased by $2.863 million due to revised scope. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 36 195 | 1 823 | 5 211 | 29 161 | various |
| The TEI has decreased by $4.382 million due to reclassification of remaining minor projects into other reporting categories. |  |  |  |  |  |
| Total existing projects | 1 032 786 | 64 219 | 98 127 | 870 440 |  |
| Total Central Gippsland Region Water Corporation projects | 1 052 216 | 65 082 | 99 080 | 888 055 |  |

Source: Central Gippsland Region Water Corporation

Note:

(a)	Central Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Non prescribed – Gippsland regional organics (Dutson) | 1 187 | 1 187 | qtr 4 2025-26 |
| Other works and services – corporate (regional various) | 2 042 | 2 042 | qtr 4 2025-26 |
| Sewer collection – branch sewer and sewer rising main (regional various) | 8 462 | 8 462 | qtr 4 2025-26 |
| Water supply – reticulation (regional various) | 1 045 | 1 045 | qtr 4 2025-26 |
| Water treatment and quality (regional various) | 5 463 | 5 463 | qtr 4 2025-26 |
| All remaining projects with a TEI less than $1 million | 1 021 | 1 021 | qtr 4 2025-26 |

Source: Central Gippsland Region Water Corporation

Note:

(a)	Central Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Central Highlands Region Water Corporation

Existing projects (a)(b)(c)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Fleet replacement program and building maintenance (regional various) | 33 003 | 8 561 | 1 557 | 22 885 | ongoing |
| The TEI has decreased by $6.874 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Headworks improvements – construction (regional various) | 90 580 | 9 459 | 7 191 | 73 930 | ongoing |
| The TEI has increased by $34.432 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, an increased reported TEI is in relation to expected upcoming drought resilience projects. |  |  |  |  |  |
| Information management implementation (regional various) | 31 519 | 2 410 | 236 | 28 873 | ongoing |
| The TEI has decreased by $24.202 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Land development shared assets (regional various) | 4 787 | 653 | 396 | 3 738 | ongoing |
| The TEI has increased by $0.074 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, a major project that has been reported under this program previously is expected to be completed during 2025-26, the Upsizing and efficiency program – Pinnacle trunk sewer (Ballarat). |  |  |  |  |  |
| Sewerage collection system upgrade (regional various) | 106 628 | 3 113 | 8 558 | 94 957 | ongoing |
| The TEI has decreased by $102.905 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, a major project that has been reported under this program previously is expected to be completed during 2025-26, the Ballarat sewer build – Ballarat south outfall project (Ballarat). |  |  |  |  |  |
| Wastewater reticulation replacements (regional various) | 42 949 | 8 481 | 2 401 | 32 067 | ongoing |
| The TEI has decreased by $21.121 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, a major project that has been reported under this program previously is expected to be completed during 2025-26, the Sewer rising main renewals program – Creswick sewerage pumping station rising main upgrade (Ballarat). |  |  |  |  |  |
| Wastewater treatment plant upgrades (regional various) | 279 896 | 11 526 | 9 180 | 259 190 | ongoing |
| The TEI has increased by $115.524 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, a major project that has been reported under this program previously is expected to be completed during 2025-26, the Regional recycled water – Daylesford wastewater treatment plant reuse expansion (Daylesford). |  |  |  |  |  |
| Water meters replacement (regional various) | 27 747 | 13 925 | 4 044 | 9 778 | ongoing |
| The TEI has decreased by $6.993 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Water network upgrades (regional various) | 184 793 | 2 341 | 5 078 | 177 374 | ongoing |
| The TEI has decreased by $77.294 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Water quality improvement (regional various) | 19 009 | 162 | 195 | 18 652 | ongoing |
| The TEI has decreased by $1.055 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Water reticulation replacement (regional various) | 69 639 | 10 287 | 4 286 | 55 066 | ongoing |
| The TEI has decreased by $34.406 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Water supply (tanks) renewal (regional various) | 31 478 | 3 005 | 2 979 | 25 494 | ongoing |
| The TEI has decreased by $14.334 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Water treatment plant upgrade (regional various) | 42 081 | 9 662 | 8 924 | 23 495 | ongoing |
| The TEI has decreased by $5.791 million. Refer to general footnotes (a), (b) and (c) for explanation. Additionally, a major project that has been reported under this program previously that has or is expected to be completed during 2025-26 includes White Swan UV upgrade (Ballarat). |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 486 | .. | 486 | .. |  |
| The TEI has decreased by $25.601 million. Refer to general footnotes (a), (b) and (c) for explanation. |  |  |  |  |  |
| Total existing projects | 964 595 | 83 585 | 55 511 | 825 499 |  |
| Total Central Highlands Region Water Corporation projects | 964 595 | 83 585 | 55 511 | 825 499 |  |

Source: Central Highlands Region Water Corporation

Notes:

(a) 	Central Highlands Region Water oversees programs of works that appear in the existing and completed projects year on year. As such, as forecasts are revised continuously, and as components of these programs move from existing to completed, program TEIs are likely to vary significantly from year to year. Program TEIs capture historical expenditure from 2023-24 onwards, and are forecast out to 2036-37.

(b) 	A change in project classification has resulted in a reduction of projects listed against ‘All remaining projects with a TEI less than $1 million’. These are now listed against various other classifications, resulting in a change of TEI.

(c) 	A re-evaluation of projected capital budgets has resulted in a downward revision across Central Highlands Region Water’s capital plan by approximately $190 million over the next 10 years.

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Ballarat sewer build – Ballarat south outfall project (Ballarat) | 20 897 | 20 897 | qtr 4 2025-26 |
| This project was originally captured under the Sewerage collection system upgrade (regional various) program. |  |  |  |
| Regional recycled water – Daylesford wastewater treatment plant reuse expansion (Daylesford) | 2 232 | 2 232 | qtr 4 2025-26 |
| This project was originally captured under the Wastewater treatment plant upgrades (regional various) program. |  |  |  |
| Sewer network – sewer rising main renewals program – Creswick sewerage pumping station rising main upgrade (Ballarat) | 2 330 | 2 330 | qtr 4 2025-26 |
| This project was originally captured under the Wastewater reticulation replacements (regional various) program. |  |  |  |
| Upsizing and efficiency program – Pinnacle trunk sewer (Ballarat) | 3 552 | 3 552 | qtr 4 2025-26 |
| This project was originally captured under the Land development shared assets (non-metro various) program. Project completion was anticipated in quarter 4 2024-25, however, has been revised due to delays in relation to a contractor liquidation event. The TEI has decreased by $0.012 million due to a reduced contingency allowance as completion nears. |  |  |  |
| White Swan UV upgrade (Ballarat) | 2 857 | 2 857 | qtr 4 2025-26 |
| This project was originally captured under the Water treatment plant upgrade (regional various) program. |  |  |  |

Source: Central Highlands Region Water Corporation

Coliban Region Water Corporation

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Castlemaine link (various) | 99 800 | 2 568 | 2 255 | 94 977 | qtr 2 2031-32 |
| The TEI is a current estimate, to be finalised in the business case in November 2026. |  |  |  |  |  |
| Corporate (various digital technology, SCADA and operations facilities) (various) | 6 229 | 1 321 | 1 769 | 3 139 | various |
| New projects to be included in the Corporate program of work include: Operations Facility, Treatment Plant Planning, Large Generation Certificate Purchase C23, Climate Change Adaptation – Energy Resilience. |  |  |  |  |  |
| Victorian-led Coliban Rural Water Efficiency Project | 118 250 | 45 000 | 39 125 | 34 125 | qtr 4 2030-31 |
| The TEI is funded by $118.250 million of Commonwealth Government funding (Federation Funding Agreement – Environment). The funding contribution from Coliban Water is not included in this table. |  |  |  |  |  |
| Total new projects | 224 279 | 48 889 | 43 149 | 132 241 |  |

Source: Coliban Region Water Corporation

Note:

(a) 	Coliban Region Water has consolidated a number of smaller projects into broader annual programs or larger projects with varying completion dates. A footnote has been included to identify the projects comprising these programs of works.

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Bendigo water reclamation plant solids handling upgrade (Bendigo) | 147 620 | 21 242 | 61 076 | 65 302 | qtr 3 2028-29 |
| The estimated completion date has been revised to quarter 3 2028-29 due to a revised project schedule. |  |  |  |  |  |
| Bendigo water reclamation upgrades (Bendigo) | 293 079 | 10 482 | 6 826 | 275 771 | qtr 4 2031-32 |
| The TEI has increased by $6.749 million due to increased scope. The estimated completion date has been revised to quarter 4 2031-32 to reflect refinement of the business case. |  |  |  |  |  |
| Bulk water (regional various) | 32 482 | 30 450 | 942 | 1 090 | various |
| This program is made up of the following projects from the 2025-26 Budget: High Priority Main Channel Replacements (regional various), Land Management (regional various), Occupational Health and Safety remedial upgrades of main channel offtakes (regional various), Raw Water Systems Investigations (regional various), Reservoir Renewals and Improvements Program (regional various), Superpipe (regional various), and projects previously categorised as having a TEI of less than $1 million. |  |  |  |  |  |
| Castlemaine water reclamation plant upgrade (Castlemaine) | 189 600 | 10 656 | 13 067 | 165 877 | qtr 4 2030-31 |
| The TEI has increased by $13.330 million to reflect revised contingency allowances. The estimated completion date has been revised to quarter 4 2030-31 to reflect the approval of the business case. |  |  |  |  |  |
| Corporate (various digital technology, SCADA and operations facilities) (various) | 60 093 | 45 788 | 8 831 | 5 474 | various |
| This program is made up of the following projects from the 2025-26 Budget: Asset information management system enhancements and data (Bendigo), Bendigo emergency power Eppalock hydroelectricity plant (Bendigo), IT equipment (Bendigo), Occupational health and safety remedial works program (regional various), Planned corrective reactive maintenance (regional various), Renewable energy initiatives (regional various), Supervisory control and data acquisition hardware (Bendigo), Supervisory control and data acquisition software and security (Bendigo), Integrated Water and Sewer Planning, Vehicle renewals (regional various), Future Workplace (Bendigo). |  |  |  |  |  |
| Recycled water (regional various) | 30 886 | 10 389 | 7 588 | 12 909 | various |
| This new program aggregates two projects from the 2025-26 Budget, Recycled water class A reconfiguration (Bendigo) and Bendigo water reclamation plant recycled water factory upgrade (Bendigo). |  |  |  |  |  |
| Rural channel system modernisation (regional various) | 160 000 | 1 500 | 17 750 | 140 750 | qtr 4 2033-34 |
| The TEI has increased by $154.281 million due to revised scope approved via business case. The project includes $120.000 million in Commonwealth Government funding under the Resilient River Water Infrastructure Program. The estimated completion date has been revised to quarter 4 2033-34 to reflect the approval of the business case. |  |  |  |  |  |
| Rural water (regional various) | 2 594 | 1 844 | 541 | 209 | various |
| This program aggregates a number of projects of the Channel renewals (regional various) projects from the 2025-26 Budget. |  |  |  |  |  |
| Sewerage – pipelines/network (various) | 185 014 | 20 054 | 15 968 | 148 993 | various |
| This program aggregates the following projects from the 2025-26 Budget: Bendigo sewer emergency relief structures program (Bendigo), Bendigo sewer outfall and long gully trunk main augmentation and compliance (Bendigo), Castlemaine sewerage Campbells Creek sewer pump station 1 additional storage (Castlemaine), Developer shared sewer assets (regional various), Eaglehawk sewer compliance upgrades (Bendigo), Malmsbury outfall sewer augmentation (Malmsbury), Kyneton sewerage Jeffrey Street sewer pump station (Kyneton), Maiden Gully and Marong sewer compliance upgrade (Bendigo), Mannes Lane Strathfieldsaye sewer pump station renewal (Bendigo), New customer pressure sewer works (regional various), Sewer main renewals (regional various), Sewer network improvements and enhancement program (regional various), Sewer pumping station renewals (regional various), Craigie Street Harcourt sewer pump station (Harcourt). |  |  |  |  |  |
| Sewerage – treatment (various) | 38 383 | 14 999 | 5 058 | 18 326 | various |
| This program aggregates the following projects from the 2025-26 Budget: Cohuna water reclamation plant upgrade (Cohuna), Heathcote water reclamation plant and reuse system upgrade (Heathcote), Water reclamation plant renewals and optimisation (regional various). |  |  |  |  |  |
| Water – pipelines/network (regional various) | 93 123 | 54 541 | 7 961 | 30 620 | various |
| This program aggregates the following projects from the 2025-26 Budget: Bendigo water treatment plant outlet security of supply (Bendigo), Developer shared water assets (regional various), Digital customer metering program (regional various), Edwards Road tank to Strathfieldsaye water main (Bendigo), Intelligent water networks program (regional various), Low pressure towns (Bendigo), Maiden Gully Marong water growth project C (regional various), Maiden Gully Marong water growth project B (regional various), Meter replacement program (regional various), Strathfieldsaye water network augmentation stage 1 (Bendigo), System flow meter renewals and optimisation (regional various), Trentham water treatment plant clear water storage (Trentham), Water main renewals (regional various), Kalimna Basin (Castlemaine). |  |  |  |  |  |
| Water – treatment (regional various) | 160 968 | 36 262 | 19 167 | 105 539 | various |
| This program aggregates the following projects from the 2025-26 Budget: Bendigo water treatment plant clear water storage (Bendigo), Bendigo water treatment plant membrane upgrade (Bendigo), Bridgewater system tank renewals (Bridgewater), Cohuna water treatment plant upgrade Stage 2 (Cohuna), Echuca water treatment plant stage 2 upgrades (Echuca), Groundwater supply Goornong water treatment plant (Goornong), Gunbower water treatment plant upgrades (Gunbower), Trentham water treatment plant capacity upgrade (Trentham), Water treatment plant programmable logic controller renewal program (regional various), Water treatment plant renewals and optimisation (regional various). |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million (various) | 4 755 | 3 211 | 1 298 | 246 | various |
| Total existing projects | 1 398 597 | 261 418 | 166 073 | 971 106 |  |
| Total Coliban Region Water Corporation projects | 1 622 876 | 310 307 | 209 222 | 1 103 347 |  |

Source: Coliban Region Water Corporation

Note:

(a) 	Coliban Region Water has consolidated a number of smaller projects into broader annual programs or larger projects with varying completion dates. A footnote has been included to identify the projects comprising these programs of works.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Bendigo biosolids handling facility enhancements (Bendigo) | 439 | 439 | qtr 4 2025-26 |
| The TEI has been redirected to enable this project to be carried out within Bendigo water reclamation plant solids handling upgrade (Bendigo). |  |  |  |
| Bendigo, Castlemaine and Kyneton water treatment plant health-based targets upgrades (regional various) | 20 909 | 19 700 | qtr 4 2025-26 |
| The estimated completion date has been revised to quarter 4 2025‑26 to reflect a revised project schedule. |  |  |  |

Source: Coliban Region Water Corporation

Note:

(a) 	Coliban Region Water has consolidated a number of smaller projects into broader annual programs or larger projects with varying completion dates. A footnote has been included to identify the projects comprising these programs of works.

East Gippsland Region Water Corporation

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Generators Critical Sites – Water and Sewer (regional various) | 8 717 | 17 | 1 000 | 7 700 | ongoing |
| Marlo Clear Water Storage Tank and Pump Station – Water (Orbost) | 4 469 | 21 | .. | 4 448 | qtr 4 2028-29 |
| Total new projects | 13 186 | 38 | 1 000 | 12 148 |  |

Source: East Gippsland Region Water Corporation

Note:

(a) 	East Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Bairnsdale North Growth Corridor – (Water Pump Stations, Main Supply Pipelines) (regional various) | 22 184 | 1 087 | 5 029 | 16 068 | ongoing |
| The TEI has increased by $6.173 million due to additional projects included in the program. |  |  |  |  |  |
| Bairnsdale Recycled Water Plant upgrade (Bairnsdale) | 113 500 | 762 | 200 | 112 538 | qtr 4 2029‑30 |
| The project name has changed from ‘Bairnsdale Sewage Treatment Plant Upgrade’ when it was published in the 2025-26 Budget. The TEI has increased by $0.034 million due to detailed design estimates. The estimated completion date has been revised to quarter 4 2029-30 to reflect a revised schedule of works. |  |  |  |  |  |
| Corporate – Other (Vehicles, Plant and Equipment, Site Security, Depots Buildings, HSE) (regional various) | 4 460 | 2 372 | 300 | 1 788 | ongoing |
| The TEI has decreased by $1.022 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |  |  |
| Corporate – Systems (Including IT) (SCADA, Digital Meters, IT Hardware, Total Asset Management) (regional various) | 15 308 | 4 979 | 2 004 | 8 325 | ongoing |
| The TEI has increased by $2.163 million due to additional projects included in the program. |  |  |  |  |  |
| Environment – Sustainability (Energy Offsets, Solar, Digester) (regional various) | 4 026 | 1 456 | 300 | 2 270 | ongoing |
| The TEI has increased by $1.716 million due to additional projects included in the program. |  |  |  |  |  |
| Paynesville Water Recycling Plant Winter Storage (Paynesville) | 14 058 | 14 058 | .. | .. | qtr 4 2027‑28 |
| The TEI has increased by $3.703 million following the tender award. The estimated completion date has been revised to quarter 4 2027-28 to reflect a revised project delivery schedule. |  |  |  |  |  |
| Recycled Water class A treatment plant (Bairnsdale) | 2 306 | 677 | 1 629 | .. | qtr 3 2026‑27 |
| The TEI has decreased by $0.394 million following the tender award. The estimated completion date has been revised to quarter 3 2026-27 to reflect a revised schedule of works. The TEI includes $1.170 million of State Government funding. |  |  |  |  |  |
| Sewer – Growth (Sewer Pump Stations, Rising Mains, Sewer Mains, Reticulation mains) (regional various) | 4 611 | 1 077 | 1 | 3 533 | ongoing |
| The TEI has increased by $1.445 million due to additional projects included in the program. |  |  |  |  |  |
| Sewer – Regulatory Compliance (Sewer Treatment, Odour, Biosolids, Ground Water monitoring, Generators) (regional various) | 25 387 | 6 689 | 8 461 | 10 237 | ongoing |
| The TEI has increased by $6.430 million due to additional projects included in the program. |  |  |  |  |  |
| Sewer – Renewals (Sewer Pump Stations, Rising Mains, Irrigation Stations, Pressure Sewers, Sewer Treatment) (regional various) | 24 217 | 6 694 | 7 459 | 10 064 | ongoing |
| The TEI has increased by $4.388 million due to additional projects included in the program. |  |  |  |  |  |
| Water – Growth (Main Supply pipelines, Reticulation pipelines, Water Pump Stations) (regional various) | 12 553 | 662 | 406 | 11 485 | ongoing |
| The TEI has increased by $8.800 million due to the reclassification of projects and associated funding, with corresponding decreases in the Water – Growth, and Water – Regulatory Compliance programs. |  |  |  |  |  |
| Water – Regulatory Compliance (Water Treatment, Safety upgrades, Filter Access, UV Disinfection) (regional various) | 5 608 | 1 457 | 886 | 3 265 | ongoing |
| The TEI has increased by $0.842 million due to the reclassification of projects and associated funding, with corresponding increases in the Water – Growth, and Water – Regulatory Compliance programs. |  |  |  |  |  |
| Water – Renewals (Pumps, Main Supply pipelines, Reticulation pipelines, Water Pump Stations, Switchboards) (regional various) | 27 025 | 2 723 | 1 895 | 22 407 | ongoing |
| The TEI has decreased by $1.342 million due to the reclassification of projects and associated funding, with corresponding increases in the Water – Growth, and Water – Regulatory Compliance programs. |  |  |  |  |  |
| Water – Security and Reliability (Basins, Tanks, Water Pump Stations and Pipelines) (regional various) | 12 003 | 833 | .. | 11 170 | ongoing |
| The TEI has decreased by $12.289 million due to the reclassification of projects and associated funding to the Water – Growth, and Water – Regulatory Compliance programs. |  |  |  |  |  |
| Woodglen water treatment plant #3 raw water storage basin (Woodglen) | 61 007 | 3 994 | 2 013 | 55 000 | qtr 3 2028‑29 |
| The TEI has increased by $2.327 million due to detailed design estimates. The estimated completion date has been revised to quarter 3 2028-29 in line with this revision. The TEI includes $1.110 million of Commonwealth Government funding from the National Water Grid Fund. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 1 187 | 1 187 | .. | .. | ongoing |
| The TEI has increased by $0.471 million due to additional projects included in the program. This program of works consolidates projects with a TEI less than $1 million into a single project line item, ‘All remaining projects with TEI less than $1 million’, combining Water – Headworks (Raw Water Offtakes), Alternative Suppliers – Recycled Water (Class A, Treatment and Network) and Environment – Waterways and Drainage (Wetlands, Erosion) projects delivered across regional various locations. The TEI includes $0.477 million of State Government funding for treated recycled water pipelines. |  |  |  |  |  |
| Total existing projects | 349 440 | 50 707 | 30 583 | 268 150 |  |
| Total East Gippsland Region Water Corporation projects | 362 626 | 50 745 | 31 583 | 280 298 |  |

Source: East Gippsland Region Water Corporation

Note:

(a) 	East Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Buchan Clear water tanks 1ML replacement (Buchan) | 4 780 | 4 780 | qtr 4 2025‑26 |
| The TEI has increased by $0.319 million following tender award. The TEI includes $1.905 million of Commonwealth Government funding from the National Water Grid Fund. |  |  |  |
| Corporate – Other (Vehicles, Plant and Equipment, Site Security, Depots Buildings, HSE) (regional various) | 938 | 938 | qtr 4 2025‑26 |
| This project was previously reported as part of the Corporate – Other (Vehicles, Plant and Equipment, Site Security, Depots Buildings and HSE) program and is now reported separately as a completed project. |  |  |  |
| Corporate – Systems (Including IT) (SCADA, Digital Meters, IT Hardware, Total Asset Management) (regional various) | 161 | 161 | qtr 4 2025‑26 |
| This project was previously reported as part of the Corporate – Systems (including IT) (SCADA, Digital Meters, IT Hardware and Total Asset Management) program and is now reported separately as a completed project. |  |  |  |
| North Arm Crossing (Watermain Replacement) (Lakes Entrance) | 3 521 | 3 521 | qtr 2 2025‑26 |
| The TEI has increased by $3.521 million following tender award. |  |  |  |
| Sewer – Growth (Sewer Pump Stations, Rising Mains, Sewer Mains, Reticulation mains) (regional various) | 958 | 958 | qtr 4 2025‑26 |
| This project was previously reported as part of the Sewer – Growth (sewer pump stations, rising mains, sewer mains and reticulation mains) program and is now reported separately as a completed project. |  |  |  |
| Sewer – Regulatory Compliance (Sewer Treatment, Odour, Biosolids, Ground Water monitoring, Generators) (regional various) | 2 563 | 2 563 | qtr 4 2025‑26 |
| This project was previously reported as part of the Sewer – Regulatory Compliance (sewer treatment, odour, biosolids, groundwater monitoring and generators) program and is now reported separately as a completed project. |  |  |  |
| Sewer – Renewals (Sewer Pump Stations, Rising Mains, Irrigation Stations, Pressure Sewers, Sewer Treatment) (regional various) | 1 334 | 1 334 | qtr 4 2025‑26 |
| This project was previously reported as part of the Sewer – Renewals (sewer pump stations, rising mains, irrigation stations, pressure sewers and sewer treatment) program and is now reported separately as a completed project. |  |  |  |
| Water – Growth (Main Supply pipelines, Reticulation pipelines, Water Pump Stations) (regional various) | 1 023 | 1 023 | qtr 4 2025‑26 |
| This project was previously reported as part of the Water – Growth (main supply pipelines, reticulation pipelines and water pump stations) program and is now reported separately as a completed project. |  |  |  |
| Water – Regulatory Compliance (Water Treatment, Safety upgrades, Filter Access, UV Disinfection) (regional various) | 1 072 | 1 072 | qtr 4 2025‑26 |
| This project was previously reported as part of the Water – Regulatory Compliance (water treatment, safety upgrades, filter access and UV disinfection) program and is now reported separately as a completed project. |  |  |  |
| Water – Renewals (Pumps, Main Supply pipelines, Reticulation pipelines, Water Pump Stations, Switchboards) (regional various) | 1 987 | 1 987 | qtr 4 2025‑26 |
| This project was previously reported as part of the Water – Renewals (pumps, main supply pipelines, reticulation pipelines, water pump stations and switchboards) program and is now reported separately as a completed project. |  |  |  |

Source: East Gippsland Region Water Corporation

Note:

(a) 	East Gippsland Region Water Corporation structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised, and programs are prioritised to ensure projects are completed at the most appropriate time.

Gippsland and Southern Rural Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Enterprise resource planning (Maffra) | 4 090 | 999 | 2 224 | 867 | qtr 4 2027-28 |
| Glenmaggie southern needle valve refurbishment (Glenmaggie) | 2 387 | 1 541 | 846 | .. | qtr 1 2026-27 |
| Ladders and walkway compliance program (Gippsland and Western Victoria) | 3 831 | 1 290 | 1 097 | 1 444 | qtr 4 2027-28 |
| MID channel reconstruction program (Gippsland) | 4 359 | 672 | 855 | 2 832 | qtr 4 2027-28 |
| Southern main concrete flume joint repair (Gippsland) | 1 737 | 467 | 600 | 670 | qtr 4 2027-28 |
| All remaining projects with a TEI less than $1 million | 4 085 | 1 064 | 1 969 | 1 052 | various |
| Total new projects | 20 489 | 6 033 | 7 591 | 6 865 |  |

Source: Gippsland and Southern Rural Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Glenmaggie Gate Repainting (Glenmaggie Dam) | 2 722 | 1 384 | 1 338 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.946 million due to revised scope of work. |  |  |  |  |  |
| Maffra weir fishway (Maffra) | 10 845 | 841 | 10 004 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.241 million following confirmation of construction work engagement. |  |  |  |  |  |
| Meter replacement program – PS23 (Southern Victoria) | 6 440 | 3 942 | 2 498 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.611 million following confirmation of construction work engagement. |  |  |  |  |  |
| MID 2030: modernising the Macalister irrigation district phase 2 (Gippsland) | 62 934 | 61 840 | 1 094 | .. | qtr 2 2026-27 |
| The TEI has increased by $0.334 million due to a revised project scope. The estimated completion date has been revised to quarter 2 2026-27 due to the revised project scope. |  |  |  |  |  |
| MID Regulator Replacement Program PS23 (Maffra) | 7 726 | 2 287 | 2 467 | 2 972 | qtr 4 2027-28 |
| The TEI has increased by $0.694 million due to a revised project scope. |  |  |  |  |  |
| MID Tunnel No 5 Relining/Repairs (Glenmaggie) | 4 141 | 2 982 | 1 159 | .. | qtr 4 2027-28 |
| The TEI has increased by $0.329 million following confirmation of construction work engagement. |  |  |  |  |  |
| WID and BMID automation upgrade (Werribee and Bacchus Marsh) | 1 752 | 1 578 | 174 | .. | qtr 4 2026-27 |
| The project name has been changed from ‘BMID Automation upgrade’ when it was published in the 2025-26 Budget. The project location has changed from Bacchus Marsh to Werribee and Bacchus Marsh to better reflect the project’s service area. The TEI has decreased by $0.015 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2026-27 to reflect updated timelines following scope and budget adjustments. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 7 378 | 4 640 | 994 | 1 744 | various |
| Total existing projects | 103 938 | 79 494 | 19 728 | 4 716 |  |
| Total Gippsland and Southern Rural Water Corporation projects | 124 427 | 85 527 | 27 319 | 11 581 |  |

Source: Gippsland and Southern Rural Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Carbon reforestation project (Glenmaggie) | 941 | 889 | qtr 4 2025-26 |
| The TEI has decreased by $0.545 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2025-26 to reflect the updated scope and forecast schedule. |  |  |  |
| Werribee irrigation district flow meter upgrade (Werribee) | 1 186 | 1 184 | qtr 4 2025-26 |
| The TEI has decreased by $0.190 million following confirmation of construction work engagement. |  |  |  |

Source: Gippsland and Southern Rural Water Corporation

Goulburn Murray Rural Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Effluent Re-lift Station (Lake Eildon – Jerusalem Creek, Connection to Jerusalem Creek – Eildon Township sewer pipeline) | 1 783 | .. | .. | 1 783 | qtr 4 2030-31 |
| Plunge Pool and Cascades Rehabilitation (Laanecoorie) | 1 714 | .. | .. | 1 714 | qtr 4 2030-31 |
| Pump Station Electrical Cabinet Upgrade (Lake Hawthorn) | 1 050 | .. | .. | 1 050 | qtr 4 2029-30 |
| Total new projects | 4 547 | .. | .. | 4 547 |  |

Source: Goulburn Murray Rural Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Access tracks program (regional various) | 4 634 | 773 | 810 | 3 052 | various |
| The TEI has increased by $0.514 million due to additional works to be completed to maintain access to irrigation assets. |  |  |  |  |  |
| Batteries (regional various) | 5 147 | 1 040 | 779 | 3 329 | various |
| The TEI has increased by $2.701 million due to increased material component replacement costs. The estimated completion date has been revised to ‘various’ to reflect this program of work. |  |  |  |  |  |
| Dam Safety Upgrade Project – Spillway/embankment filters and embankment raise and strengthen spillway (Newlyn) | 13 270 | .. | .. | 13 270 | qtr 4 2030‑31 |
| The TEI has increased by $0.381 million due to revised project scope and costings. |  |  |  |  |  |
| Filter secondary embankment upgrade works (Tullaroop) | 6 220 | 100 | 332 | 5 788 | qtr 4 2029-30 |
| The TEI has increased by $0.533 million due to revised project scope and costings. The estimated completion date has been revised to quarter 4 2029-30 in line with a more accurate forecast for this project. |  |  |  |  |  |
| Goulburn Murray irrigation district communication network project (regional various) | 2 491 | 415 | 415 | 1 661 | various |
| The TEI has increased by $0.711 million due to an increase in costs for replacement of GMID Node Communication network. The estimated completion date has been revised to ‘various’ to reflect a program of work. |  |  |  |  |  |
| ICT enhancements projects (regional various) | 8 101 | 1 239 | 1 113 | 5 749 | various |
| The TEI has decreased by $0.730 million due to cost savings. |  |  |  |  |  |
| Linear program (regional various) | 51 614 | 8 509 | 7 987 | 35 119 | various |
| The TEI has increased by $14.281 million due to increased investment in the irrigation network to deliver water efficiently. |  |  |  |  |  |
| Meters program (regional various) | 18 957 | 2 421 | 3 163 | 13 373 | various |
| The TEI has increased by $1.150 million due to increased focus on metering assets. |  |  |  |  |  |
| Murray Darling Basin Telemetry Uplift Program (regional various) | 3 845 | 615 | 2 046 | 1 184 | qtr 4 2028-29 |
| The project name has changed from ‘Non‑Urban Watering Metering and Telemetry Project’ when it was published in the 2025-26 Budget. Non‑Urban Watering Metering will be completed in 2025-26 and is reported separately. The TEI has increased by $0.545 million due to revised project scope and costings. The estimated completion date has been revised to quarter 4 2028-29 in line with a more accurate forecast for this project. |  |  |  |  |  |
| Property and equipment replacement program (regional various) | 13 310 | 1 296 | 1 749 | 10 265 | various |
| The TEI has increased by $0.950 million due to increased replacements in the plant fleet, to continue the delivery of the capital program. |  |  |  |  |  |
| Pumps, Pump Stations and Reticulation Pipe Replacement (regional various) | 11 923 | .. | 1 115 | 10 808 | various |
| The project name has changed from ‘Reticulation pipe replacement (regional various)’ when it was published in the 2025-26 Budget, as it now includes more projects within this program of work. The TEI has increased by $8.779 million due to revised project scope and costings. |  |  |  |  |  |
| Regionalisation Strategy (West) | 1 475 | .. | 1 475 | .. | qtr 4 2026-27 |
| The project name has changed from ‘Regionalisation Strategy (Regional Various)’ when it was published in the 2025-26 Budget, as the project now is just inclusive of the West. The TEI has decreased by $1.306 million due to revised project scope and costings. The estimated completion date has been revised to quarter 4 2026-27, in line with a more accurate forecast for this project. |  |  |  |  |  |
| Spillway and outlet works upgrade (Laanecoorie) | 4 912 | 300 | 623 | 3 989 | qtr 4 2028-29 |
| The TEI has increased by $1.116 million due to revised project scope and costings. The estimated completion date has been revised to quarter 4 2028-29 in line with a more accurate forecast for this project. |  |  |  |  |  |
| Spillway gates upgrade (Nagambie) | 1 357 | .. | 26 | 1 332 | qtr 4 2030-31 |
| The TEI has decreased by $0.137 million due revised costings. The estimated completion date has been revised to quarter 4 2030-31 in line with a more accurate forecast for this project. |  |  |  |  |  |
| Spillway wall stabilisation works (Nillahcootie) | 4 577 | .. | 208 | 4 369 | qtr 4 2030‑31 |
| The TEI has decreased by $0.125 million due revised costings. |  |  |  |  |  |
| Structure program (regional various) | 42 320 | 4 820 | 4 499 | 33 001 | various |
| The TEI has increased by $15.068 million due to additional programs of work. The flumegate projects are now included in this program. |  |  |  |  |  |
| Tower superstructure upgrade (Eildon) | 12 911 | .. | .. | 12 911 | qtr 4 2029‑30 |
| The TEI has increased by $0.654 million due to revised project scope and costings. |  |  |  |  |  |
| Total existing projects | 207 064 | 21 528 | 26 340 | 159 200 |  |
| Total Goulburn Murray Rural Water Corporation projects | 211 611 | 21 528 | 26 340 | 163 747 |  |

Source: Goulburn Murray Rural Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Intake Tower – Bridge – Protective Coating Replacement (Eppalock) | .. | .. | .. |
| This project has been removed from the capital works program. |  |  |  |
| Irrigation outlet valve refurbishment and trash screens replacement (Myrtleford) | 1 312 | 1 312 | qtr 4 2025‑26 |
| The TEI has decreased by $0.053 million due to change in scope of works. |  |  |  |
| Outlet Butterfly Valve – Relocate electrical cabinet and hydraulic power unit to higher level (Eppalock) | 682 | 682 | qtr 4 2025-26 |
| The TEI has decreased by $1.064 million due to change in scope of works. |  |  |  |

Source: Goulburn Murray Rural Water Corporation

Goulburn Valley Region Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Water treatment plant dissolved air filtration and floatation (Shepparton) | 5 300 | .. | .. | 5 300 | qtr 4 2027-28 |
| All remaining projects with a TEI less than $1 million | 281 | 36 | 35 | 210 | various |
| Total new projects | 5 581 | 36 | 35 | 5 510 |  |

Source: Goulburn Valley Region Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| 441 Allan Street sewer augmentation – stage 1 and 2 (Kyabram) | 3 050 | 1 995 | 932 | 123 | qtr 4 2026-27 |
| The project and the TEI have been combined with 441 Allan Street sewer augmentation – stage 1 (Kyabram). The estimated completion date has been revised to quarter 4 2026-27 in line with the stage 1 works. |  |  |  |  |  |
| Above ground asset replacement (regional various) | 10 669 | 475 | 480 | 9 714 | ongoing |
| Additional 200 megalitre raw water storage (Mansfield) | 9 390 | 181 | .. | 9 209 | qtr 4 2031-32 |
| Almond farm irrigation upgrade (Shepparton) | 1 820 | .. | .. | 1 820 | qtr 4 2029-30 |
| Asset acquisition (regional various) | 58 764 | 3 467 | 2 650 | 52 647 | ongoing |
| The TEI has increased by $0.572 million to reflect revised funding requirements. This program of works includes Asset acquisitions – corporate assets (regional various), Asset acquisitions – digital assets (regional various), Asset acquisitions‑farming assets (regional various), Asset acquisitions – vehicles (regional various) and Occupational health and safety initiatives (regional various) as these projects are similar in nature. |  |  |  |  |  |
| Asset management information system replacement phase 2 (regional various) | 1 300 | 476 | 440 | 384 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Broadford to Kilmore pipeline (Broadford) | 27 360 | 355 | 410 | 26 595 | qtr 4 2030-31 |
| Clear water storage augmentation (Alexandra) | 1 425 | .. | .. | 1 425 | qtr 4 2030-31 |
| Core business automation – supervisory control and data acquisition infrastructure replacement (regional various) | 9 720 | 1 342 | 2 153 | 6 225 | qtr 4 2030-31 |
| Corporate office upgrades (Shepparton) | 8 472 | 1 895 | .. | 6 577 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29, in line with a revised project schedule. |  |  |  |  |  |
| Councils – water and sewer (regional various) | 17 187 | 546 | 790 | 15 851 | ongoing |
| Delatite River to Ritchie’s Reservoir transfer main (Mansfield) | 9 090 | .. | .. | 9 090 | qtr 4 2033-34 |
| Diameter nominal 375 direct feed water main to south tank (Shepparton) | 4 540 | .. | .. | 4 540 | qtr 4 2034-35 |
| Diameter nominal 375 water main south of Raftery Road (Shepparton) | 1 670 | 93 | .. | 1 577 | qtr 4 2032-33 |
| Diameter nominal 450 trunk water main south of Kialla Lakes Drive (Shepparton) | 1 250 | 172 | .. | 1 078 | qtr 4 2031-32 |
| Drought response (Kilmore) | 3 461 | 179 | 2 181 | 1 101 | qtr 4 2027-28 |
| The TEI has increased by $1.739 million due to scope refinement and revised costings. The estimated completion date has been revised to quarter 4 2027-28, in line with uncertainty over weather conditions. |  |  |  |  |  |
| Dry well to wet well conversion (regional various) | 1 100 | .. | .. | 1 100 | qtr 4 2030-31 |
| Externally funded works – sewer (regional various) | 111 621 | 4 530 | 4 650 | 102 441 | ongoing |
| The TEI has increased by $4.530 million due to the project work schedule for ongoing development. |  |  |  |  |  |
| Externally funded works – water (regional various) | 97 486 | 4 543 | 4 150 | 88 793 | ongoing |
| The TEI has increased by $4.543 million due to the project work schedule for ongoing development. |  |  |  |  |  |
| Gooram pipeline replacement (Euroa) | 5 791 | 14 | .. | 5 778 | qtr 4 2035-36 |
| Ground level and elevated tank replacement – stage 2 (Waterford Park) | 1 354 | 175 | 1 000 | 179 | qtr 4 2028-29 |
| Health based target program (regional various) | 28 500 | 4 456 | 10 000 | 14 044 | qtr 4 2031-32 |
| The estimated completion date has been revised to quarter 4 2031-32, in line with a revised project schedule. |  |  |  |  |  |
| Intelligent metering to all of Goulburn Valley Water (regional various) | 21 940 | .. | .. | 21 940 | qtr 4 2034-35 |
| The estimated completion date has been revised to quarter 4 2034-35, in line with a revised project schedule. |  |  |  |  |  |
| Internal pipework upgrade (Mooroopna) | 1 820 | .. | .. | 1 820 | qtr 4 2033-34 |
| Kilmore south trunk sewer (Kilmore) | 8 900 | 3 589 | 3 500 | 1 811 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28, in line with a revised project schedule. |  |  |  |  |  |
| Lemnos pump station upgrade (Shepparton) | 2 320 | 865 | 212 | 1 243 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29, in line with a revised project schedule. |  |  |  |  |  |
| Linking of tanks program (regional various) | 1 725 | 184 | 500 | 1 041 | qtr 4 2028-29 |
| McLennan Street pump station upgrade (Mooroopna) | 1 750 | .. | .. | 1 750 | qtr 4 2034-35 |
| The estimated completion date has been revised to quarter 4 2034-35, in line with a revised project schedule. |  |  |  |  |  |
| McLennan Street water main augmentation (Mooroopna) | 1 690 | .. | .. | 1 690 | qtr 4 2035-36 |
| The estimated completion date has been revised to quarter 4 2035-36, in line with a revised project schedule. |  |  |  |  |  |
| Microbial risk reduction (regional various) | 14 000 | 1 384 | 4 000 | 8 616 | qtr 4 2029-30 |
| The estimated completion date has been revised to quarter 4 2029-30, in line with a revised project schedule. |  |  |  |  |  |
| Minor infrastructure items (regional various) | 6 462 | 450 | 400 | 5 612 | ongoing |
| Modernising irrigation (regional various) | 1 718 | 745 | 200 | 773 | qtr 4 2028-29 |
| Mooroopna west growth corridor distribution main – stage 7 (Mooroopna) | 1 600 | .. | .. | 1 600 | qtr 4 2031-32 |
| Non-revenue bulk flow meters upgrade and replacement (regional various) | 4 791 | 353 | 266 | 4 172 | ongoing |
| Numurkah water treatment plant to Katunga pipeline (Katunga) | 5 700 | 2 389 | 40 | 3 271 | qtr 4 2027-28 |
| Old Dookie Road water main (Shepparton) | 1 512 | .. | .. | 1 512 | qtr 4 2031-32 |
| Operations centre clear water storage augmentation (Shepparton) | 22 400 | 14 513 | 1 104 | 6 783 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28, in line with the defects liability period. |  |  |  |  |  |
| Programmable logic control code standardisation (regional various) | 1 131 | 352 | 100 | 679 | qtr 4 2032-33 |
| Programmable logic control replacement program (regional various) | 2 376 | 890 | 200 | 1 286 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29, in line with a revised project schedule. |  |  |  |  |  |
| Raw water pipeline upgrade Ritchies to Mansfield No. 3 (Mansfield) | 21 000 | 3 463 | 7 816 | 9 721 | qtr 4 2028-29 |
| The TEI has increased $9.550 million due to a revised scope following detail design. The estimated completion date has been revised to quarter 4 2028-29, in line with a revised project schedule. |  |  |  |  |  |
| Raw water pump station augmentation (Shepparton) | 3 990 | 1 331 | 595 | 2 064 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29, in line with additional design work. |  |  |  |  |  |
| Raw water pump station upgrade (Rushworth) | 1 320 | .. | .. | 1 320 | qtr 4 2032-33 |
| Sewage pump station No. 21, 23 and 32 upgrades (Shepparton) | 1 900 | .. | .. | 1 900 | qtr 4 2030-31 |
| Sewer network augmentation (Alexandra) | 1 270 | .. | .. | 1 270 | qtr 4 2032-33 |
| Sewer network master plan projects – stage 2 (Mansfield) | 1 310 | .. | .. | 1 310 | qtr 4 2030-31 |
| Sewer network projects – stage 1 (Nagambie) | 2 595 | 115 | 185 | 2 295 | qtr 4 2028-29 |
| Sewer network projects – stage 2 (Nagambie) | 2 870 | 51 | 99 | 2 720 | qtr 4 2029-30 |
| Sewer odour program (regional various) | 1 053 | 27 | 50 | 976 | ongoing |
| Sewer pump station modernisation (regional various) | 1 670 | .. | .. | 1 670 | qtr 4 2036-37 |
| Sewer pump station No. 1 pump station and inlet work upgrades (Seymour) | 1 850 | 21 | 50 | 1 779 | qtr 4 2029-30 |
| Sewer pump station No. 2 dry well to wet well conversion (Shepparton) | 1 100 | 122 | 25 | 953 | qtr 4 2028-29 |
| Sewer pump station No. 4 pump station and rising main upgrade stage 2 (Nagambie) | 4 980 | 62 | 50 | 4 868 | qtr 4 2029-30 |
| Sewer pump station No. 54 pump station and rising main upgrade (Shepparton) | 1 760 | 1 585 | 175 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27, in line with the defects liability period. |  |  |  |  |  |
| Sewer pump station No. 56 rising main stage 3 (Shepparton) | 4 590 | 845 | 3 744 | 1 | qtr 4 2027-28 |
| Sewer pump station No. 7 dry well to wet well conversion (Shepparton) | 1 050 | 117 | .. | 933 | qtr 4 2028-29 |
| Sewer relining program (regional various) | 46 626 | 4 739 | 500 | 41 387 | ongoing |
| Sewer rising main No. 1 replacement stage 2 (Euroa) | 4 392 | 92 | 2 140 | 2 160 | qtr 4 2028-29 |
| The TEI has increased by $2.232 million due to scope maturity following detail design. |  |  |  |  |  |
| Shepparton operation centre 14 mega litre tank floor replacement (Shepparton) | 1 980 | .. | .. | 1 980 | qtr 4 2034-35 |
| The project name has changed from ‘Shepparton operation centre 14ML tank floor replacement (Shepparton)’ when it was published in the 2025-26 Budget. |  |  |  |  |  |
| Shepparton South dedicated pump station (Shepparton) | 1 890 | .. | .. | 1 890 | qtr 4 2032-33 |
| Shepparton South tank pump station upgrade (Shepparton) | 2 430 | .. | .. | 2 430 | qtr 4 2033-34 |
| Shepparton waste management facility reuse supply to Ascot Park (Shepparton) | 16 800 | .. | .. | 16 800 | qtr 4 2036-37 |
| Shepparton water treatment plant dosing pipe provision for asset inspection (Shepparton) | 1 186 | .. | .. | 1 186 | qtr 4 2032-33 |
| Sludge management (Euroa) | 1 180 | 693 | 487 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27, in line with a revised project schedule. |  |  |  |  |  |
| Standpipe upgrade program – stage 2 (regional various) | 2 650 | 1 568 | 60 | 1 022 | qtr 4 2028-29 |
| Supply main replacement – stage 2 (Dookie) | 1 190 | .. | .. | 1 190 | qtr 4 2033-34 |
| Switchboard replacements (regional various) | 9 093 | 411 | 370 | 8 312 | ongoing |
| Tank asset life extension (Eildon) | 2 100 | .. | .. | 2 100 | qtr 4 2029-30 |
| Tanks and tower rehabilitation program (regional various) | 2 600 | .. | .. | 2 600 | qtr 4 2034-35 |
| The estimated completion date has been revised to quarter 4 2034-35, in line with a revised project schedule. |  |  |  |  |  |
| Tower decommissioning (Merrigum) | 1 455 | 50 | 350 | 1 055 | qtr 4 2026-27 |
| Waste management facility additional winter storage (Kilmore) | 5 320 | .. | .. | 5 320 | qtr 4 2034-35 |
| Waste management facility additional winter storage and irrigation area (Tongala) | 1 830 | .. | .. | 1 830 | qtr 4 2036-37 |
| Waste management facility farm irrigation and re-vegetation (Broadford) | 1 660 | 27 | .. | 1 633 | qtr 4 2032-33 |
| Waste management facility high rate anaerobic lagoon replacement (Mooroopna) | 1 840 | .. | .. | 1 840 | qtr 4 2031-32 |
| Waste management facility irrigation capacity upgrade (Broadford) | 2 190 | .. | .. | 2 190 | qtr 4 2032-33 |
| Waste management facility irrigation capacity upgrade (Nagambie) | 3 313 | 392 | 1 921 | 1 000 | qtr 4 2033-34 |
| Waste management facility irrigation capacity upgrade (Yea) | 5 430 | .. | .. | 5 430 | qtr 4 2033-34 |
| Waste management facility irrigation pipeline (Mansfield) | 1 900 | 280 | 720 | 900 | qtr 4 2026-27 |
| Waste management facility lagoon 6 refurbishment (Alexandra) | 1 680 | .. | .. | 1 680 | qtr 4 2034-35 |
| The estimated completion date has been revised to quarter 4 2034-35, in line with a revised project schedule. |  |  |  |  |  |
| Waste management facility performance improvement (Kilmore) | 1 261 | 844 | 417 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27, in line with a revised project schedule. |  |  |  |  |  |
| Waste management facility secondary treatment plant upgrade (Eildon) | 1 100 | .. | .. | 1 100 | qtr 4 2032-33 |
| Waste management facility sludge handling upgrade (Eildon) | 2 140 | .. | .. | 2 140 | qtr 4 2033-34 |
| Waste management facility winter storage capacity upgrade (Shepparton) | 11 490 | .. | .. | 11 490 | qtr 4 2031-32 |
| Water mains replacement (regional various) | 83 974 | 2 232 | 2 341 | 79 401 | ongoing |
| Water meters replacement (regional various) | 8 537 | 550 | 480 | 7 507 | ongoing |
| Water meters stock (regional various) | 4 289 | 496 | 190 | 3 603 | ongoing |
| Water network augmentation – stage 2 (Alexandra) | 2 171 | 3 | .. | 2 168 | qtr 4 2030-31 |
| Water network augmentation – stage 2 (Mansfield) | 1 030 | .. | .. | 1 030 | qtr 4 2032-33 |
| Water network master plan projects (Yea) | 8 232 | 830 | 2 850 | 4 552 | qtr 4 2027-28 |
| Water pressure improvement (regional various) | 3 500 | 187 | 1 100 | 2 213 | qtr 4 2029-30 |
| Water supply pipeline (Nathalia) | 26 510 | 11 595 | 8 961 | 5 954 | qtr 4 2027-28 |
| Water treatment plant augmentation stage 3 (Cobram) | 2 206 | 36 | .. | 2 170 | qtr 4 2033-34 |
| The TEI has decreased by $1.364 million due to a revised project scope. |  |  |  |  |  |
| Water treatment plant flood barrier (Shepparton) | 4 020 | 485 | 617 | 2 918 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29, in line with a revised project schedule. |  |  |  |  |  |
| Water treatment plant improvement works (Shepparton) | 1 170 | .. | .. | 1 170 | qtr 4 2034-35 |
| Water treatment plant new clear water storage (Mansfield) | 4 300 | .. | .. | 4 300 | qtr 4 2033-34 |
| Water treatment plant optimisation (regional various) | 13 373 | 909 | 600 | 11 864 | ongoing |
| Water treatment plant upgrade (Broadford) | 24 353 | 1 481 | 3 345 | 19 527 | qtr 4 2029-30 |
| Water treatment plant upgrade (Mansfield) | 15 400 | 445 | 565 | 14 390 | qtr 4 2029-30 |
| Yarra Valley Water – water supply connection (Kilmore) | 1 262 | 295 | 100 | 867 | qtr 4 2029-30 |
| Yea water treatment plant future proofing (Yea) | 5 400 | 13 | .. | 5 387 | qtr 4 2040-41 |
| All remaining projects with a TEI less than $1 million | 35 798 | 5 849 | 4 718 | 25 231 | various |
| The TEI has increased by $0.046 million based on revised project scope for a number of projects. |  |  |  |  |  |
| Total existing projects | 953 414 | 92 849 | 85 979 | 774 587 |  |
| Total Goulburn Valley Region Water Corporation projects | 958 995 | 92 885 | 86 014 | 780 097 |  |

Source: Goulburn Valley Region Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Abbinga Reservoir relining works (Euroa) | 6 400 | 6 400 | qtr 4 2025-26 |
| The TEI has decreased by $0.800 million based on project completion figures. |  |  |  |
| Actiflo ferric sulphate tank replacement and system upgrade (Shepparton) | 1 200 | 1 200 | qtr 4 2025-26 |
| The TEI has increased by $0.081 million based on project completion figures. |  |  |  |
| Clear water storage replacement (Nathalia) | 2 205 | 2 205 | qtr 4 2025-26 |
| The TEI has decreased by $0.145 million based on project completion figures. The estimated completion date has been revised to quarter 4 2025-26 in line with a revised project schedule. |  |  |  |
| Kilmore recycled water scheme – water network (Kilmore) | 2 553 | 2 553 | qtr 4 2025-26 |
| Network automation uplift (regional various) | .. | .. | .. |
| This project has been removed from the Capital works portfolio as it was a duplicate of ’Core business automation – supervisory control and data acquisition infrastructure replacement (regional various)’ project. |  |  |  |
| Scope 2 emissions reductions (regional various) | .. | .. | .. |
| This project has been removed from the capital works program. |  |  |  |
| Waste management facility tertiary treatment plant Actiflo filter replacement (Shepparton) | 1 035 | 1 035 | qtr 4 2025-26 |
| The Project was initiated after the submission of 2025-26 Budget due to urgent emergent works. |  |  |  |
| Waste management facility tree harvesting (Shepparton) | 1 085 | 1 085 | qtr 4 2025-26 |
| The TEI has been reduced by $0.015 million based on project completion figures. |  |  |  |
| Waste management facility winter storage and irrigation augmentation (Mansfield) | 8 413 | 8 413 | qtr 4 2025-26 |
| The TEI has been reduced by $0.152 million based on project completion figures. |  |  |  |
| All remaining projects with a TEI less than $1 million | 9 046 | 9 046 | various |

Source: Goulburn Valley Region Water Corporation

Grampians Wimmera Mallee Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Mininera rural pipeline project (East Grampians) | 30 187 | 16 468 | 13 719 | .. | qtr 4 2026-27 |
| Total new projects | 30 187 | 16 468 | 13 719 | .. |  |

Source: Grampians Wimmera Mallee Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Dam safety works (regional various) | 1 692 | 358 | 676 | 658 | qtr 4 2027-28 |
| The TEI has decreased by $0.064 million due to revised cost estimates. |  |  |  |  |  |
| Headworks structure renewals (regional various) | 11 610 | 2 080 | 4 626 | 4 905 | qtr 4 2027-28 |
| The TEI has increased by $0.019 million due to revised cost estimates. |  |  |  |  |  |
| Meter replacements (regional various) | 8 421 | 5 717 | 2 513 | 190 | qtr 4 2027-28 |
| The TEI has increased by $3.308 million. Urban and bulk water meter replacement programs moved from All remaining projects with a TEI less than $1 million. |  |  |  |  |  |
| Office and depot renewals (regional various) | 6 354 | 909 | 2 340 | 3 105 | qtr 4 2027-28 |
| The TEI has increased by $3.149 million due to a revised project schedule. The estimated completion date has been revised to quarter 4 2027-28 in line with Horsham depot relocation project planning and approvals timing. |  |  |  |  |  |
| Renewable energy projects (regional various) | 21 217 | 18 411 | 1 506 | 1 300 | qtr 4 2027-28 |
| The TEI has decreased by $2.171 million due to a reduced program. |  |  |  |  |  |
| Service line connections (regional various) | 1 370 | 887 | 233 | 249 | qtr 4 2027-28 |
| The TEI has increased by $0.200 million due to revised cost estimates. Previously disclosed under ‘All remaining projects with a TEI less than $1 million’. |  |  |  |  |  |
| Sewer mains – replacement and other works (regional various) | 17 341 | 10 467 | 4 321 | 2 554 | qtr 4 2027-28 |
| The TEI has increased by $1.576 million due to revised cost estimates and project scope. |  |  |  |  |  |
| Vehicle renewals (regional various) | 12 005 | 7 606 | 2 882 | 1 517 | qtr 4 2027-28 |
| The TEI has increased by $3.556 million due to the inclusion of plant and equipment. |  |  |  |  |  |
| Wastewater treatment plant upgrades (regional various) | 17 271 | 4 232 | 7 791 | 5 247 | qtr 4 2027-28 |
| The TEI has decreased by $1.786 million due to reprioritisation of planned upgrades and renewals. |  |  |  |  |  |
| Water mains – replacement and other works (regional various) | 21 854 | 11 107 | 5 227 | 5 521 | qtr 4 2027-28 |
| The TEI has decreased by $7.055 million due to reprioritisation of planned renewals and the Water storage tank renewals project being moved to Water Storage renewals (regional various). |  |  |  |  |  |
| Water quality upgrade (regional various) | 12 189 | 9 888 | 2 300 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.301 million due to a revised project schedule. The estimated completion date has been revised to quarter 4 2026-27 to allow time to procure easements. |  |  |  |  |  |
| Water storage renewals (regional various) | 5 228 | 3 836 | 617 | 774 | qtr 4 2027-28 |
| The TEI has increased by $4.122 million. Water storage tank renewals moved from Water mains – replacement and other works. |  |  |  |  |  |
| Water supply security augmentation (regional various) | 1 397 | 633 | 395 | 369 | qtr 4 2027-28 |
| The TEI has increased by $0.366 million in alignment with increased scope and funding of $0.300 million from the State Government. |  |  |  |  |  |
| Water supply system upgrade – industrial fire flow (regional various) | 5 204 | 546 | 2 200 | 2 458 | qtr 4 2027-28 |
| The TEI has decreased by $1.977 million in line with a revised project schedule. |  |  |  |  |  |
| Water treatment plant major infrastructure (regional various) | 18 230 | 8 408 | 8 107 | 1 715 | qtr 4 2027-28 |
| The TEI has increased by $2.626 million due to a revised project scope. |  |  |  |  |  |
| Water treatment plant upgrades – health based treatment targets (regional various) | 20 008 | 3 850 | 7 928 | 8 231 | qtr 4 2028-29 |
| The TEI has increased by $3.121 million and been revised to quarter 4 2028-29 due to inclusion of works planned for completion in 2028-29 (not previously included in the TEI). |  |  |  |  |  |
| Water treatment plant upgrades and modernisation (regional various) | 1 326 | 323 | 500 | 503 | qtr 4 2027-28 |
| The TEI has decreased by $0.182 million due to reduced scope. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 11 179 | 7 334 | 2 469 | 1 376 | qtr 4 2027-28 |
| The TEI has decreased by $6.356 million due to the recategorisation of several projects. Service line connections (regional various) $1.370 million, moved to its own category. Plant and equipment $3.837 million moved to Vehicle renewals (regional various). Urban and bulk water meter replacement programs moved to Water meter replacement (regional various) $1.801 million. Domestic and stock mains $0.915 million previously reported separately. Pipeline energy optimisation project completed $0.186 million. |  |  |  |  |  |
| Total existing projects | 193 896 | 96 592 | 56 631 | 40 672 |  |
| Total Grampians Wimmera Mallee Water Corporation projects | 224 083 | 113 060 | 70 350 | 40 672 |  |

Source: Grampians Wimmera Mallee Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| East Grampians rural water supply (East Grampians) | 87 400 | 87 400 | qtr 4 2025-26 |
| The TEI has decreased by $7.100 million, reflecting the separate categorisation of the Mininera water supply project. This project is funded by the Commonwealth, State Government, Grampians Wimmera Mallee Water Corporation and customer contributions. |  |  |  |
| All remaining projects with a TEI less than $1 million | 205 | 205 | qtr 4 2025-26 |
| The TEI for Reuse upgrades has decreased $2.011 million due to a revision of priorities. This project is now complete. |  |  |  |

Source: Grampians Wimmera Mallee Water Corporation

Greater Western Water Corporation

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Melton Recycled Water Plant – major mechanical upgrade works (Melton) | 94 256 | 6 775 | 36 225 | 51 256 | qtr 4 2027-28 |
| Total new projects | 94 256 | 6 775 | 36 225 | 51 256 |  |

Source: Greater Western Water Corporation

Note:

(a) 	Greater Western Water Corporation has consolidated several smaller projects into annual programs or larger projects with ongoing completion dates.

Existing projects (a)(b)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Alternative water – compliance (metropolitan and regional various) | 43 489 | .. | 2 662 | 40 827 | ongoing |
| The TEI has increased by $15.961 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Alternative water – growth (metropolitan and regional various) | 151 377 | .. | 6 981 | 144 396 | ongoing |
| The TEI has decreased by $30.327 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Alternative water – renewal (metropolitan and regional various) | 41 530 | .. | 2 504 | 39 025 | ongoing |
| The TEI has increased by $24.716 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| CBD Stage 4 – Siddeley St (Melbourne) | 93 062 | 31 265 | 36 225 | 25 573 | qtr 4 2026‑27 |
| The TEI has increased by $1.834 million due to variations in contract costs. |  |  |  |  |  |
| Corporate – buildings (metropolitan and regional various) | 28 593 | .. | 3 846 | 24 747 | ongoing |
| The TEI has increased by $10.558 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Corporate – information technology (metropolitan and regional various) | 166 187 | .. | 9 673 | 156 514 | ongoing |
| The TEI has decreased by $36.891 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Corporate – intangibles (metropolitan and regional various) | 84 441 | .. | 9 029 | 75 411 | ongoing |
| The TEI has increased by $28.505 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Corporate – minor plant and equipment (metropolitan and regional various) | 39 203 | .. | 6 974 | 32 228 | ongoing |
| The TEI has increased by $11.867 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Holden Tank Water Pumping Station and transfer main (Sunbury) | 144 360 | 5 713 | 3 535 | 135 112 | qtr 4 2028‑29 |
| The TEI has increased by $2.417 million due to variations in contract costs. |  |  |  |  |  |
| Parwan Balliang irrigation district storage (Parwan) | 25 909 | 17 879 | 6 430 | 1 600 | qtr 4 2027-28 |
| The TEI has increased by $6.912 million due to a revised estimate of commercial settlement costs. The estimated completion date has been revised to quarter 4 2027‑28 in line with a revised project schedule. |  |  |  |  |  |
| Sewer – compliance (metropolitan and regional various) | 165 648 | .. | 4 043 | 161 605 | ongoing |
| The TEI has increased by $112.072 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Sewer – growth (metropolitan and regional various) | 1 704 651 | .. | 88 466 | 1 616 185 | Ongoing |
| The TEI has increased by $548.387 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Sewer – renewal (metropolitan and regional various) | 393 142 | .. | 26 822 | 366 320 | ongoing |
| The TEI has increased by $91.887 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Water – backlog (metropolitan and regional various) | 2 961 | .. | 278 | 2 683 | ongoing |
| The TEI has increased by $0.675 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Water – compliance (metropolitan and regional various) | 52 126 | .. | 4 679 | 47 447 | ongoing |
| The TEI has increased by $11.617 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Water – growth (metropolitan and regional various) | 1 733 164 | .. | 82 079 | 1 651 085 | ongoing |
| The TEI has increased by $914.992 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Water – renewal (metropolitan and regional various) | 1 284 957 | .. | 77 729 | 1 207 228 | ongoing |
| The TEI has increased by $443.586 million as rolling programs of works are reviewed annually and are updated to take into account future requirements based on the information available, improved technology and any cost changes to deliver those assets. |  |  |  |  |  |
| Woodend Recycled Water Plant – mechanical dewatering (Woodend) | 11 391 | 7 285 | 4 053 | 53 | qtr 1 2027‑28 |
| The TEI has decreased by $0.681 million due to variations in contract costs. |  |  |  |  |  |
| Total existing projects | 6 166 191 | 62 142 | 376 008 | 5 728 039 |  |
| Total Greater Western Water projects | 6 260 447 | 68 917 | 412 233 | 5 779 295 |  |

Source: Greater Western Water Corporation

Notes:

(a)	Greater Western Water Corporation has consolidated several smaller projects into annual programs or larger projects with ongoing completion dates.

(b)	Greater Western Water Corporation has extended the time horizon on a number of projects, resulting in increases to TEI due to inclusion of new works under the rolling program.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Alternative water – compliance 2026 (metropolitan and regional various) | 3 254 | 3 254 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Alternative water – growth 2026 (metropolitan and regional various) | 14 324 | 14 324 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Alternative water – renewal 2026 (metropolitan and regional various) | 1 551 | 1 551 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Bald Hills tank construction (Bald Hills) | 31 525 | 31 525 | qtr 4 2025-26 |
| The TEI has decreased by $1.407 million due to the requirement for contingency being reduced as the project nears completion. The estimated completion date has been revised to quarter 2 2025‑26 to align with a revised project schedule. |  |  |  |
| Corporate – buildings 2026 (metropolitan and regional various) | 4 032 | 4 032 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Corporate – information technology 2026 (metropolitan and regional various) | 5 023 | 5 023 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Corporate – intangibles 2026 (metropolitan and regional various) | 7 653 | 7 653 | qtr 4 2025-26 |
| Project was originally captured under the Corporate – information technology rolling program of works. |  |  |  |
| Corporate – minor plant and equipment 2026 (metropolitan and regional various) | 2 423 | 2 423 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Gisborne recycled water plant Upgrade (Gisborne) | 61 846 | 61 846 | qtr 3 2025-26 |
| Melton recycled water plant primary sedimentation tank 1 and 2 renewal (Melton) | 7 692 | 7 692 | qtr 4 2025-26 |
| Romsey water filtration plant upgrade (Romsey) | 28 456 | 28 456 | qtr 4 2025-26 |
| Sewer – compliance 2026 (metropolitan and regional various) | 5 585 | 5 585 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Sewer – growth 2026 (metropolitan and regional various) | 72 272 | 72 272 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Sewer – renewal 2026 (metropolitan and regional various) | 23 763 | 23 763 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Water – compliance 2026 (metropolitan and regional various) | 4 482 | 4 482 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Water – growth 2026 (metropolitan and regional various) | 76 581 | 76 581 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |
| Water – renewal 2026 (metropolitan and regional various) | 62 458 | 62 458 | qtr 4 2025-26 |
| Project was originally captured under the rolling program of works. |  |  |  |

Source: Greater Western Water Corporation

Note:

(a) 	Greater Western Water Corporation has consolidated several smaller projects into annual programs or larger projects with ongoing completion dates.

Homes Victoria

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Bushfire recovery – additional recovery support for January 2026 bushfires (regional) | 17 600 | 5 600 | 12 000 | .. | qtr 4 2026-27 |
| Total new projects | 17 600 | 5 600 | 12 000 | .. |  |

Source: Homes Victoria

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Aboriginal Family Violence Refuge for Wimmera South West Area (Horsham) | 9 030 | 1 776 | 5 011 | 2 243 | qtr 1 2027-28 |
| Big Housing Build (statewide) | 2 227 271 | 1 820 564 | 387 812 | 18 895 | qtr 4 2027-28 |
| The TEI has decreased by $20.000 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with the accounting standards. |  |  |  |  |  |
| Cooling our public housing towers (metropolitan) | 101 172 | 29 407 | 71 765 | .. | qtr 4 2026-27 |
| This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Family Violence – refuge redevelopment (statewide) | 68 883 | 64 244 | 4 639 | .. | qtr 3 2026-27 |
| The estimated completion date has been revised to quarter 3 2026-27 in line with a revised project schedule. |  |  |  |  |  |
| Flemington estate redevelopment (Flemington) | 30 000 | 24 737 | 5 263 | .. | qtr 2 2026-27 |
| High-rise Redevelopment Program (metropolitan) | 1 200 695 | 277 172 | 317 961 | 605 561 | various |
| The TEI has increased by $344.011 million, comprising an increase of $329.718 million for the expanded scope of works for the redevelopment of seven towers across six sites in Albert Park, Flemington, Kensington, North Melbourne, Prahran and St Kilda, and a further increase of $20.986 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards, partially offset by $6.692 million reprioritised to the Public Housing Renewal Program initiative. |  |  |  |  |  |
| Homes Victoria Ground Lease Model Project 1 (metropolitan) | 517 422 | 511 160 | 6 262 | .. | qtr 2 2026-27 |
| Homes Victoria Ground Lease Model Project 2 (metropolitan) | 686 644 | 603 362 | 83 282 | .. | qtr 2 2026-27 |
| Housing Support Program – Priority Works (statewide) | 85 949 | 52 085 | 33 864 | .. | qtr 4 2026-27 |
| The TEI has decreased by $15.149 million due to $17.415 million being reclassified as operating instead of capital expenditure, in line with accounting standards, partially offset by $2.266 million of additional funding for an expanded scope of works. |  |  |  |  |  |
| Investing in a thriving North Richmond (Richmond) | 5 500 | 4 800 | 700 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with increased scope to include security enhancements. |  |  |  |  |  |
| Public Housing Renewal Program (statewide) | 293 095 | 257 467 | 35 628 | .. | qtr 1 2027-28 |
| The TEI has increased by $6.692 million due to funding being reprioritised from the High-rise Redevelopment Program initiative to facilitate modifications at Stokes Penola, North Melbourne and Northcote to support relocations. The estimated completion date has been revised to quarter 1 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Refuge and crisis accommodation (statewide) | 33 655 | 12 200 | 10 503 | 10 952 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Regional Housing Fund (regional) | 748 301 | 251 884 | 417 353 | 79 064 | qtr 4 2027-28 |
| Social Housing Accelerator Program (statewide) | 480 008 | 267 264 | 169 536 | 43 207 | qtr 4 2027-28 |
| Total existing projects | 6 487 625 | 4 178 124 | 1 549 580 | 759 923 |  |
| Total Homes Victoria projects | 6 505 225 | 4 183 724 | 1 561 580 | 759 923 |  |

Source: Homes Victoria

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| High-rise fire upgrade program (statewide) | 22 091 | 22 091 | qtr 4 2025-26 |

Source: Homes Victoria

Lower Murray Urban Rural Water Corporation

New projects (a)(b)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Sewer – treatment (regional various) | 84 900 | .. | .. | 84 900 | various |
| Sewer – pipelines (regional various) | 9 300 | .. | .. | 9 300 | various |
| Victorian Murray Floodplain Restoration Project Stage 2 (regional various) | 87 865 | 73 885 | 13 980 | .. | qtr 2 2026-27 |
| The TEI is funded by $87.865 million of Commonwealth Government funding (Federation Funding Agreement – Environment). |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 5 295 | 2 694 | 1 519 | 1 082 | various |
| Total new projects | 187 360 | 76 579 | 15 499 | 95 282 |  |

Source: Lower Murray Urban Rural Water Corporation

Notes:

(a) 	Lower Murray Water has consolidated several smaller projects into annual programs or larger projects with various completion dates. A footnote is provided to list the projects included in these programs of works.

(b) 	Lower Murray Water oversees programs of works that appear in the new, existing and completed projects year on year. As such, as forecasts are revised continuously, and as components of these programs move from new to existing and from existing to completed, program TEIs are likely to vary significantly from year to year. Program TEIs capture historical expenditure from 2024-25 onwards and are forecast out to 2035-36. Previously TEI was only calculated out to 2032-33.

Existing projects (a)(b)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Corporate – other works and services (regional various) | 72 761 | 4 336 | 5 952 | 62 473 | various |
| This is made up of the following projects from the 2025-26 Budget: various projects previously reported under ‘All remaining existing projects with a TEI less than $1 million’, Annual Vehicle replacement and building maintenance program (regional various), Control System Network, Irrigation Distribution, Meter System (including SCADA), Purchase of water (regional various). |  |  |  |  |  |
| Irrigation – channels (regional various) | 6 137 | 137 | .. | 6 000 | various |
| This is made up of the following projects from the 2025-26 Budget: Irrigation – Mildura replace/refurb of bridges (Mildura), Irrigation Distribution, Meter System (including SCADA), Irrigation – Mildura upgrade metermade (Mildura). |  |  |  |  |  |
| Irrigation – headworks (regional various) | 23 702 | 602 | .. | 23 100 | various |
| This is made up of the following projects from the 2025-26 Budget: Irrigation – Pump station variable speed drive replacement (regional various), Irrigation – Robinvale peak capacity enhancement irrigation delivery network (Robinvale), Irrigation – Red Cliffs main pumping station (Red Cliffs). |  |  |  |  |  |
| Irrigation – pipelines (regional various) | 3 330 | 381 | 1 168 | 1 781 | various |
| This is made up of the following projects from the 2025-26 Budget: Irrigation Distribution and Meter System (including SCADA), Irrigation Private Divertors, Irrigation Reticulation and Mains. |  |  |  |  |  |
| Land development shared assets (regional various) | 17 106 | 612 | 3 655 | 12 839 | various |
| The TEI has decreased by $23.130 million due to a revised forecast of land development shared asset projects. |  |  |  |  |  |
| Sewer – pipelines (regional various) | 10 409 | 860 | 840 | 8 709 | various |
| This is made up of the following projects from the 2025-26 Budget: Sewerage Reticulation and Rising Mains, Sewer – Robinvale SPS 6 renewal and pipeline (Robinvale), Sewer – Koorlong rising main duplication (Koorlong). |  |  |  |  |  |
| Sewer – treatment (regional various) | 11 739 | 849 | 5 388 | 5 503 | various |
| This is made up of the following projects from the 2025-26 Budget: various projects previously reported under ‘All remaining existing projects with a TEI less than $1 million’, Sewer – Koorlong wet weather storage No 2 (Koorlong), Sewer – rehabilitation of Koorlong irrigation areas (Koorlong), Sewer – wastewater treatment plant aeration works (Koorlong), Sewer – Swan Hill South West development (Swan Hill), Sewer – Mildura Pumping Station rebuild/upgrade (Mildura). |  |  |  |  |  |
| Water – headworks (regional various) | 17 460 | 5 782 | 1 177 | 10 500 | various |
| This is made up of the following projects from the 2025-26 Budget: Water – Red Cliffs pump station works (Red Cliffs), Water – storage works (regional various), Water Decommission Work, Water – Merbein variable speed drive, programmable logic controllers and the switchboards upgrade for treated water pump station (Merbein), PLC switchboards upgrade TWPS, Water – Mildura 10th Street tower repair work, Water – storage works pre-sedimental tank Kerang raw water supply (Kerang), Water – Mildura 14th Street tower (Mildura), Water – all sites pump station plant replacement (regional various). |  |  |  |  |  |
| Water – pipelines (regional various) | 22 575 | 2 221 | 1 887 | 18 467 | various |
| This is made up of the following projects from the 2025-26 Budget: Water – Red Cliffs pump station works (Red Cliffs), Water – all sites minor capital works – replacement (regional various), Water Reticulation and Rising Mains. |  |  |  |  |  |
| Water – treatment (regional various) | 117 684 | .. | 588 | 117 096 | various |
| This is made up of the following projects from the 2025-26 Budget: Water – Mildura WTP wash water balance tank (Mildura), Water – Swan Hill water treatment plant – new (Swan Hill North), Water – water treatment plant treated water pump station (stage 1) (Swan Hill North), Water – Mildura water treatment plant RWPS reconfiguration (Mildura), Water – Mildura water treatment plant filter to waste (Mildura), Water – Mildura ground level storage repaint (Mildura West), Water – Mildura 10ML treated water supply tank and pump station upgrade water reticulation system (Mildura). The TEI has increased by $68.328 million due to a revised project scope and review of planned spend mostly for the Water – water treatment plant treated water pump station (stage 1) (Swan Hill North) water treatment plant capacity upgrade. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 81 099 | 5 847 | 11 823 | 63 429 | various |
| This is made up of the following projects from the 2025-26 Budget: various projects previously reported under ‘All remaining existing projects with a TEI less than $1 million’, Water – all sites minor capital works – new (regional various), Water – all sites minor capital works – replacement (regional various), Water – all sites re–coat internals (regional various), Water – storage works (regional various), Water Reticulation and Rising Mains, Irrigation Pumping Stations, Irrigation Decommission Work, Irrigation Distribution and Meter System (including SCADA), Irrigation – minor capital – replacement (regional various), Private divertors replacement program (regional various), Irrigation Reticulation and Mains, Rehabilitation of sewers (regional various), Sewer – all sites minor capital works – new (regional various), Sewer – all sites minor capital works – replacement (regional various), Sewerage Reticulation and Rising Mains. |  |  |  |  |  |
| Total existing projects | 384 002 | 21 627 | 32 478 | 329 897 |  |
| Total Lower Murray Urban Rural Water Corporation projects | 571 362 | 98 206 | 47 977 | 425 179 |  |

Source: Lower Murray Urban Rural Water Corporation

Notes:

(a) 	Lower Murray Water has consolidated several smaller projects into annual programs or larger projects with various completion dates. A special once off footnote is provided to articulate the list of projects included in these programs of works.

(b) 	Lower Murray Water oversees programs of works that appear in the new, existing and completed projects year on year. As such, as forecasts are revised continuously, and as components of these programs move from new to existing and from existing to completed, program TEIs are likely to vary significantly from year to year. Program TEIs capture historical expenditure from 2024-25 onwards and are forecast out to 2035-36. Previously TEI was only calculated out to 2032-33.

Completed projects (a)(b)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Corporate – Other works and services (regional various) | 467 | 467 | qtr 4 2025-26 |
| This is made up of the Control System Network project from the 2025-26 Budget. |  |  |  |
| Land Development shared assets (regional various) | 25 | 25 | qtr 4 2025-26 |
| Sewer – Treatment (regional various) | 1 807 | 1 807 | qtr 4 2025-26 |
| This is made up of the following projects from the 2025-26 Budget: various projects previously reported under ‘All remaining existing projects with a TEI less than $1 million’. |  |  |  |
| Water – Headworks (regional various) | 141 | 141 | qtr 4 2025-26 |
| This is made up of the Water – Mildura 10th Street tower repair work project from the 2025-26 Budget. |  |  |  |
| Water – Treatment (regional various) | 800 | 800 | qtr 4 2025-26 |
| This is made up of the following projects from the 2025-26 Budget: Water – Mildura ground level storage repaint (Mildura West) |  |  |  |
| All remaining existing projects with a TEI less than $1 million | 3 506 | 3 506 | qtr 4 2025-26 |
| This is made up of the following projects from the 2025-26 Budget: Water – all sites minor capital works – replacement (regional various), Water – all sites minor capital works – new (regional various), various projects previously reported under ‘All remaining existing projects with a TEI less than $1 million’, Irrigation Distribution and Meter System (incl. Scada), Irrigation – minor capital –replacement (regional various), Irrigation – main replacements (regional various), Rehabilitation of sewers (regional various), Sewer – all sites minor capital works – new (regional various), Land development shared assets (regional various). |  |  |  |

Source: Lower Murray Urban Rural Water Corporation

Notes:

(a) 	Lower Murray Water has consolidated several smaller projects into annual programs or larger projects with various completion dates. A footnote is provided to list the projects included in these programs of works.

(b) 	Lower Murray Water oversees programs of works that appear in the new, existing and completed projects year on year. As such, as forecasts are revised continuously, and as components of these programs move from new to existing and from existing to completed, program TEIs are likely to vary significantly from year to year. Program TEIs capture historical expenditure from 2024-25 onwards and are forecast out to 2035-36. Previously TEI was only calculated out to 2032-33.

Melbourne Water Corporation

New projects (a)(b)(c)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Eastern treatment plant projects (Bangholme) | 8 585 | .. | 541 | 8 044 | ongoing |
| Land development projects (statewide) | 507 315 | .. | 85 908 | 421 406 | ongoing |
| Sewerage transfer projects (statewide) | 4 705 | .. | 4 210 | 495 | ongoing |
| Water production and storage projects (statewide) | 8 860 | .. | .. | 8 860 | ongoing |
| Water quality projects (statewide) | 5 242 | .. | 3 303 | 1 939 | ongoing |
| Water transfer projects (statewide) | 12 359 | .. | 430 | 11 929 | ongoing |
| All remaining projects with a TEI less than $1 million | 34 583 | .. | 11 020 | 23 563 | ongoing |
| Total new projects | 581 649 | .. | 105 412 | 476 236 |  |

Source: Melbourne Water Corporation

Notes:

(a) 	Melbourne Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

(b) 	Melbourne Water Corporation classifies ‘New’ projects as those that have not had any spending against them to date. Programs of work and projects are planned multiple years in advance, without any capital expenditure on individual projects until later years of the program. Therefore, there may be projects that are classified as ‘New’ for multiple years until they move into project development and delivery phases.

(c) 	All figures in these tables are based on Melbourne Water’s 10-Year Capital Plan. They do not represent Melbourne Water's 2026 Price Submission, which has been submitted and is waiting for determination.

Existing projects (a)(b)(c)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Cardinia dam safety upgrade project (Emerald) | 188 069 | 17 527 | 23 235 | 147 308 | qtr 2 2029-30 |
| The project was previously reported under Water Production and Storage (statewide) and is now being reported as a standalone project |  |  |  |  |  |
| Corporate support projects (statewide) | 170 931 | 10 314 | 20 426 | 140 190 | ongoing |
| Drainage and flood projects (statewide) | 886 076 | 93 100 | 97 107 | 695 868 | ongoing |
| Eastern treatment plant projects (Bangholme) | 3 773 194 | 158 358 | 79 623 | 3 535 213 | ongoing |
| Eastern treatment plant sludge dewatering upgrade project (Bangholme) | 192 041 | 1 807 | 517 | 189 717 | qtr 1 2030-31 |
| The project was previously included under the Eastern Treatment Plant Projects (Bangholme) and is now being reported as a standalone project. |  |  |  |  |  |
| Hobsons Bay Main Yarra crossing duplication (Spotswood) | 183 632 | 178 621 | 5 011 | .. | qtr 2 2026-27 |
| The TEI has increased by $2.345 million due to sewer relining which was confirmed following condition assessment. |  |  |  |  |  |
| Information technology projects (statewide) | 373 615 | 25 122 | 35 296 | 313 197 | ongoing |
| Land development projects (statewide) | 3 007 272 | 187 872 | 202 214 | 2 617 186 | ongoing |
| Maribyrnong main sewer augmentation project (Maribyrnong) | 108 304 | 71 021 | 20 997 | 16 286 | qtr 1 2028-29 |
| The project was previously included under Sewerage Transfer Projects (statewide) and is now being reported as a standalone project. |  |  |  |  |  |
| Sewerage transfer projects (statewide) | 2 141 035 | 70 022 | 87 296 | 1 983 718 | ongoing |
| Water production and storage projects (statewide) | 2 071 567 | 29 102 | 40 435 | 2 002 030 | ongoing |
| Water quality projects (statewide) | 2 091 950 | 70 949 | 88 447 | 1 932 554 | ongoing |
| Water transfer projects (statewide) | 2 222 986 | 37 663 | 48 359 | 2 136 964 | ongoing |
| Waterways condition projects (statewide) | 512 847 | 35 885 | 49 183 | 427 780 | ongoing |
| Waterways stormwater quality projects (statewide) | 299 449 | 23 488 | 33 258 | 242 703 | ongoing |
| Western treatment plant 5 West nutrient removal plant (Werribee) | 343 334 | 343 104 | 229 | .. | qtr 1 2026-27 |
| The TEI has increased by $11.639 million due to a revised project scope. The estimated completion date has been revised to quarter 1 2026‑27 in line with a revised project schedule. |  |  |  |  |  |
| Western treatment plant High Voltage Power and Energy Resilience (Werribee) | 137 257 | 25 488 | 48 769 | 63 000 | qtr 4 2027-28 |
| The project was previously included in the rolled-up Western Treatment Plant projects (Werribee) program and is now being reported as a standalone project. |  |  |  |  |  |
| Western treatment plant preliminary treatment (stage 1) (Werribee) | 374 908 | 1 751 | 5 801 | 367 356 | qtr 1 2031-32 |
| The project was previously included in the rolled-up Western Treatment Plant projects (Werribee) program and is now being reported as a standalone project. |  |  |  |  |  |
| Western treatment plant primary treatment capacity augmentation (Werribee) | 407 108 | 266 218 | 84 926 | 55 964 | qtr 4 2027-28 |
| The TEI has increased by $39.024 million due to a refined project design and forecast. |  |  |  |  |  |
| Western treatment plant projects (Werribee) | 2 348 875 | 73 002 | 88 786 | 2 187 087 | ongoing |
| Western treatment plant waste activated sludge treatment augmentation (Werribee) | 95 371 | 74 958 | 12 623 | 7 790 | qtr 4 2027-28 |
| The TEI has decreased by $11.139 million due to a revised project scope. |  |  |  |  |  |
| Western trunk sewer: shallow conduit rehabilitation (Werribee) | 231 538 | 30 425 | 54 233 | 146 880 | qtr 3 2029-30 |
| The TEI has decreased by $0.311 million based on the accepted tenderer’s cost. The estimated completion date has been revised to quarter 3 2029-30 in line with the revised project schedule. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 260 466 | 90 661 | 137 344 | 32 460 | ongoing |
| Total existing projects | 22 421 825 | 1 916 458 | 1 264 115 | 19 241 251 |  |
| Total Melbourne Water Corporation projects | 23 003 474 | 1 916 458 | 1 369 527 | 19 717 487 |  |

Source: Melbourne Water Corporation

Notes:

(a) 	Melbourne Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

(b) 	Melbourne Water Corporation classifies ‘New’ projects as those that have not had any spending against them to date. Programs of work and projects are planned multiple years in advance, without any capital expenditure on individual projects until later years of the program. Therefore, there may be projects that are classified as ‘New’ for multiple years until they move into project development and delivery phases.

(c) 	All figures in these tables are based on Melbourne Water’s 10-Year Capital Plan. They do not represent Melbourne Water's 2026 Price Submission, which has been submitted and waiting for determination.

Completed projects (a)(b)(c)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| 2021 condition monitoring of dams and headworks assets (regional various) | 1 243 | 1 243 | qtr 4 2025-26 |
| 2023 flood mapping program (regional various) | 3 666 | 3 666 | qtr 4 2025-26 |
| 2024 condition monitoring service reservoirs (regional various) | 5 662 | 5 662 | qtr 4 2025-26 |
| 24 volt direct current system upgrade and monitoring (regional various) | 1 572 | 1 572 | qtr 4 2025-26 |
| Alira drainage scheme shared assets subproject C (Berwick) | 2 279 | 2 279 | qtr 2 2025-26 |
| Audio visual upgrade phase 2 (regional various) | 1 443 | 1 443 | qtr 4 2025-26 |
| Black Forest Road drain section 10 council pipeline (Wyndham) | 1 976 | 1 976 | qtr 2 2025-26 |
| Botanic Ridge and Wylies drain branch F section 9 pipeline (Cranbourne) | 2 946 | 2 946 | qtr 2 2025-26 |
| Brooklyn pump station pumpset 4 pump and valves overhaul (Brooklyn) | 1 544 | 1 544 | qtr 3 2025-26 |
| Burrungma Dalga Creek section 10 (New Gisborne) | 3 664 | 3 664 | qtr 4 2025-26 |
| Burrungma Dalga Creek section 6 (New Gisborne) | 1 329 | 1 329 | qtr 3 2025-26 |
| Burrungma Dalga Creek section 7 (Gisborne) | 1 476 | 1 476 | qtr 4 2025-26 |
| Cardinia chlorine solution piping renewal (Emerald) | 3 693 | 3 693 | qtr 1 2025-26 |
| Cardinia Creek Lower section 26 – land reimbursement (Clyde North) | 3 225 | 3 225 | qtr 4 2025-26 |
| Chlorine contact pipe for Lyrebird and Brahams plant (regional various) | 2 841 | 2 841 | qtr 4 2025-26 |
| Clyde outfall section 10 retarding basin (Clyde) | 4 134 | 4 134 | qtr 2 2025-26 |
| Curly Sedge Creek section 3 (Wollert) | 2 524 | 2 524 | qtr 3 2025-26 |
| Cyber defence initiatives (regional various) | 3 404 | 3 404 | qtr 4 2025-26 |
| Darebin Creek Upper section – land reimbursement (Donnybrook) | 13 356 | 13 356 | qtr 3 2025-26 |
| Darebin Creek Upper section 5 (Dannybrook) | 7 444 | 7 444 | qtr 2 2025-26 |
| Dilop Drive retarding basin section 4 (Epping) | 10 325 | 10 325 | qtr 2 2025-26 |
| Disaster recovery enablement (Brooklyn) | 1 042 | 1 042 | qtr 3 2025-26 |
| Dry Creek section 14 (Tarneit) | 1 054 | 1 054 | qtr 3 2025-26 |
| Dry Creek section 23 (Mount Cottrell) | 7 310 | 7 310 | qtr 3 2025-26 |
| Easter treatment plant bandscreen 2 and 3 renewals (Bangholme) | 1 280 | 1 280 | qtr 2 2025-26 |
| Easter treatment plant combo truck replacement (Bangholme) | 1 054 | 1 054 | qtr 2 2025-26 |
| Eastern contour drain section 14 (Dandenong South) | 1 473 | 1 473 | qtr 2 2025-26 |
| Eastern treatment plant dissolved air flotation 2 3 and 6 Top Collector Assembly Renewal (Bangholme) | 2 709 | 2 709 | qtr 3 2025-26 |
| Eastern treatment plant grit roof renewal (Bangholme) | 2 335 | 2 335 | qtr 3 2025-26 |
| Eastern treatment plant grit washers renewal (Bangholme) | 1 385 | 1 385 | qtr 2 2025-26 |
| Eastern treatment plant influent pump station 6 and 8 delivery valve refurbishment (Bangholme) | 2 030 | 2 030 | qtr 4 2025-26 |
| Eastern treatment plant preliminary sediment tank 1 renewal (Bangholme) | 1 602 | 1 602 | qtr 4 2025-26 |
| Eastern treatment plant preliminary sediment tank 6 renewal (Bangholme) | 1 701 | 1 701 | qtr 3 2025-26 |
| Eastern treatment plant primary sediment tank 6 mechanical and electrical refurbishment (Bangholme) | 1 159 | 1 159 | qtr 3 2025-26 |
| Eastern treatment plant primary sedimentation tank 1 mechanical and electrical refurbishment (Bangholme) | 1 064 | 1 064 | qtr 4 2025-26 |
| Eastern treatment plant secondary sedimentation tank 21 mechanical and electrical renewal and civil assessment (Bangholme) | 1 711 | 1 711 | qtr 4 2025-26 |
| Eastern treatment plant skylights renewal (Bangholme) | 2 277 | 2 277 | qtr 3 2025-26 |
| Eastern treatment plant ultra violet lamps renewal 2024 (Bangholme) | 1 187 | 1 187 | qtr 1 2025-26 |
| Eastern treatment plant vacuum and superchlorinated water pipework renewals (Bangholme) | 4 008 | 4 008 | qtr 2 2025-26 |
| Eastern treatment plant vacuum pressure swing adsorption adsorber vessel media replacement (Bangholme) | 3 323 | 3 323 | qtr 4 2025-26 |
| Edgars Creek east branch section 11 retarding basin and wetland system (Wollert) | 3 329 | 3 329 | qtr 3 2025-26 |
| Edgars Creek section 58 (Wollert) | 6 019 | 6 019 | qtr 2 2025-26 |
| Electric vehicle charging stations 2025 (regional various) | 2 501 | 2 501 | qtr 4 2025-26 |
| End-use computing lifecycle renewal FY24-26 (regional various) | 3 219 | 3 219 | qtr 4 2025-26 |
| Essex Street main drain renewal (South Yarra) | 16 374 | 16 374 | qtr 3 2025-26 |
| Faulds and Olinda chlorine and pH analysers renewal (Montrose) | 1 325 | 1 325 | qtr 4 2025-26 |
| Findon Creek sections 26 and 29 waterways and sediment pond (Wollert) | 2 341 | 2 341 | qtr 3 2025-26 |
| Flood mapping program (regional various) | 2 385 | 2 385 | qtr 4 2025-26 |
| Forsyth Road drain section 48 (Truganina) | 2 291 | 2 291 | qtr 3 2025-26 |
| Forsyth Road drain section 48 land reimbursement (Tarneit) | 1 373 | 1 373 | qtr 1 2025-26 |
| Greenvale reservoir park – southern section minor works (Greenvale) | 2 530 | 2 530 | qtr 2 2025-26 |
| Heavy firefighting machinery acquisition 2021-23 (regional various) | 1 539 | 1 539 | qtr 4 2025-26 |
| Highlands West sediment pond east of Darwinia Drive (Mickleham) | 1 848 | 1 848 | qtr 3 2025-26 |
| Impervious mapping data improvement 2022 (regional various) | 1 332 | 1 332 | qtr 4 2025-26 |
| Jacksons Creek section 7 (Sunbury) | 3 634 | 3 634 | qtr 4 2025-26 |
| Kororoit Creek section 54 (Plumpton) | 5 860 | 5 860 | qtr 2 2025-26 |
| Kororoit Creek Upper drainage scheme section 36 retarding basin and wetland (Melton) | 4 418 | 4 418 | qtr 2 2025-26 |
| Kororoit Creek Upper section 63 – land (Plumpton) | 2 805 | 2 805 | qtr 1 2025-26 |
| Kororoit Creek Upper section 63 (Plumpton) | 3 325 | 3 325 | qtr 3 2025-26 |
| Kororoit Creek Upper section 76 – land (Plumpton) | 7 841 | 7 841 | qtr 2 2025-26 |
| Kororoit Creek Upper section 90 (Plumpton) | 2 171 | 2 171 | qtr 2 2025-26 |
| Kororoit Creek Upper section 94 – land (Plumpton) | 2 064 | 2 064 | qtr 3 2025-26 |
| Kororoit Creek Upper section 94 retarding basin and wetland (Plumpton) | 5 345 | 5 345 | qtr 1 2025-26 |
| Kororoit Creek Upper section 97, 98 and 99 (Mount Cottrell) | 1 021 | 1 021 | qtr 4 2025-26 |
| Kororoit Creek Upper sections 67 and 80 (Plumpton) | 3 198 | 3 198 | qtr 1 2025-26 |
| Laverton Creek drainage scheme section 66 (Truganina) | 2 785 | 2 785 | qtr 3 2025-26 |
| Lehamanns Road drain section 6 retarding basin and wetland (Wollert) | 1 850 | 1 850 | qtr 4 2025-26 |
| Lollypop Creek section 34 deed reimbursement (Werribee) | 3 846 | 3 846 | qtr 3 2025-26 |
| M22 -M46 water mains renewal (Glen Waverley) | 68 443 | 68 443 | qtr 3 2025-26 |
| M76 water main renewal (Mount Waverley) | 31 799 | 31 799 | qtr 1 2025-26 |
| Maroondah Road 13-9-24 loop renewal (Healesville) | 1 636 | 1 636 | qtr 4 2025-26 |
| Masons Lane drain section 2 retarding basin (Bacchus Marsh) | 2 199 | 2 199 | qtr 4 2025-26 |
| Masterplan and modelling for Fishermans Bend urban renewal cost recovery scheme (regional various) | 3 687 | 3 687 | qtr 3 2025-26 |
| Mill Park wetland rectification (South Morang) | 19 363 | 19 363 | qtr 1 2025-26 |
| Monbulk Creek smart water network – lake retrofit (Lysterfield) | 1 115 | 1 115 | qtr 4 2025-26 |
| Mordialloc main sewer rehabilitation (Mordialloc) | 13 115 | 13 115 | qtr 3 2025-26 |
| Muddy Gates drain central branch section 14 (Clyde) | 1 385 | 1 385 | qtr 3 2025-26 |
| Muddy Gates drain central section 15 (Clyde) | 1 900 | 1 900 | qtr 4 2025-26 |
| NWS007 access cover and siphon air line upgrade (Aberfeldie) | 2 424 | 2 424 | qtr 3 2025-26 |
| Pintail Drive section 31 raingarden and outfall pipe (Melton South) | 2 601 | 2 601 | qtr 3 2025-26 |
| Point Cook Creek section 22 and 23 (Point Cook) | 5 144 | 5 144 | qtr 3 2025-26 |
| Power Station genset service year 1 (Bangholme) | 3 086 | 3 086 | qtr 3 2025-26 |
| SET012 and SET013 multipart gatic cover replacement (regional various) | 1 163 | 1 163 | qtr 4 2025-26 |
| Sewer ventilation stack renewals 2025 (regional various) | 1 741 | 1 741 | qtr 3 2025-26 |
| Sewerage transfer condition monitoring 2024-25 (regional various) | 2 676 | 2 676 | qtr 3 2025-26 |
| Sewerage transfer reactive capital 2023-24 (regional various) | 1 291 | 1 291 | qtr 3 2025-26 |
| Sheltons drain west branch section 33 (Keysborough) | 2 268 | 2 268 | qtr 4 2025-26 |
| St Albans reservoir bypass pipeline (St Albans) | 7 801 | 7 801 | qtr 2 2025-26 |
| St Georges Road billing flowmeter replacements (Brunswick East) | 2 566 | 2 566 | qtr 3 2025-26 |
| Stephens Creek section 14 (Gisborne) | 5 562 | 5 562 | qtr 1 2025-26 |
| Streamside vegetation surveillance monitoring (regional various) | 2 302 | 2 302 | qtr 4 2025-26 |
| Sunbury waterway health data acquisition (regional various) | 1 898 | 1 898 | qtr 4 2025-26 |
| Tank boot seal replacements stage 1 (St Albans) | 2 749 | 2 749 | qtr 3 2025-26 |
| Tank boot seal replacements stage 2 (St Albans) | 2 764 | 2 764 | qtr 4 2025-26 |
| TechOne cloud transition (regional various) | 1 154 | 1 154 | qtr 1 2025-26 |
| Thompsons drain section 4 (Truganina) | 3 614 | 3 614 | qtr 4 2025-26 |
| Thomson Hydro capacitor bank (Thomson) | 4 178 | 4 178 | qtr 1 2025-26 |
| Thomson TJ and Graptolite Road Renewal (Baw Baw) | 1 505 | 1 505 | qtr 4 2025-26 |
| Ti-Tree Creek section 129 – land reimbursement (Cranbourne West) | 10 672 | 10 672 | qtr 3 2025-26 |
| Toolern Creek section 36 (Melton South) | 1 823 | 1 823 | qtr 3 2025-26 |
| Toomuc Creek Lower section 21 (Office South) | 3 129 | 3 129 | qtr 4 2025-26 |
| Tributary of 6511 section 1 (Donnybrook) | 2 774 | 2 774 | qtr 4 2025-26 |
| Tributary of Dry Creek section 1 – land reimbursement (Tarneit) | 4 674 | 4 674 | qtr 4 2025-26 |
| Tributary of 6557 section 2 (Beveridge) | 7 123 | 7 123 | qtr 3 2025-26 |
| Tributary of 6557 section 3 (Beveridge) | 6 196 | 6 196 | qtr 4 2025-26 |
| Tributary of 6559 section 3 (Beveridge) | 6 343 | 6 343 | qtr 4 2025-26 |
| Tributary of 6561 Section 1 (Beveridge) | 3 565 | 3 565 | qtr 1 2025-26 |
| Tributary of 7730 section 8 (Manor Lakes) | 4 036 | 4 036 | qtr 3 2025-26 |
| Tributary of Aitken Creek section 13 (Mickleham) | 1 502 | 1 502 | qtr 2 2025-26 |
| Tributary of Davis Creek section 3 (Tarneit) | 1 493 | 1 493 | qtr 3 2025-26 |
| Tributary of Davis Creek section 4 (Tarneit) | 1 005 | 1 005 | qtr 3 2025-26 |
| Tributary of Dry Creek section 7 (Tarneit) | 4 692 | 4 692 | qtr 3 2025-26 |
| Tributary of Emu Creek sediment tank and pipework (Sunbury) | 4 621 | 4 621 | qtr 3 2025-26 |
| Tributary of Kororoit Creek Upper section 2 and 11 (Rockbank) | 2 668 | 2 668 | qtr 2 2025-26 |
| Tributary of Kororoit Creek Upper section 8 (Plumpton) | 1 477 | 1 477 | qtr 4 2025-26 |
| Tributary of Lollypop Creek section 1 wetland (Manor Lakes) | 4 329 | 4 329 | qtr 3 2025-26 |
| Tributary of Lollypop Creek section 6 (Manor Lakes) | 1 304 | 1 304 | qtr 3 2025-26 |
| Tributary of Skeleton Creek Upper section 2 – land (Truganina) | 3 548 | 3 548 | qtr 1 2025-26 |
| Tributary of Skeleton Creek Upper section 2 (Tarneit) | 6 017 | 6 017 | qtr 4 2025-26 |
| Tributary of Stony Hill creek section 14 (Plumpton) | 1 484 | 1 484 | qtr 3 2025-26 |
| Tributary of Stony Hill Creek section 16 (Plumpton) | 8 550 | 8 550 | qtr 1 2025-26 |
| Tributary of Werribee River Lower section 2 council wetland and pipeline (Wyndham Vale) | 1 867 | 1 867 | qtr 3 2025-26 |
| Ultraviolet transmittance and colour analysers for membrane for water treatment sites (regional various) | 1 196 | 1 196 | qtr 4 2025-26 |
| Upper Yarra reservoir spillway ogee weir remediation (Reefton) | 4 360 | 4 360 | qtr 4 2025-26 |
| Wallaby Road 10 north renewal (Whittlesea) | 1 054 | 1 054 | qtr 4 2025-26 |
| Wantirna divide valve and cathodic protection work (Wantirna) | 2 006 | 2 006 | qtr 2 2025-26 |
| Water quality and treatment reactive capital 2025 (regional various) | 1 044 | 1 044 | qtr 2 2025-26 |
| Water Transfer reactive capital 2025 (regional various) | 4 301 | 4 301 | qtr 2 2025-26 |
| Waterways exclusion fencing and signage 2025 (regional various) | 1 138 | 1 138 | qtr 3 2025-26 |
| Web enhancements (regional various) | 1 455 | 1 455 | qtr 4 2025-26 |
| Werribee River Lower section 12 (Tarneit) | 7 594 | 7 594 | qtr 3 2025-26 |
| Western treatment plant 160S nitrogen removal plan membrane renewal (Werribee) | 5 979 | 5 979 | qtr 4 2025-26 |
| Western treatment plant 25 west lateral floatation solution (Werribee) | 1 838 | 1 838 | qtr 3 2025-26 |
| Western treatment plant procurement of combination truck (Werribee) | 1 285 | 1 285 | qtr 2 2025-26 |
| Wetland southwest of surround circuit (Rockbank) | 5 163 | 5 163 | qtr 1 2025-26 |
| Winneke pump station replacement of gland seal panels on supernatant pumps (Christmas Hills) | 1 158 | 1 158 | qtr 2 2025-26 |
| Wylies drain branch F section 12 waterway (Junction Village) | 2 117 | 2 117 | qtr 3 2025-26 |
| Wylies drain F branch section 2 retarding basin including inlet pipe (Devon Meadows) | 1 928 | 1 928 | qtr 4 2025-26 |
| Yale Drive drain Council pipeline (Epping) | 1 057 | 1 057 | qtr 4 2025-26 |
| Yan Yean to Bald Hill pipeline cross connection to Yarra Valley system (Yan Yean) | 1 699 | 1 699 | qtr 2 2025-26 |
| Yarra River habitat improvement Dights Falls to Banksia Steet (Abbotsford) | 1 069 | 1 069 | qtr 2 2025-26 |
| Yarra Valley conduit valve house isolation valves replacement and condition monitoring (Stratmore) | 1 071 | 1 071 | qtr 3 2025-26 |
| Yering George pump station, main pump motor 3 and main pumpset 2 and 3 overhaul (Christmas Hills) | 2 506 | 2 506 | qtr 4 2025-26 |
| Yering Gorge pump station service water system renewal (Christmas Hills) | 5 321 | 5 321 | qtr 4 2025-26 |

Source: Melbourne Water Corporation

Notes:

(a) 	Melbourne Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

(b) 	Melbourne Water Corporation classifies ‘New’ projects as those that have not had any spending against them to date. Programs of work and projects are planned multiple years in advance, without any capital expenditure on individual projects until later years of the program. Therefore, there may be projects that are classified as ‘New’ for multiple years until they move into project development and delivery phases.

(c) 	All figures in these tables are based on Melbourne Water’s 10-Year Capital Plan. They do not represent Melbourne Water's 2026 Price Submission, which has been submitted and waiting for determination.

North East Region Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Barnawartha sewer upgrade (Barnawartha) | 1 616 | 1 616 | .. | .. | qtr 4 2025-26 |
| Benalla wastewater treatment plant upgrade stage 1 (Benalla) | 5 848 | 101 | 147 | 5 600 | qtr 4 2030-31 |
| Wangaratta water treatment plant Faithful Street upgrade (Wangaratta) | 19 498 | 29 | 275 | 19 194 | qtr 4 2030-31 |
| Yarrawonga 5 megalitre clear water storage (Yarrawonga) | 2 569 | 76 | 250 | 2 243 | qtr 4 2027-28 |
| Yarrawonga southern sewer pump station (Yarrawonga) | 5 560 | 119 | .. | 5 441 | qtr 4 2030-31 |
| All remaining projects with a TEI less than $1 million | 4 409 | 467 | 1 106 | 2 836 | various |
| Total new projects | 39 500 | 2 408 | 1 778 | 35 314 |  |

Source: North East Region Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Above ground asset replacement – wastewater (regional various) | 16 555 | 3 219 | 3 434 | 9 902 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Above ground asset replacement – water (regional various) | 13 516 | 2 432 | 2 943 | 8 141 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Baranduda Whytes Road sewer pump station (Baranduda) | 9 946 | 3 625 | 4 011 | 2 310 | qtr 4 2027-28 |
| The TEI has increased by $3.737 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2027-28. |  |  |  |  |  |
| Beechworth wastewater treatment plant upgrade (Beechworth) | 18 041 | 588 | 4 850 | 12 603 | qtr 4 2029-30 |
| The TEI has increased by $1.520 million due to the inclusion of the second stage of the project. The estimated completion date been revised to quarter 4 2029-30. |  |  |  |  |  |
| Below ground asset replacement – wastewater (regional various) | 15 249 | 2 649 | 2 520 | 10 080 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Below ground asset replacement – water (regional various) | 19 190 | 4 190 | 3 000 | 12 000 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Bright wastewater treatment plant upgrade (Bright) | 21 026 | 1 021 | 305 | 19 700 | qtr 4 2028-29 |
| The estimated completion date has been revised to quarter 4 2028-29 in line with a revised project schedule. |  |  |  |  |  |
| Information communication technology infrastructure replacements (regional various) | 2 086 | 356 | 250 | 1 480 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Kiewa and Tangambalanga water system upgrade (Tangambalanga) | 18 453 | 2 579 | .. | 15 874 | qtr 4 2030-31 |
| The TEI has increased by $2.398 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2030-31 pending North East Water’s price review. |  |  |  |  |  |
| Mount Beauty clear water storage (Mount Beauty) | 5 947 | 655 | 1 110 | 4 182 | qtr 4 2027-28 |
| The TEI has increased by $1.911 million due to a revised project scope. The estimated completion date been revised to quarter 4 2027-28 in line with this revised scope. |  |  |  |  |  |
| Mount Beauty raw water offtake upgrade (Mount Beauty) | 5 478 | 2 152 | 3 326 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.044 million due to a revised project schedule. The estimated completion date has been revised to quarter 4 2026-27 in line with external delays in site works. |  |  |  |  |  |
| Permanent water purchase (regional various) | 6 475 | 1 775 | 940 | 3 760 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Porepunkah security of supply project (Porepunkah) | 2 337 | 136 | 300 | 1 901 | qtr 4 2030-31 |
| The estimated completion date has been revised to quarter 4 2030-31 pending North East Water’s next price review. |  |  |  |  |  |
| Region wide digital metering (regional various) | 1 210 | 38 | 612 | 560 | qtr 4 2028-29 |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Region wide minor capital expenditure (regional various) | 1 498 | 249 | 250 | 1 000 | ongoing |
| Rutherglen reuse land – stage 1 (Rutherglen) | 11 937 | 1 157 | 5 480 | 5 300 | qtr 4 2027-28 |
| The TEI has decreased by $1.241 million due to a revised project scope. |  |  |  |  |  |
| Supervisory control and data acquisition system upgrade and replacement (regional various) | 3 879 | 129 | 750 | 3 000 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Tallangatta clear water storage (Tallangatta) | 3 209 | 331 | .. | 2 878 | qtr 4 2030-31 |
| The estimated completion date has been revised to quarter 4 2030-31 in line with a number of clear water storage projects being delivered as a package of works. |  |  |  |  |  |
| Vehicle replacement (regional various) | 7 582 | 1 082 | 1 300 | 5 200 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Wangaratta groundwater investigation (Wangaratta) | 1 795 | 1 208 | 587 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.647 million due to additional test monitoring bores being required. |  |  |  |  |  |
| Wangaratta trade waste plant upgrade project (Wangaratta) | 1 509 | 89 | .. | 1 420 | qtr 4 2030-31 |
| The TEI has decreased by $0.803 million due to a revised project scope. Timing of this project is now expected for completion in quarter 4 2030-31 as a result of this revised project scope. |  |  |  |  |  |
| Wangaratta works depot relocation (Wangaratta) | 2 414 | 1 009 | .. | 1 405 | qtr 4 2030-31 |
| The TEI has increased by $0.328 million due to a revised project scope. Timing for this project is now expected for completion in quarter 4 2030-31 as a result of this revised project scope. |  |  |  |  |  |
| Wodonga Leneva wastewater (Wodonga) | 13 098 | 4 957 | 4 800 | 3 341 | ongoing |
| The TEI has decreased by $5.714 million due to a revised project scope. |  |  |  |  |  |
| Wodonga Leneva water (Wodonga) | 23 846 | 3 887 | 3 600 | 16 359 | ongoing |
| The TEI has increased by $6.433 million due to a revised project scope. |  |  |  |  |  |
| Wodonga sewerage transfer capacity (Wodonga) | 37 992 | 4 644 | 500 | 32 848 | ongoing |
| The TEI has increased by $12.144 million due to a revised project scope. |  |  |  |  |  |
| Wodonga wastewater treatment plan outfall pipeline (Wodonga) | 7 623 | 3 749 | 2 874 | 1 000 | qtr 4 2027-28 |
| The estimated completion date is now quarter 4 2027-28 due to a revised project schedule. |  |  |  |  |  |
| Wodonga wastewater treatment plant capacity and emissions reduction upgrade (Wodonga) | 84 303 | 76 904 | 7 400 | .. | qtr 4 2026-27 |
| The TEI has decreased by $1.420 million due to a reduction in the project’s contingency allowance as the project nears completion. |  |  |  |  |  |
| Yarrawonga water treatment plant renewal (Yarrawonga) | 7 905 | 223 | 300 | 7 382 | qtr 4 2030-31 |
| The TEI has increased by $4.655 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2030-31 in line with this revised project scope. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 9 142 | 2 835 | 2 788 | 3 519 | ongoing |
| Occupational health and safety improvements, Region wide online applications, Region wide digital business sustainability, Region wide renewable energy and climate efficiencies, Water trunk mains, Water and wastewater systems improvement project have all had TEI decreases to less than $1.000 million. |  |  |  |  |  |
| Total existing projects | 373 241 | 127 868 | 58 230 | 187 145 |  |
| Total North East Region Water Corporation projects | 412 741 | 130 276 | 60 008 | 222 459 |  |

Source: North East Region Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Barnawartha sewer upgrade (Barnawartha) | 1 616 | 1 616 | qtr 4 2025-26 |
| Project was commenced and completed in the 2025-26 financial year. |  |  |  |
| Beechworth Road water pump station upgrade (Wodonga) | 547 | 547 | qtr 4 2025-26 |
| The TEI has increased by $0.558 million due to changes to design scope. The estimated completion date been revised to quarter 4 2025-26. |  |  |  |
| Benalla wastewater treatment plant upgrade (Benalla) | 2 623 | 2 623 | qtr 4 2025-26 |
| The TEI has decreased by $5.907 million as this phase of the project has now been completed. |  |  |  |
| Region wide strategic land acquisition (regional various) | 3 842 | 3 842 | qtr 4 2025-26 |
| The TEI has decreased by $0.232 million due to recognition of a provisional budget for land acquisition in 2025-26 under the actual project budget (Wodonga Leneva Water (Wodonga)). |  |  |  |
| Wangaratta north west detention tanks (Wangaratta) | 3 658 | 3 658 | qtr 4 2025-26 |
| The TEI has increased by $0.322 million due to additional works required for project completion. |  |  |  |
| Wangaratta Reith Lindner Road sewer pump station (Wangaratta) | 3 259 | 3 259 | qtr 4 2025-26 |
| The TEI has increased by $0.376 million due to additional works required for project completion. |  |  |  |
| Wangaratta Wangandary pump station (Wangaratta) | 1 764 | 1 764 | qtr 4 2025-26 |
| The TEI has increased by $0.109 million due to additional works required for project completion. |  |  |  |
| Wodonga water treatment plant – powder activated carbon upgrade (Wodonga) | 6 425 | 6 425 | qtr 4 2025-26 |
| Yarrawonga South Road sewer pump station upgrade (Yarrawonga) | .. | .. |  |
| This project has been removed from the capital works program. |  |  |  |

Source: North East Region Water Corporation

Port of Hastings Development Authority

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Concrete Remediation Works (Crib Point) | 2 600 | 500 | 700 | 1 400 | qtr 4 2028‑29 |
| Ongoing Capital Program (Crib Point, Hastings) | 1 170 | .. | 400 | 770 | ongoing |
| All remaining projects with a TEI less than $1 million | 3 858 | 2 128 | 635 | 1 095 | various |
| Asset replacement and maintenance, including jetty strengthening works, fender installation and upgrades, and punt replacements. |  |  |  |  |  |
| Total new projects | 7 628 | 2 628 | 1 735 | 3 265 |  |

Source: Port of Hastings Development Authority

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| All remaining projects with a TEI less than $1 million | 623 | 473 | 90 | 60 | various |
| Total existing projects | 623 | 473 | 90 | 60 |  |
| Total Port of Hastings Corporation projects | 8 251 | 3 101 | 1 825 | 3 325 |  |

Source: Port of Hastings Development Authority

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| All remaining projects with a TEI less than $1 million | 85 | 85 | qtr 4 2025‑26 |

Source: Port of Hastings Development Authority

Ports Victoria

New projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Channels and waterways – capital projects (Port Phillip Bay, Geelong and Hastings) | 2 750 | 200 | 550 | 2 000 | various |
| The TEI has decreased by $3.140 million due to Marine and Navigation related upgrade requirements. |  |  |  |  |  |
| Station Pier capital projects (Port Melbourne) | 2 393 | .. | 330 | 2 063 | various |
| The TEI has increased by $2.393 million due to Station Pier related initiatives including screening equipment lift/escalator replacements and Australian Border Force screens. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 295 | 245 | 50 | .. | various |
| The TEI now includes Information technology – upgrades and development (Melbourne, Geelong and Hastings). |  |  |  |  |  |
| Total new projects | 5 438 | 445 | 930 | 4 063 |  |

Source: Ports Victoria

Note:

(a) 	Ports Victoria structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs of programs are likely to vary year on year and are completed based on appropriate timing, resourcing and priority.

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Channels and waterways – capital projects (Port Phillip Bay, Geelong and Hastings) | 16 648 | 5 597 | 3 052 | 8 000 | various |
| The TEI has increased by $4.133 million predominately due to Vessel Traffic Service related upgrades and projects. |  |  |  |  |  |
| Station Pier capital projects (Port Melbourne) | 13 824 | 524 | .. | 13 300 | various |
| The TEI has decreased by $2.595 million predominately due to the Station Pier Fender Upgrade project and a deferral of fender upgrade phasing and updated estimated costings. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 2 707 | 1 937 | 770 | .. | various |
| The TEI now includes Information technology – upgrades and development (Melbourne, Geelong and Hastings) and has decreased by $0.552 million mainly due to a project which did not proceed. |  |  |  |  |  |
| Total existing projects | 33 179 | 8 058 | 3 822 | 21 300 |  |
| Total Ports Victoria projects | 38 617 | 8 503 | 4 752 | 25 363 |  |

Source: Ports Victoria

Note:

(a) 	Ports Victoria structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs of programs are likely to vary year on year and are completed based on appropriate timing, resourcing and priority.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| All remaining projects with a TEI less than $1 million | 137 | 137 | qtr 4 2025-26 |

Source: Ports Victoria

Note:

(a) 	Ports Victoria structures its projects as programs of work, which comprise new, existing and completed components year on year. The TEIs of programs are likely to vary year on year and are completed based on appropriate timing, resourcing and priority.

South East Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Corporate miscellaneous – other (metropolitan various) | 30 342 | 19 301 | 6 781 | 4 260 | qtr 4 2027-28 |
| Recycled water growth – other (metropolitan various) | 29 247 | 1 478 | 1 356 | 26 413 | qtr 4 2031-32 |
| Sewer and trade waste compliance – other (metropolitan various) | 20 713 | 3 496 | 1 590 | 15 627 | qtr 4 2032-33 |
| Sewer and trade waste growth – other (metropolitan various) | 12 999 | 1 269 | 194 | 11 536 | qtr 4 2032-33 |
| Sewer and trade waste reliability – other (metropolitan various) | 28 557 | 10 342 | 150 | 18 065 | qtr 4 2030-31 |
| Water growth – other (metropolitan various) | 108 029 | 2 614 | 1 016 | 104 399 | qtr 4 2031-32 |
| Water quality – other (metropolitan various) | 12 505 | 1 184 | .. | 11 321 | qtr 4 2031-32 |
| Water reliability – other (metropolitan various) | 274 894 | 6 695 | 5 394 | 262 805 | qtr 4 2035-36 |
| Total new projects | 517 286 | 46 379 | 16 481 | 454 426 |  |

Source: South East Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Corporate climate change – other (metropolitan various) | 15 254 | 1 871 | 1 423 | 11 960 | ongoing |
| The TEI has decreased by $1.300 million due to revised investments into climate change projects. |  |  |  |  |  |
| Corporate miscellaneous (metropolitan various) | 59 346 | 12 773 | 7 251 | 39 322 | ongoing |
| The TEI has decreased by $9.507 million mainly due to completion of planned land acquisitions. |  |  |  |  |  |
| Information technology – other (metropolitan various) | 93 547 | 9 524 | 21 437 | 62 586 | ongoing |
| The TEI has decreased by $122.293 million due to reallocation of IT related costs into different projects, as well as completion, reprioritisation and reprofiling of projects. |  |  |  |  |  |
| Meters (metropolitan various) | 204 067 | 43 364 | 46 361 | 114 342 | ongoing |
| The TEI has decreased by $35.516 million due to the digital metering program progressing through 2024-25, and also due to contracted price of meters being lower than originally forecasted. |  |  |  |  |  |
| Recycled water compliance – other (metropolitan various) | 16 263 | 5 440 | 1 795 | 9 028 | qtr 4 2032-33 |
| The TEI has decreased by $7.569 million due to reprioritisation and reprofiling of recycled water compliance projects. |  |  |  |  |  |
| Recycled water growth – other (metropolitan various) | 156 172 | 30 485 | 22 963 | 102 724 | ongoing |
| The TEI has decreased by $22.339 million due to reprioritisation and reprofiling of recycled water growth projects. There has also been reallocation of Mt Martha Treatment Plant Switchboard upgrade project from Recycled Water growth to Sewer and Trade Waste Growth – Mornington Peninsula Shire. |  |  |  |  |  |
| Recycled water quality – Cardinia Shire Council (Cardinia) | 54 134 | 3 679 | 23 385 | 27 070 | qtr 4 2036-37 |
| The TEI has decreased by $24.105 million mainly due to project reprioritisation. External funding from the National Water Grid program has also been received, resulting in reduced costs required. |  |  |  |  |  |
| Sewer and trade waste compliance – other (metropolitan various) | 284 310 | 37 879 | 39 113 | 207 318 | qtr 4 2033-24 |
| The TEI has increased by $7.260 million due to reprioritisation and reprofiling of sewer and trade waste compliance projects. |  |  |  |  |  |
| Sewer and trade waste growth – Cardinia Shire Council (Cardinia) | 200 377 | 5 697 | 1 610 | 193 070 | qtr 4 2032-33 |
| The TEI has increased by $85.515 million due to revised project scope and continued increasing investment for projects. |  |  |  |  |  |
| Sewer and trade waste growth – City of Melbourne (Melbourne) Hanna Street | 99 846 | 5 828 | 33 860 | 60 158 | qtr 4 2034-35 |
| The TEI has decreased by $16.422 million due to revised schedules for projects shifting investment spend to future periods. However, there has been no change to project scope. |  |  |  |  |  |
| Sewer and trade waste growth – Mornington Peninsula Shire (Mornington) | 100 301 | 17 300 | 25 313 | 57 688 | qtr 4 2029-30 |
| The TEI has increased by $4.005 million due to revised project scope. |  |  |  |  |  |
| Sewer and trade waste growth – other (metropolitan various) | 638 099 | 65 343 | 86 826 | 485 930 | qtr 4 2037-38 |
| The TEI has increased by $148.337 million due to revised project scope. |  |  |  |  |  |
| Sewer and trade waste quality – other (metropolitan various) | 24 838 | 10 783 | 1 326 | 12 729 | qtr 4 2032-33 |
| The TEI has decreased by $7.731 million due to reprioritisation and reprofiling of sewer and trade waste quality projects. |  |  |  |  |  |
| Sewer and trade waste reliability – other (metropolitan various) | 383 799 | 39 889 | 51 421 | 292 489 | qtr 4 2034-35 |
| The TEI has increased by $57.529 million due to budget reprioritisation and accelerated project spend. |  |  |  |  |  |
| Water growth – other (metropolitan various) | 168 826 | 24 431 | 36 392 | 108 003 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water quality – other (metropolitan various) | 95 308 | 7 363 | 15 725 | 72 220 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Water reliability – other (metropolitan various) | 494 899 | 61 598 | 70 136 | 363 165 | ongoing |
| The TEI has increased by $137.037 million due to progress in delivery and increase in allocated investment of projects such as the Rosebud to Dromana Water Mains Renewal, as well as budget reprioritisation. |  |  |  |  |  |
| Total existing projects | 3 089 386 | 383 247 | 486 337 | 2 219 802 |  |
| Total South East Water Corporation projects | 3 606 672 | 429 626 | 502 818 | 2 674 228 |  |

Source: South East Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Corporate – City of Melbourne (Melbourne) | 6 158 | 6 158 | qtr 4 2025-26 |
| This is specifically related to completion of the land acquisition of Fishermans Bend, as part of wider program of Corporate – City of Melbourne (Melbourne) works. |  |  |  |
| Corporate miscellaneous – other (metropolitan various) | 17 727 | 17 727 | qtr 4 2025-26 |
| This is a completed component of a wider program of Corporate miscellaneous – other (metro various) works. |  |  |  |
| Information technology – other (metropolitan various) | 22 296 | 22 296 | qtr 4 2025-26 |
| This is a completed component of a wider program of Information technology – other (metro various) works. |  |  |  |
| Sewer and trade waste compliance – other (metropolitan various) | 35 694 | 35 694 | qtr 4 2025-26 |
| This is a completed component of a wider program of Sewer and trade waste compliance – other (metro various) works. |  |  |  |
| Sewer and trade waste growth – other (metropolitan various) | 18 454 | 18 454 | qtr 4 2025-26 |
| This is a completed component of a wider program of Sewer and trade waste growth – other (metro various) works. |  |  |  |
| Sewer and trade waste reliability – other (metropolitan various) | 26 705 | 26 705 | qtr 4 2025-26 |
| This is a completed component of a wider program of Sewer and trade waste reliability – other (metro various) works. |  |  |  |
| Water growth – other (metropolitan various) | 6 749 | 6 749 | qtr 4 2025-26 |
| This is a completed component of a wider program of Water growth – other (metro various) works. |  |  |  |
| Water reliability – other (metropolitan various) | 41 018 | 41 018 | qtr 4 2025-26 |
| This is a completed component of a wider program of Water reliability – other (metro various) works. |  |  |  |
| All remaining projects with TEI less than $1 million | 1 377 | 1 377 | qtr 4 2025-26 |

Source: South East Water Corporation

South Gippsland Region Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Baxters Beach effluent handling upgrades (Wonthaggi) | 5 950 | .. | .. | 5 950 | qtr 4 2032-33 |
| Total new projects | 5 950 | .. | .. | 5 950 |  |

Source: South Gippsland Region Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Carbon emission reduction upgrades (regional various) | 5 041 | 2 761 | 104 | 2 176 | ongoing |
| The TEI has decreased by $0.188 million due to a revised project scope. The estimated completion date has been updated to ongoing to reflect the program’s continuous nature. |  |  |  |  |  |
| Computers/supervisory control and data acquisition security system (regional various) | 12 980 | 1 121 | 1 166 | 10 693 | ongoing |
| The TEI has decreased by $1.690 million due to a revised scope. |  |  |  |  |  |
| Dams safety management renewal allocation (regional various) | 3 427 | 587 | 1 904 | 936 | ongoing |
| The TEI has decreased by $0.133 million due to a revised scope. |  |  |  |  |  |
| Emergency power program (regional various) | 1 810 | 1 340 | 470 | .. | qtr 2 2026-27 |
| The TEI has decreased by $0.127 million due to a revised scope. The estimated completion date has been revised to quarter 2 2026-27 in line with the revised delivery timeline. |  |  |  |  |  |
| Foster wastewater treatment plant reuse and pipeline (Foster) | 16 722 | 455 | 300 | 15 967 | ongoing |
| The TEI has decreased by $1.973 million due to a revised scope. |  |  |  |  |  |
| Headworks – dams (regional various) | 4 650 | .. | .. | 4 650 | qtr 4 2029-30 |
| The TEI has decreased by $0.677 million due to a revised scope. |  |  |  |  |  |
| Manholes upgrades (regional various) | 2 431 | 257 | 203 | 1 971 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Operational vehicles replacement (regional various) | 8 975 | 809 | 190 | 7 976 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Plant and equipment replacement (regional various) | 2 839 | 249 | 259 | 2 331 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Pump station upgrades (regional various) | 3 267 | 467 | 250 | 2 550 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Replacement and rehabilitation of water mains (regional various) | 26 036 | 6 306 | 2 185 | 17 545 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Reticulation sewer replacements/ rehabilitation (regional various) | 9 413 | 823 | 823 | 7 767 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Sewer network upgrade (regional various) | 48 816 | 12 820 | 2 191 | 33 805 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Sewer sidelines renewal (regional various) | 1 957 | 177 | 75 | 1 705 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| South Gippsland Water facilities renewal (regional various) | 8 534 | 1 828 | 507 | 6 199 | ongoing |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. |  |  |  |  |  |
| Venus Bay outfall renewal (Venus Bay) | 31 699 | 8 196 | 200 | 23 303 | qtr 4 2035-36 |
| The TEI has decreased by $3.286 million due to a revised project scope. The estimated completion date has been revised to quarter 4 2035-36. |  |  |  |  |  |
| Wastewater treatment plants renewal upgrade and expansion (Wonthaggi) | 111 727 | 10 609 | 1 830 | 99 288 | qtr 4 2033-34 |
| The project has been refined to specifically cover the Wonthaggi wastewater treatment plants upgrade and expansion. The TEI has increased by $7.657 million based on revised cost estimates, and the project is now classified as a one-off project. |  |  |  |  |  |
| Wastewater treatment plants upgrades (regional various) | 45 756 | 12 962 | 14 364 | 18 430 | ongoing |
| The TEI has increased by $23.927 million due to a revised project scope. The project now includes all other ongoing upgrades to the region’s wastewater treatment plants. |  |  |  |  |  |
| Water network upgrades (regional various) | 25 593 | 3 225 | 2 670 | 19 698 | ongoing |
| The TEI has decreased by $1.566 million due to a revised project scope. |  |  |  |  |  |
| Water treatment plants renewal upgrade expansion (regional various) | 47 554 | 13 171 | 7 328 | 27 055 | ongoing |
| The TEI has increased by $6.952 million due to a revised project scope. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 4 864 | 2 030 | 716 | 2 118 | ongoing |
| This includes all projects in the capital plan that are less than $1 million TEI, including revised project scopes and new projects. The TEI has decreased due to revised project scope and a number of small projects being completed in 2025-26 financial year. |  |  |  |  |  |
| Total existing projects | 424 091 | 80 193 | 37 735 | 306 163 |  |
| Total South Gippsland Region Water Corporation projects | 430 041 | 80 193 | 37 735 | 312 113 |  |

Source: South Gippsland Region Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Water treatment plant augmentation and upgrade (regional various) | 7 332 | 7 332 | qtr 4 2025-26 |
| All remaining projects with a TEI less than $1 million | 2 917 | 2 917 | qtr 4 2025-26 |

Source: South Gippsland Region Water Corporation

State Electricity Commission of Victoria

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Delburn Wind Farm (Delburn) | 789 300 | 128 692 | 511 918 | 148 690 | qtr 2 2028-29 |
| Total new projects | 789 300 | 128 692 | 511 918 | 148 690 |  |

Source: State Electricity Commission of Victoria

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Horsham Renewable Energy Park (Horsham) | 363 925 | 231 351 | 91 947 | 40 628 | qtr 2 2027-28 |
| Total existing projects | 363 925 | 231 351 | 91 947 | 40 628 |  |
| Total State Electricity Commission of Victoria projects | 1 153 225 | 360 043 | 603 865 | 189 318 |  |

Source: State Electricity Commission of Victoria

State Tolling Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| North East Link – Primary Package (Tunnels) and State Tolling Corporation (Greensborough) | 14 034 000 | 9 997 524 | 2 653 866 | 1 382 610 | qtr 2 2028-29 |
| The TEI includes the $11.100 billion contract with the Spark consortium to deliver the Primary Package as well as State and State Tolling Corporation costs associated with the delivery of the Primary Package. The Commonwealth Government is contributing $5.000 billion to the North East Link program. The TEI excludes financing costs associated with the Primary Package. The State Tolling Corporation is responsible for providing funding contributions to the ‘North East Link – Primary Package (Tunnels)’ initiative. |  |  |  |  |  |
| Total existing projects | 14 034 000 | 9 997 524 | 2 653 866 | 1 382 610 |  |
| Total State Tolling Corporation projects | 14 034 000 | 9 997 524 | 2 653 866 | 1 382 610 |  |

Source: State Tolling Corporation

Victorian Rail Track (VicTrack)

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Critical priorities for Melbourne’s tram network (metropolitan various) | 70 261 | .. | 28 785 | 41 476 | qtr 4 2028-29 |
| The TEI includes reprioritisation of $5.150 million from the Lydiard Street Level Crossing Upgrade initiative which was listed as a completed project in the 2025-26 Budget. |  |  |  |  |  |
| Improving safety and security on the regional network (regional) | 1 965 | .. | 1 790 | 175 | qtr 4 2026-27 |
| More new trains (metropolitan) | 673 607 | .. | 74 910 | 598 698 | qtr 2 2030-31 |
| The TEI includes reprioritisation of $146.000 million from the New metropolitan trains (statewide) initiative. |  |  |  |  |  |
| Next steps for future Melton Line electrification (metropolitan) | 76 350 | .. | 76 350 | .. | qtr 4 2026-27 |
| The TEI includes reprioritisation of $40.409 million from the Melton Line Upgrade (statewide) initiative. |  |  |  |  |  |
| Train station amenities clean-up and telecommunications upgrades (statewide) | 10 000 | .. | 5 000 | 5 000 | qtr 4 2027-28 |
| Regional rail freight infrastructure maintenance (statewide) | 103 061 | .. | 91 651 | 11 410 | qtr 4 2027-28 |
| Regional rail sustainability (regional) | 180 750 | .. | 139 519 | 41 231 | qtr 4 2029-30 |
| The TEI includes reprioritisation of $26.098 million from the Regional rail sustainability 2025-26 initiative. |  |  |  |  |  |
| Total new projects | 1 115 994 | .. | 418 005 | 697 990 |  |

Source: Victorian Rail Track (VicTrack)

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Albion station upgrade (Albion) | tbc | 7 000 | tbc | tbc | tbc |
| The TEI, estimated expenditure and estimated completion date will be disclosed when the procurement process is finalised. |  |  |  |  |  |
| Ballarat station upgrade (Ballarat) | 53 798 | 47 762 | 3 482 | 2 554 | qtr 3 2026-27 |
| Boronia Station upgrade (Boronia) | 81 486 | 49 428 | 22 258 | 9 799 | qtr 4 2026-27 |
| The TEI has increased by $0.136 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. |  |  |  |  |  |
| Delivering the Tram Plan (metropolitan) | 71 084 | 51 627 | 13 180 | 6 277 | qtr 3 2027-28 |
| The estimated completion date is now disclosed following the development of a revised project schedule. |  |  |  |  |  |
| E-Class Tram Infrastructure Program (metropolitan various) | 789 106 | 656 489 | 99 725 | 32 892 | qtr 4 2027-28 |
| East Pakenham Sub Station (Pakenham) | 27 520 | 2 569 | 19 953 | 4 998 | qtr 4 2026-27 |
| Enhancing safety and security on the network (regional various) | 16 386 | 11 126 | 5 259 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with a change in project commencement as a result of Australian Rail Track Corporation access issues. |  |  |  |  |  |
| Melbourne Airport Rail (metropolitan various) | tbc | 940 747 | 58 264 | tbc | tbc |
| The State and Commonwealth governments have committed $5.000 billion each to the project. In March 2025, a Memorandum of Understanding was agreed between the State, Commonwealth and Australia Pacific Airports (Melbourne), committing all parties to developing an approach to deliver the project. The TEI, future estimated cash flows, and the estimated completion date for the project will be disclosed once project details are finalised. In March 2025, the State and Commonwealth governments jointly committed to deliver the Sunshine Station Superhub as the first stage of a rail line to Melbourne Airport and a future electrified Melton Line. To progress Sunshine Station Superhub the Commonwealth has committed an additional $2.000 billion and the State Government has brought forward $2.000 billion. |  |  |  |  |  |
| Melton Line upgrade (statewide) | 600 591 | 138 045 | 182 162 | 280 384 | qtr 2 2027-28 |
| The TEI has decreased by $40.409 million which has been reprioritised to the Next steps for future Melton Line electrification (metropolitan) initiative. The estimated completion date has been revised to quarter 2 2027-28 in line with a revised forecast for practical completion obtained after contract award. The TEI includes $325.000 million of Commonwealth Government funding. This initiative is part of Labor’s Financial Statement 2022. |  |  |  |  |  |
| Mernda Stabling Yard (metropolitan) | 58 758 | 7 913 | 50 205 | 640 | qtr 3 2026-27 |
| Metro Tunnel Readiness (metropolitan) | 414 675 | 373 489 | 39 186 | 2 000 | qtr 2 2027-28 |
| The TEI has increased by $14.100 million due to funding previously published separately for the ‘Switching on the Metro Tunnel’ initiative. The estimated completion date has been revised to quarter 2 2027-28 in line with complex electrical works for the North Melbourne electrical intake substation project. |  |  |  |  |  |
| Metropolitan train infrastructure renewal program (metropolitan various) | 549 497 | 113 238 | 110 874 | 325 385 | qtr 4 2030-31 |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for metropolitan train infrastructure renewals from 2025-26 to 2030-31. |  |  |  |  |  |
| Metropolitan tram infrastructure renewal program (metropolitan various) | 407 183 | 97 024 | 57 252 | 252 907 | qtr 4 2030-31 |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for tram infrastructure renewals from 2025-26 to 2030-31. |  |  |  |  |  |
| Minor capital works fund (metropolitan various) | 62 164 | 11 115 | 11 049 | 40 000 | qtr 4 2030-31 |
| As a rolling program of works, the TEI and estimated completion date varies from year to year. The TEI incorporates all capital funding for railway minor capital works from 2025-26 to 2030-31. |  |  |  |  |  |
| Modernise the Digital Train Radio System (metropolitan) | 179 908 | 29 921 | 28 436 | 121 551 | qtr 2 2030-31 |
| More freight by rail 2025-26 (regional) | 82 389 | 75 536 | 6 853 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with the purchase of long lead time items for the 2026-27 major periodic maintenance program. |  |  |  |  |  |
| More VLocity trains 2023-24 (regional) | 570 759 | 531 187 | 19 745 | 19 826 | qtr 4 2027-28 |
| Murray Basin Rail Project (regional various) | 840 022 | 813 930 | 12 266 | 13 827 | qtr 1 2026-27 |
| The TEI has decreased by $0.289 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $528.116 million of Commonwealth Government funding. |  |  |  |  |  |
| New metropolitan trains (statewide) | 839 849 | 375 042 | 138 979 | 325 828 | qtr 3 2027-28 |
| The TEI has decreased by $146.000 million which has been reprioritised to the More new trains (metropolitan) initiative. |  |  |  |  |  |
| New Tarneit railway station (Tarneit) | 163 406 | 109 127 | 42 876 | 11 403 | qtr 3 2026-27 |
| New trains for Sunbury (metropolitan various) | 1 735 358 | 1 557 318 | 178 041 | .. | qtr 2 2026-27 |
| Next Generation Trams (metropolitan various) | 1 436 476 | 427 428 | 181 129 | 827 920 | qtr 4 2028-29 |
| The TEI has decreased by $3.367 million due to reprioritisation of savings to the Tram infrastructure upgrades (metropolitan various) initiative. |  |  |  |  |  |
| Personal safety on the transport network (metropolitan) | 11 354 | 8 959 | 2 395 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with further priority locations that have been added to the project scope. |  |  |  |  |  |
| Preparing the network for Next Generation Trams (metropolitan various) | 166 795 | 37 306 | 114 342 | 15 147 | qtr 4 2027-28 |
| The TEI has increased by $98.056 million and the completion date has been revised to quarter 4 2027-28 to incorporate funding previously published separately for the Preparing the network for Next Generation Trams initiative announced in the 2025-26 Budget. |  |  |  |  |  |
| Public Transport Ticketing Asset Renewal (statewide) | 680 350 | 330 724 | 80 292 | 269 334 | qtr 2 2028-29 |
| Railway crossing upgrades (statewide) | 54 754 | 9 524 | 8 605 | 36 625 | qtr 4 2030-31 |
| As a rolling program of works, the TEI and estimated completion date vary from year to year. The TEI incorporates all capital funding for railway crossing upgrades from 2025-26 to 2030-31. |  |  |  |  |  |
| Regional rail network enhancements (statewide) | 80 940 | 21 698 | 58 641 | 601 | qtr 4 2026-27 |
| The TEI has increased by $20.147 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. The estimated completion date has been revised to quarter 4 2026-27 in line with the network occupation schedule. |  |  |  |  |  |
| Regional rail sustainability 2025-26 (statewide) | 123 147 | 95 157 | 27 990 | .. | qtr 4 2026-27 |
| The TEI has decreased by $26.098 million which has been reprioritised to the new Regional Rail Sustainability (regional) initiative. |  |  |  |  |  |
| Regional rail sustainability 2022-23 (statewide) | 187 590 | 183 319 | 4 271 | .. | qtr 4 2026-27 |
| The TEI has decreased by $17.036 million due to V/Line delivering its regional rail freight maintenance program below the original allocation. The estimated completion date has been revised to quarter 4 2026-27 in line with the close-out of procurement and legacy system upgrades. |  |  |  |  |  |
| Rolling stock maintenance and disposal programs (statewide) | 107 550 | 88 931 | 9 619 | 9 000 | qtr 3 2027-28 |
| The estimated completion date has been revised to quarter 3 2027-28 due to a temporary project pause during the transition from MR4 to MR5 tram franchisee period. |  |  |  |  |  |
| South Dynon Train Maintenance Facility Stage 2 (statewide) | 296 755 | 254 459 | 15 170 | 27 126 | qtr 1 2026-27 |
| Suburban Rail Loop East – Main Works (metropolitan various) | tbc | 4 584 212 | 3 193 657 | tbc | qtr 2 2035-36 |
| The Suburban Rail Loop East is expected to cost between $30.000 billion – $34.500 billion and is targeting delivery by 2035. The expected cost includes $3.610 billion (GST exclusive) for the Tunnels South contract from Cheltenham to Glen Waverley, $1.710 billion (GST exclusive) for the Tunnels North contract between Glen Waverley and Box Hill, and $6.745 billion (GST exclusive) for Linewide delivery phase activities. Contract award for the Stations works packages is expected by 2027. The TEI and remaining expenditure will be disclosed following the procurement of the remaining main works packages. The TEI includes $2.200 billion of Commonwealth Government funding for land acquisition and early works and the Commonwealth Government has committed to additional funding as part of the Federal Budget in May 2026. |  |  |  |  |  |
| Sunshine Station Masterplan (Sunshine) | tbc | tbc | tbc | tbc | tbc |
| The TEI, estimated expenditure and estimated completion date of the Sunshine Station Masterplan will be disclosed as part of further development of the Sunshine Station Superhub procurement process. |  |  |  |  |  |
| Sunshine Station Superhub (metropolitan various) | 4 140 000 | 170 118 | 730 000 | 3 239 882 | qtr 2 2030-31 |
| The TEI includes $2.000 billion of Commonwealth Government funding. |  |  |  |  |  |
| Train radio system upgrade (metropolitan) | 190 284 | 88 418 | 90 046 | 11 820 | qtr 4 2027-28 |
| Total existing projects | 52 446 036 | 12 305 343 | 5 644 801 | 34 495 893 |  |
| Total VicTrack projects | 53 562 030 | 12 305 343 | 6 062 806 | 35 193 883 |  |

Source: Victorian Rail Track (VicTrack)

Note:

(a)	Totals include expenditure for projects with ‘tbc’ TEIs and cash flows.

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Car Parks for Commuters (statewide) | 610 250 | 563 181 | qtr 2 2027-28 |
| The TEI includes $141.740 million of Commonwealth Government funding. |  |  |  |
| High Capacity Metro Trains (metropolitan various) | 2 262 256 | 2 262 256 | qtr 4 2025-26 |
| Inclusive Safe Stations for all Victorians (statewide) | 49 481 | 40 465 | qtr 3 2026-27 |
| Kananook Train Maintenance Facility Stage 2 (metropolitan) | 364 951 | 291 799 | qtr 1 2027-28 |
| The TEI has increased by $0.117 million due to budgeted amounts being reclassified as capital instead of operating expenditure, in line with accounting standards. |  |  |  |
| Metro Tunnel (metropolitan various) | 13 480 371 | 13 379 684 | qtr 2 2028-29 |
| Major construction of the Metro Tunnel is now complete. |  |  |  |
| More freight by rail 2024-25 (statewide) | 80 300 | 80 300 | qtr 4 2025-26 |
| Regional Rail Revival |  |  |  |
| Regional Rail Revival – Gippsland Line Upgrade Stage 1 (regional various) | 862 474 | 861 404 | qtr 3 2027-28 |
| The TEI has decreased by $9.710 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $732.698 million of Commonwealth Government funding. |  |  |  |
| Regional Rail Revival – Shepparton Line Upgrade – Stage 3 (Shepparton) | 402 764 | 369 336 | qtr 4 2027-28 |
| The TEI has decreased by $5.408 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $331.360 million of Commonwealth Government funding. |  |  |  |
| Regional Rail Revival – Warrnambool Line Upgrade – Stage 2 (regional various) | 265 104 | 234 609 | qtr 4 2027-28 |
| The TEI has decreased by $0.740 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. The TEI includes $224.376 million of Commonwealth Government funding. |  |  |  |
| Regional rail sustainability 2021-22 (statewide) | 436 800 | 436 800 | qtr 4 2025-26 |
| The TEI has decreased by $27.800 million due to V/Line delivering its regional rail freight maintenance program below the original allocations. |  |  |  |
| Regional rail sustainability 2023-24 (statewide) | 28 380 | 21 040 | qtr 1 2026-27 |
| Suburban Rail Loop East – Development, Initial and Early Works (metropolitan various) | 2 326 818 | 2 098 903 | qtr 4 2030-31 |
| The TEI has decreased by $44.800 million which has been reprioritised to the Suburban Rail Loop East – Main Works (metropolitan various) initiative for the Westernport-Altona-Geelong pipeline scope of works. Delivery of Suburban Rail Loop Initial and Early Works is now complete. The financial completion date aligns with the finalisation of costs for land acquired to support project delivery. |  |  |  |
| Tram infrastructure upgrades (metropolitan various) | 424 519 | 397 899 | qtr 1 2027-28 |
| The TEI has increased by $3.218 million due to $3.367 million of additional scope including an expanded solar system and inclusion of a gatehouse and tram crossover at the Maidstone Tram Maintenance facility, offset by a decrease of $0.149 million due to budgeted amounts being reclassified as operating instead of capital expenditure, in line with accounting standards. |  |  |  |

Source: Victorian Rail Track (VicTrack)

Wannon Region Water Corporation

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| CRM and Billing System | 20 214 | 5 899 | 13 878 | 437 | qtr 1 2027-28 |
| Total new projects | 20 214 | 5 899 | 13 878 | 437 |  |

Source: Wannon Region Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Clear water storage renewals (regional various) | 2 883 | 935 | 1 218 | 730 | ongoing |
| The TEI has decreased by $0.789 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Conversion of treatment plant control software (regional various) | 2 432 | 1 350 | 916 | 166 | ongoing |
| The TEI has increased by $0.310 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Effluent management investigation (Warrnambool) | 4 252 | 945 | 2 100 | 1 207 | ongoing |
| Gravity sewer mains renewals (regional various) | 7 546 | 5 614 | 999 | 933 | ongoing |
| Hopkins Point water supply – high level system (Warrnambool) | 1 700 | .. | 1 700 | .. | qtr 4 2026-27 |
| The estimated completion date has been revised to quarter 4 2026-27 in line with retendering. |  |  |  |  |  |
| Hopkins Point water supply (Warrnambool) | 3 719 | 1 134 | 2 585 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with a revised contract delivery model. |  |  |  |  |  |
| Industrial water reclamation plant lagoon 2 (Camperdown) | 1 497 | 92 | 1 405 | .. | qtr 4 2026-27 |
| The project name has changed from ‘IWRP Lagoon No.2 (Camperdown)’ when it was published in the 2025-26 Budget, to improve clarity. |  |  |  |  |  |
| Meter replacement program (regional various) | 2 063 | 1 283 | 390 | 390 | ongoing |
| Programmable logic controller and remote telemetry unit upgrades (regional various) | 4 500 | 2 537 | 388 | 1 575 | qtr 4 2027-28 |
| Quality water for Wannon (regional various) | 52 232 | 5 380 | 20 784 | 26 068 | qtr 4 2028-29 |
| Replacement vehicles – commercial (regional various) | 5 307 | 4 040 | 623 | 644 | ongoing |
| Replacement vehicles – passenger (regional various) | 1 576 | 1 355 | .. | 221 | ongoing |
| The TEI has increased by $0.289 million due to an increase in vehicle numbers and cost of vehicles. |  |  |  |  |  |
| Roof water harvesting – trunk mains and detention tanks (Warrnambool) | 3 057 | 2 558 | 499 | .. | ongoing |
| The TEI has increased by $1.135 million due to increased contributions to developer works. |  |  |  |  |  |
| Servers, data storage and data backup (regional various) | 1 416 | 1 060 | 114 | 242 | qtr 4 2028-29 |
| The TEI has increased by $0.183 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Sewer access points renewals (regional various) | 2 195 | 517 | 827 | 851 | ongoing |
| Sewer pump station renewals (regional various) | 1 149 | 829 | 121 | 199 | ongoing |
| The TEI has increased by $0.084 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Sewer treatment plant ultraviolet disinfection (Warrnambool) | 6 319 | 2 438 | 3 881 | .. | qtr 4 2026-27 |
| Ultraviolet disinfection (Camperdown, Cobden and Terang) | 3 182 | 805 | 2 377 | .. | qtr 4 2026-27 |
| Wangoom Road water tower and pump station (Warrnambool) | 7 152 | 4 991 | 2 161 | .. | qtr 1 2026-27 |
| The TEI has increased by $0.109 million due to more accurate project costs after contract award. The estimated completion date has been revised to quarter 1 2026-27 in line with management of contractors across multiple works. |  |  |  |  |  |
| Water main replacements (regional various) | 5 879 | 2 489 | 2 060 | 1 330 | ongoing |
| The TEI has decreased by $0.050 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Water pump station renewals (regional various) | 1 069 | 615 | 194 | 260 | ongoing |
| The TEI has decreased by $0.306 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Water reclamation plant renewals (regional various) | 4 134 | 2 457 | 928 | 749 | ongoing |
| The TEI has decreased by $0.097 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| Water treatment plant renewals (regional various) | 2 947 | 1 959 | 538 | 450 | ongoing |
| The TEI has increased by $0.127 million due to the reprioritisation of project delivery across the service region. |  |  |  |  |  |
| WISER program – Gellibrand River Restoration and Supply Resilience | 10 094 | 1 569 | 8 525 | .. | qtr 4 2027-28 |
| This project was not disclosed in the 2025-26 Budget, as at the time of preparation the project was contingent on funding being approved. |  |  |  |  |  |
| Wyatt Street – infrastructure refurbishment (Portland) | 1 077 | 100 | .. | 977 | qtr 4 2027-28 |
| The estimated completion date has been revised to quarter 4 2027-28, as it is subject to the delivery timing of the Quality Water for Wannon project |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 8 432 | 3 499 | 2 170 | 2 763 | ongoing |
| The TEI has increased by $3.857 million due to new projects less than $1 million commencing. |  |  |  |  |  |
| Total existing projects | 147 809 | 50 551 | 57 503 | 39 755 |  |
| Total Wannon Region Water Corporation projects | 168 023 | 56 450 | 71 381 | 40 192 |  |

Source: Wannon Region Water Corporation

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Brierly Basin floating solar installation (Warrnambool) | 2 740 | 2 740 | qtr 4 2025-26 |
| The TEI has increased by $0.168 million due to a revised project schedule. The estimated completion date has been revised to quarter 4 2025-26 due to a revised project schedule. |  |  |  |
| Water reclamation plant – augmentation (Warrnambool) | 81 881 | 81 881 | qtr 4 2025-26 |
| The TEI has increased by $0.610 million due to minor contract variations in 2025-26. |  |  |  |

Source: Wannon Region Water Corporation

Westernport Region Water Corporation

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Asset management information system upgrade (Newhaven) | 1 723 | 1 623 | 100 | .. | qtr 4 2026-27 |
| The TEI has increased by $0.095 million due to a change in scope of works. |  |  |  |  |  |
| Candowie water purification plant civil, mechanical and electrical – pricing submission 2023 (Almurta) | 1 429 | 832 | 397 | 200 | qtr 4 2027-28 |
| This project was previously included under all remaining projects with a TEI less than $1 million. The TEI has increased by $0.430 million due to a change in scope of works. |  |  |  |  |  |
| Cowes wastewater treatment plant – master plan upgrades – stage 3 (Cowes) | 5 335 | 1 189 | 2 000 | 2 146 | qtr 4 2027-28 |
| The TEI has increased by $3.703 million due to a change in scope of works. |  |  |  |  |  |
| Cowes wastewater treatment plant civil, mechanical and electrical – pricing submission 2023 (Cowes) | 1 863 | 943 | 358 | 562 | qtr 4 2027-28 |
| The TEI has increased by $0.083 million due to a change in scope of works. |  |  |  |  |  |
| Fleet and plant renewal program – pricing submission 2023 (Newhaven) | 2 501 | 1 648 | 250 | 603 | qtr 4 2027-28 |
| The TEI has decreased by $0.243 million due to a change in scope of works. |  |  |  |  |  |
| Information and communications technology road map (Newhaven) | 1 577 | 785 | 328 | 464 | qtr 4 2027-28 |
| The TEI has decreased by $0.276 million due to a change in scope of works. |  |  |  |  |  |
| Recycled water wetland storage (Corinella) | 5 035 | 1 582 | 2 750 | 703 | qtr 4 2027-28 |
| The TEI has decreased by $0.059 million due to a change in scope of works. The estimated completion date has been revised to quarter 4 2027-28 in line with a revised project schedule. |  |  |  |  |  |
| Renewable energy generation (regional various) | 1 782 | 1 684 | 98 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.113 million due to a change in scope of works. The timeline has been revised to quarter 4 2026-27 to reflect the consolidation of installation at various sites to one location. |  |  |  |  |  |
| Sewage pump station civil, mechanical and electrical – pricing submission 2023 (regional various) | 2 692 | 1 478 | 535 | 679 | qtr 4 2027-28 |
| The TEI has increased by $0.031 million due to a change in scope of works. |  |  |  |  |  |
| Sewer mains and junction renewals – pricing submission 2023 (regional various) | 1 633 | 946 | 435 | 252 | qtr 4 2027-28 |
| The TEI has increased by $0.166 million due to a change in scope of works. |  |  |  |  |  |
| Sustainable reuse and afforestation (regional various) | 1 355 | 876 | 300 | 179 | qtr 4 2027-28 |
| The TEI has increased by $0.107 million due to a change in scope of works. |  |  |  |  |  |
| Wastewater systems future – pricing submission 2023 (regional various) | 1 705 | 1 599 | 106 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.355 million due to a change in scope of works. |  |  |  |  |  |
| Water distribution and storage improvement (regional various) | 1 017 | 357 | 660 | .. | qtr 4 2026-27 |
| The TEI has decreased by $0.288 million due to a change in scope of works. |  |  |  |  |  |
| Water mains renewals – pricing submission 2023 (regional various) | 2 079 | 2 030 | .. | 49 | qtr 4 2027-28 |
| The TEI has decreased by $0.005 million due to a change in scope of works. |  |  |  |  |  |
| Water quality improvement program – stage 2 (regional various) | 2 135 | 750 | 100 | 1 285 | qtr 4 2027-28 |
| The TEI has decreased by $0.005 million due to a change in scope of works. |  |  |  |  |  |
| All remaining projects with a TEI less than $1 million | 9 588 | 5 580 | 1 637 | 2 371 | various |
| Bio gas waste to energy, building asset management and Treatment plant energy efficiency projects previously reported separately with TEI more than $1 million have been included as TEI below $1 million, due to reduced budget estimates with reduced funds being reallocated to support. |  |  |  |  |  |
| Total existing projects | 43 449 | 23 902 | 10 054 | 9 493 |  |
| Total Westernport Region Water Corporation projects | 43 449 | 23 902 | 10 054 | 9 493 |  |

Source: Westernport Region Water Corporation

Yarra Valley Water Corporation

Existing projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Community sewerage (metropolitan various) | 149 581 | 30 928 | 33 134 | 85 519 | ongoing |
| The TEI has decreased by $12.302 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Facilities (Mitcham) | 9 296 | 2 445 | 2 780 | 4 072 | ongoing |
| The TEI has increased by $2.232 million due to reprioritisation and reprofiling of facilities projects. |  |  |  |  |  |
| Information Technology – Infrastructure (Mitcham) | 197 630 | 44 077 | 50 218 | 103 334 | ongoing |
| The TEI has decreased by $6.369 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Motor vehicle fleet (metropolitan various) | 18 158 | 3 694 | 3 500 | 10 963 | ongoing |
| The TEI has decreased by $0.958 million due to reprioritisation and reprofiling of deliverables. |  |  |  |  |  |
| Sewer capacity (metropolitan various) | 33 441 | 8 610 | 5 632 | 19 199 | ongoing |
| This program name has changed from Sewer improved system capacity (metropolitan various) as reported in the 2025-26 Budget. The TEI has increased by $1.477 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Sewer growth projects (metropolitan various) | 373 650 | 43 101 | 63 455 | 267 094 | ongoing |
| The TEI has increased by $54.564 million due to reprioritisation and reprofiling of the program. This includes sewer growth projects across Beveridge, Wallan, Craigieburn, Mickleham, Kalkallo, Donnybrook, Lalor, Epping and Epping North, Mernda and Doreen. |  |  |  |  |  |
| Sewer reliability (metropolitan various) | 84 679 | 18 921 | 17 128 | 48 630 | ongoing |
| The TEI has decreased by $7.720 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Sewer reticulation main renewals (metropolitan various) | 262 852 | 49 030 | 59 708 | 154 113 | ongoing |
| The TEI has decreased by $1.496 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Sewer treatment and recycling (metropolitan various) | 186 917 | 35 083 | 43 675 | 108 159 | ongoing |
| This program name has changed from Sewage treatment and recycling (metropolitan various) as reported in the 2025-26 Budget. The TEI has decreased by $12.054 million due to revised project scopes and reprofiling of the program. |  |  |  |  |  |
| Water conservation (metropolitan various) | 16 147 | 2 000 | 6 150 | 7 997 | ongoing |
| The TEI has decreased by $8.409 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Water customer meter replacements (metropolitan various) | 310 624 | 57 857 | 64 739 | 188 028 | ongoing |
| The TEI has decreased by $2.835 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Water distribution main renewals (metropolitan various) | 134 592 | 11 827 | 36 080 | 86 685 | ongoing |
| The TEI has increased by $13.442 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Water growth projects (metropolitan various) | 574 164 | 64 592 | 111 905 | 397 667 | ongoing |
| The TEI has increased by $23.615 million due to reprioritisation and reprofiling of the program. This includes water growth projects across Beveridge, Wallan, Craigieburn, Mickleham, Kalkallo, Donnybrook, Lalor, Epping and Epping North. |  |  |  |  |  |
| Water improved quality (metropolitan various) | 60 450 | 9 844 | 13 402 | 37 204 | ongoing |
| The TEI has increased by $1.567 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Water reliability (metropolitan various) | 153 292 | 24 438 | 35 486 | 93 368 | ongoing |
| The TEI has decreased by $1.527 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Water reticulation main renewals (metropolitan various) | 248 101 | 45 858 | 53 197 | 149 046 | ongoing |
| The TEI has decreased by $11.161 million due to reprioritisation and reprofiling of the program. |  |  |  |  |  |
| Total existing projects | 2 813 574 | 452 305 | 600 189 | 1 761 078 |  |
| Total Yarra Valley Water Corporation projects | 2 813 574 | 452 305 | 600 189 | 1 761 078 |  |

Source: Yarra Valley Water Corporation

Note:

(a) 	Yarra Valley Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

Completed projects (a)

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Brushy Creek – Influent Pump Stations 1 and 2 Refurbishment (Croydon) | 1 430 | 1 430 | qtr 2 2025-26 |
| This project was previously reported under Sewer treatment and recycling program. |  |  |  |
| Brushy Creek Recycled Water Treatment Plant – Chemical Dosing Facility Upgrades (Croydon) | 3 943 | 3 943 | qtr 4 2025-26 |
| This project was previously reported under Sewer treatment and recycling program. |  |  |  |
| Maximo 2025 Upgrade (Mitcham) | 2 852 | 2 852 | qtr 3 2025-26 |
| This project was previously reported under Information Technology – Infrastructure program. |  |  |  |
| Sewer Pump Station 639 Upgrade and Rising Main (Doreen) | 11 775 | 11 775 | qtr 4 2025-26 |
| This project was previously reported under Sewer growth projects program. |  |  |  |

Source: Yarra Valley Water Corporation

Note:

(a) 	Yarra Valley Water Corporation structures its projects as programs of work, which comprise new, existing and completed projects year on year. The TEIs for the programs of work differ between budget years, as forecasts are revised monthly, and programs are prioritised to ensure projects are completed at the most appropriate time.

Other public non-financial corporations

New projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Critical asset renewals within the Great Ocean Road coast and parks (regional) | 7 850 | .. | 7 850 | .. | qtr 4 2026-27 |
| Hamer Hall infrastructure enhancements (Southbank) | 11 084 | .. | 11 084 | .. | qtr 2 2027-28 |
| Improving water quality in our alpine resorts (regional) | 5 700 | 150 | 5 000 | 550 | qtr 4 2027-28 |
| State sporting facilities maintenance and renewal program (statewide) | 20 000 | .. | 10 000 | 10 000 | qtr 4 2027-28 |
| Total new projects | 44 634 | 150 | 33 934 | 10 550 |  |

Source: Other public non-financial corporations

Existing projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Estimated expenditure 2026-27 | Remaining expenditure | Estimated completion date |
| --- | --- | --- | --- | --- | --- |
| Geelong City Deal – Apollo Bay Harbour Redevelopment (Apollo Bay) | 10 194 | 9 347 | 846 | .. | qtr 1 2026-27 |
| The estimated completion date has been revised to quarter 1 2026-27 in line with the revised grant agreement with DJSIR and updated project schedule. The TEI includes $10.194 million of Commonwealth Government funding. |  |  |  |  |  |
| Geelong City Deal – Point Grey redevelopment (Lorne) | 11 632 | 8 143 | 3 490 | .. | qtr 2 2026-27 |
| The estimated completion date has been revised to quarter 2 2026-27 in line with the revised grant agreement with DJSIR and updated project schedule. The TEI includes $9.632 million of Commonwealth Government funding. |  |  |  |  |  |
| Lakeside Trailhead and Foreshore redevelopment (Falls Creek) | 2 700 | 1 100 | 1 600 | .. | qtr 4 2026-27 |
| Melbourne Arts Precinct Transformation (Melbourne) | 1 671 006 | 784 720 | 386 129 | 500 157 | qtr 2 2028-29 |
| The TEI has increased by $96.617 million due to a $95.000 million Commonwealth Government contribution to the project and $1.617 million being reclassified as capital instead of operating expenditure, in line with accounting standards. |  |  |  |  |  |
| Melbourne Indoor Sports Centre (Albert Park) | 426 076 | 189 372 | 169 335 | 67 369 | qtr 1 2028-29 |
| The project name has changed from the ‘Albert Park Pit Building Redevelopment’ when it was published in the 2025-26 Budget. The TEI and estimated expenditure are now disclosed following the finalisation of the procurement process, and include the costs for site remediation. The new Melbourne Indoor Sports Centre is planned to be ready for the community and to host the Formula 1 Australian Grand Prix in 2028. The estimated completion date has been revised to quarter 1 2028-29 to reflect the final works relating to all year-round building use. |  |  |  |  |  |
| Total existing projects | 2 121 608 | 992 682 | 561 400 | 567 526 |  |
| Total Other PNFC projects | 2 166 242 | 992 832 | 595 334 | 578 076 |  |

Source: Other public non-financial corporations

Completed projects

($ thousand)

|  | Total estimated investment | Estimated expenditure to 30 Jun 2026 | Financial completion date |
| --- | --- | --- | --- |
| Geelong City Deal – Improvement to Tourism Infrastructure at Kennett River (Kennett River) | 3 128 | 3 128 | qtr 4 2026-27 |
| The TEI includes $2.428 million of Commonwealth Government funding. |  |  |  |
| Estimated to be completed after publication date and before 30 June 2026 |  |  |  |
| Sports Trusts Asset Maintenance and Renewal Fund (statewide) | 20 113 | 20 113 | qtr 4 2025-26 |

Source: Other public non-financial corporations

Definitions and style conventions

Budget Paper No. 4 lists ‘estimated completion date’ which is defined as the date of practical project completion. The date is reported as one of the following options:

- qtr 1 yyyy-zz – for projects expected to be completed in July, August or September of that financial year

- qtr 2 yyyy-zz – for projects expected to be completed in October, November or December of that financial year

- qtr 3 yyyy-zz – for projects expected to be completed in January, February or March of that financial year

- qtr 4 yyyy-zz – for projects expected to be completed in April, May or June of that financial year.

Figures in the tables and in the text have been rounded. Discrepancies in tables between totals and sums of components reflect rounding. Percentage changes are based on the underlying unrounded amounts.

The notation used in the tables and charts is as follows:

n.a. or na	not available or not applicable

1 billion	1 000 million

1 basis point	0.01 per cent

..	zero, or rounded to zero

tbc	to be confirmed

ongoing	continuing output, program, project etc.

(x xxx.x)	negative amount

x xxx.0	rounded amount

Please refer to the Treasury and Finance glossary for budget and financial reports at dtf.vic.gov.au for additional terms and references.